## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | Preliminaries & Site Establishment |  |  |  | 114233.62
1.1 | Establishment |  |  |  | 13709.33
1.1.1 | Environmental controls - sed. fence, shaker grid etc | item | 1 | 7727.33 | 7727.33
1.1.2 | Project signage as per spec cl 4.2 (refer dwg C-401) | each | 3 | 1994 | 5982
1.2 | Ongoing Site Costs |  |  |  | 100524.29
1.2.1 | Traffic management incl. TMP & permits | day | 17 | 1962 | 33354
1.2.2 | Site establishment, mobilisation & demob | Item | 1 | 57447.49 | 57447.49
1.2.3 | Dilapidation surveys & CCTV existing assets | item | 2.18 | 4460 | 9722.8
2 | DEMOLITION & SITE CLEARING |  |  |  | 143989.92
2.1 | Demolition & Site Clearing - Part A |  |  |  | 83662.22
2.1.1 | Clear & grub incl. removal offsite * | sqm | 7960.7 | 6.3202 | 50313.22
2.1.2 | Demolish exist. structures & cart away | item | 1 | 33349 | 33349
2.2 | Demolition & Site Clearing - Part B |  |  |  | 60327.7
2.2.1 | Remove trees incl. stump grinding (arborist sup.) | No. | 10.7 | 873.5 | 9346.45
2.2.2 | Remove exist. kerb & channel & dispose | m | 567 | 17 | 9639
2.2.3 | Strip topsoil 150mm & stockpile on site | m3 | 4155 | 9.95 | 41342.25
3 | BULK & DETAILED EARTHWORKS |  |  |  | 471674.73
3.1 | Bulk & Detailed Earthworks |  |  |  | 471674.73
3.1.1 | Excavate unsuitable mat. & replace w/ approved fill * | m³ | 977.3 | 63 | 61569.9
3.1.2 | Import & place select fill (VENM cert. req.) | m³ | 8085 | 38.5 | 311272.5
3.1.3 | Excavation in rock, Class A (jack hammer/rock saw) | m3 | 426.71 | 153.6434 | 65561.18
3.1.4 | Trim & proof roll subgrade (incl. Level 1 testing) | m² | 5522 | 6.0252 | 33271.15
4 | STRUCTURES & RETAINING |  |  |  | 434509.76
4.1 | Structures & Retaining - Part A |  |  |  | 348695.5
4.1.1 | Precast L-wall units supply & install | lm | 170 | 825.59 | 140350.3
4.1.2 | Reinforced blockwork retaining wall H<1.8m incl. found. * | m2 | 291.8 | 714 | 208345.2
4.2 | Structures & Retaining - Part B |  |  |  | 85814.26
4.2.1 | Handrail - galv. tube to AS1657 | lm | 127.43 | 339 | 43198.77
4.2.2 | Structural steel - galv. incl. shop dwgs (S&E) | tonne | 8.54 | 4990.104 | 42615.49
5 | Stormwater Drainage |  |  |  | 303941.39
5.1 | Pipelines |  |  |  | 105615.27
5.1.1 | Supply & lay 450dia RCP RRJ Cl.3 | lm | 133 | 331.68 | 44113.44
5.1.2 | Grated inlet pits SA2 type incl. lintel | each | 12.09 | 5087 | 61501.83
5.2 | Pits & Structures |  |  |  | 198326.12
5.2.1 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | m | 418.8 | 176.64 | 73976.83
5.2.2 | Junction pits 900x900 precast incl. lid | No. | 14.8 | 4599.4688 | 68072.14
5.2.3 | GPT unit supply & install (Rocla CDS or approved equiv.) | item | 1.77 | 31795 | 56277.15
6 | LANDSCAPING & URBAN DESIGN |  |  |  | 200784.91
6.1 | Landscaping & Urban Design - Part A |  |  |  | 111564.09
6.1.1 | Turf - kikuyu rolls incl. estab. watering 12wks (refer dwg C-104) | m² | 3217 | 16.5233 | 53155.46
6.1.2 | Irrigation to medians - drip incl. controller | item | 1 | 32872 | 32872
6.1.3 | Street trees 100L incl. staking, guard & 12mth maint. | No. | 67 | 381.1437 | 25536.63
6.2 | Landscaping & Urban Design - Part B |  |  |  | 89220.82
6.2.1 | Garden beds - mulch 75thk & planting as per LA dwgs | m² | 988 | 54.7887 | 54131.24
6.2.2 | Imported topsoil 100thk spread to verges | m3 | 2425 | 8.5823 | 20812.08
6.2.3 | Street furniture - seats, bins & bike hoops (refer dwg C-403) | LS | 1 | 14277.5 | 14277.5
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 101449
P.1 | Provisional Sums & Quantities |  |  |  | 101449
P.1.1 | Service relocations - allowance (PROV SUM) | LS | 1 | 51642.3677 | 51642.37
P.1.2 | Latent conditions allowance (PROV SUM) | LS | 1 | 13627.3647 | 13627.36
P.1.3 | Dayworks - 20t excavator incl. operator | hr | 96.33 | 201.1715 | 19378.85
P.1.4 | Dayworks - labourer incl. small tools | hrs | 181 | 92.82 | 16800.42
|  |  |  | TOTAL | 1770583.33

## Budget
Stockton Foreshore Protection Works - Stage 1
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: City of Newcastle |  | Prepared: 6/07/2026 ¦ Rev A ¦ S. Nguyen
Budget method: WBS / Resource Breakdown
Item Code | Description | Resource Category | BOQ ($) | Budget ($) | Notes
1.1.1 | Environmental controls - sed. fence, shaker grid etc | Labour | 3074 | 2589
|  | Miscellaneous | 2798 | 2357
|  | Plant and Equipment | 1855.33 | 1562 | check qty vs dwg rev D
| 1.1.1 subtotal |  | 7727.33 | 6508
1.1.2 | Project signage as per spec cl 4.2 (refer dwg C-401) | Labour | 3164 | 2559 | carried from tender est.
|  | Miscellaneous | 2818 | 2279
| 1.1.2 subtotal |  | 5982 | 4838
1.2.1 | Traffic management incl. TMP & permits | Labour | 13995 | 11172
|  | Miscellaneous | 9325 | 7444
|  | Plant and Equipment | 6118 | 4884 | PC sum
|  | Subcontract | 3916 | 3127
| 1.2.1 subtotal |  | 33354 | 26627
1.2.2 | Site establishment, mobilisation & demob | Labour | 23470 | 19208 | rate ex GST
|  | Miscellaneous | 16704 | 13671
|  | Plant and Equipment | 11634 | 9522
|  | Subcontract | 5639.49 | 4614
| 1.2.2 subtotal |  | 57447.49 | 47015
1.2.3 | Dilapidation surveys & CCTV existing assets | Labour | 3646 | 2981
|  | Miscellaneous | 2648 | 2165
|  | Plant and Equipment | 2349 | 1920
|  | Subcontract | 1079.8 | 884 | rate ex GST
| 1.2.3 subtotal |  | 9722.8 | 7950
2.1.1 | Clear & grub incl. removal offsite * | Plant and Equipment | 27681 | 22846 | quote expires 30/7
|  | Labour | 11943 | 9857
|  | Subcontract | 10689.22 | 8823
| 2.1.1 subtotal |  | 50313.22 | 41526
2.1.2 | Demolish exist. structures & cart away | Plant and Equipment | 17605 | 14385
|  | Labour | 8141 | 6652
|  | Subcontract | 5748 | 4696 | carried from tender est.
|  | Miscellaneous | 1855 | 1517
| 2.1.2 subtotal |  | 33349 | 27250
2.2.1 | Remove trees incl. stump grinding (arborist sup.) | Plant and Equipment | 5245 | 4406
|  | Labour | 2261 | 1899
|  | Subcontract | 1840.45 | 1547
| 2.2.1 subtotal |  | 9346.45 | 7852
2.2.2 | Remove exist. kerb & channel & dispose | Plant and Equipment | 6084 | 5340
|  | Labour | 3555 | 3121
| 2.2.2 subtotal |  | 9639 | 8461
2.2.3 | Strip topsoil 150mm & stockpile on site | Plant and Equipment | 26610 | 22678
|  | Labour | 14732.25 | 12556
| 2.2.3 subtotal |  | 41342.25 | 35234
3.1.1 | Excavate unsuitable mat. & replace w/ approved fill * | Plant and Equipment | 45125 | 36646
|  | Labour | 16444.9 | 13354
| 3.1.1 subtotal |  | 61569.9 | 50000
3.1.2 | Import & place select fill (VENM cert. req.) | Plant and Equipment | 198875 | 168096 | allow for wet weather
|  | Labour | 72706 | 61454
|  | Material | 39691.5 | 33548
| 3.1.2 subtotal |  | 311272.5 | 263098
3.1.3 | Excavation in rock, Class A (jack hammer/rock saw) | Plant and Equipment | 36239 | 31369
|  | Labour | 18278 | 15822
|  | Material | 11044.18 | 9559
| 3.1.3 subtotal |  | 65561.18 | 56750
3.1.4 | Trim & proof roll subgrade (incl. Level 1 testing) | Plant and Equipment | 20923 | 17315
|  | Labour | 7886 | 6526
|  | Material | 4462.15 | 3692
| 3.1.4 subtotal |  | 33271.15 | 27533
4.1.1 | Precast L-wall units supply & install | Subcontract | 58261 | 47094
|  | Material | 45682 | 36926
|  | Labour | 24278 | 19625
|  | Plant and Equipment | 12129.3 | 9805 | quote expires 30/7
| 4.1.1 subtotal |  | 140350.3 | 113450
4.1.2 | Reinforced blockwork retaining wall H<1.8m incl. found. * | Subcontract | 98578 | 79591 | site mtg 2/7 - qty TBC w/ super
|  | Material | 75349 | 60837 | incl. cartage
|  | Labour | 34418.2 | 27789
| 4.1.2 subtotal |  | 208345.2 | 168217
4.2.1 | Handrail - galv. tube to AS1657 | Subcontract | 24443 | 20540 | incl. cartage
|  | Material | 18755.77 | 15760
| 4.2.1 subtotal |  | 43198.77 | 36300
4.2.2 | Structural steel - galv. incl. shop dwgs (S&E) | Subcontract | 19620 | 15202
|  | Material | 14826 | 11488
|  | Labour | 8169.49 | 6329
| 4.2.2 subtotal |  | 42615.49 | 33019
5.1.1 | Supply & lay 450dia RCP RRJ Cl.3 | Material | 18789 | 15204
|  | Labour | 13313 | 10772 | incl. cartage
|  | Plant and Equipment | 12011.44 | 9719 | rate ex GST
| 5.1.1 subtotal |  | 44113.44 | 35695
5.1.2 | Grated inlet pits SA2 type incl. lintel | Material | 39164 | 31742
|  | Labour | 22337.83 | 18104
| 5.1.2 subtotal |  | 61501.83 | 49846
5.2.1 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | Material | 34419 | 27684
|  | Labour | 21151 | 17012
|  | Plant and Equipment | 18406.83 | 14804
| 5.2.1 subtotal |  | 73976.83 | 59500
5.2.2 | Junction pits 900x900 precast incl. lid | Material | 30468 | 25728 | check qty vs dwg rev D
|  | Labour | 20432 | 17254
|  | Plant and Equipment | 17172.14 | 14500
| 5.2.2 subtotal |  | 68072.14 | 57482
5.2.3 | GPT unit supply & install (Rocla CDS or approved equiv.) | Material | 27576 | 21879
|  | Labour | 15617 | 12390 | allow for wet weather
|  | Plant and Equipment | 13084.15 | 10381
| 5.2.3 subtotal |  | 56277.15 | 44650
6.1.1 | Turf - kikuyu rolls incl. estab. watering 12wks (refer dwg C-104) | Subcontract | 29714 | 22397
|  | Material | 14941 | 11262
|  | Labour | 8500.46 | 6407
| 6.1.1 subtotal |  | 53155.46 | 40066
6.1.2 | Irrigation to medians - drip incl. controller | Subcontract | 17723 | 13559
|  | Material | 8511 | 6512 | incl. cartage
|  | Labour | 6638 | 5079
| 6.1.2 subtotal |  | 32872 | 25150
6.1.3 | Street trees 100L incl. staking, guard & 12mth maint. | Subcontract | 14672 | 12509
|  | Material | 6826 | 5820
|  | Labour | 4038.63 | 3442 | check qty vs dwg rev D
| 6.1.3 subtotal |  | 25536.63 | 21771
6.2.1 | Garden beds - mulch 75thk & planting as per LA dwgs | Subcontract | 35524 | 28473
|  | Material | 18607.24 | 14915
| 6.2.1 subtotal |  | 54131.24 | 43388
6.2.2 | Imported topsoil 100thk spread to verges | Subcontract | 11624 | 9662
|  | Material | 5661 | 4705
|  | Labour | 3527.08 | 2932
| 6.2.2 subtotal |  | 20812.08 | 17299
6.2.3 | Street furniture - seats, bins & bike hoops (refer dwg C-403) | Subcontract | 8260 | 7116 | sub quote - CivilTech 14/6
|  | Material | 3762 | 3241
|  | Labour | 2255.5 | 1943
| 6.2.3 subtotal |  | 14277.5 | 12300