## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | PRELIMINARIES & SITE ESTABLISHMENT |  |  |  | 168448.76
1.1 | Establishment |  |  |  | 59196.11
1.1.1 | Environmental controls - sed. fence, shaker grid etc | LS | 1 | 12004.55 | 12004.55
1.1.2 | Site establishment, mobilisation & demob | item | 1 | 47191.56 | 47191.56
1.2 | Ongoing Site Costs |  |  |  | 109252.65
1.2.1 | Site office, amenities & temp fencing | week | 27.6 | 2046.87 | 56493.61
1.2.2 | Traffic management incl. TMP & permits | item | 10.39 | 3755 | 39014.45
1.2.3 | Survey & set-out (all works) (refer dwg C-309) | LS | 1 | 13744.59 | 13744.59
2 | Bulk & Detailed Earthworks |  |  |  | 230932.4
2.1 | Bulk Earthworks |  |  |  | 59250.4
2.1.1 | Excavation in rock, Class A (jack hammer/rock saw) | m3 | 156 | 157.9641 | 24642.4
2.1.2 | Batter shaping & topsoil respread 100mm | m2 | 7210 | 4.8 | 34608
2.2 | Detailed Earthworks |  |  |  | 171682
2.2.1 | Excavate unsuitable mat. & replace w/ approved fill | m3 | 738 | 55 | 40590
2.2.2 | Import & place select fill (VENM cert. req.) | m³ | 2521 | 52 | 131092
3 | Concrete Works |  |  |  | 825149.17
3.1 | Concrete Works |  |  |  | 825149.17
3.1.1 | Supply & place N32 conc. footings incl. exc. & reo | m³ | 294.48 | 449 | 132221.52
3.1.2 | Supply & fix reinforcement (all grades) | tonne | 16 | 2216 | 35456
3.1.3 | Kerb & channel B2 barrier type (machine extruded) | LM | 1805 | 62.61 | 113011.05
3.1.4 | Supply & place N40 slab on grade 200thk incl. SL82 | m2 | 2920 | 116.5 | 340180
3.1.5 | Concrete footpath 125thk broom finish | m2 | 2547 | 58.4163 | 148786.32
3.1.6 | Pram ramps to AS1428.1 incl. TGSIs | each | 17.85 | 1823 | 32540.55
3.1.7 | Vehicle crossings 150thk reinforced | m² | 232 | 98.9385 | 22953.73
4 | Structures & Retaining |  |  |  | 619439.83
4.1 | Structures & Retaining |  |  |  | 619439.83
4.1.1 | Guardrail w-beam incl. terminals (public road spec) | lm | 841.5 | 150.5 | 126645.75
4.1.2 | Chainwire fencing 1.8m incl. gates | lm | 496 | 124 | 61504
4.1.3 | Reinforced blockwork retaining wall H<1.8m incl. found. | m² | 335 | 505 | 169175
4.1.4 | Precast L-wall units supply & install | lm | 106.76 | 905 | 96617.8
4.1.5 | Structural steel - galv. incl. shop dwgs (S&E) | tonne | 35.76 | 4628 | 165497.28
5 | LANDSCAPING & URBAN DESIGN |  |  |  | 175659.57
5.1 | Landscaping & Urban Design |  |  |  | 175659.57
5.1.1 | Turf - kikuyu rolls incl. estab. watering 12wks | m² | 981.82 | 15.14 | 14864.75
5.1.2 | Imported topsoil 100thk spread to verges | m3 | 7460 | 8.5 | 63410
5.1.3 | Garden beds - mulch 75thk & planting as per LA dwgs | m² | 1208.1 | 54.12 | 65382.37
5.1.4 | Street furniture - seats, bins & bike hoops * | item | 1 | 12062.87 | 12062.87
5.1.5 | Street trees 100L incl. staking, guard & 12mth maint. | No. | 34.2 | 583.0286 | 19939.58
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 125055.16
P.1 | Provisional Sums & Quantities |  |  |  | 125055.16
P.1.1 | Dayworks - project engineer | hrs | 47.4 | 151.77 | 7193.9
P.1.2 | Service relocations - allowance (PROV SUM) | LS | 1 | 53691 | 53691
P.1.3 | Dayworks - 20t excavator incl. operator | hr | 117 | 179 | 20943
P.1.4 | Latent conditions allowance (PROV SUM) | LS | 1 | 43227.26 | 43227.26
|  |  |  | TOTAL | 2144684.89

## Budget
Hume Fwy Noise Wall Package 2 (NW-07 to NW-11)
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Major Road Projects Victoria |  | Prepared: 6/07/2026 ¦ Rev B ¦ ML
Budget method: WBS / Resource Breakdown
Item Code | Description | Resource Category | BOQ ($) | Budget ($) | Notes
1.1.1 | Environmental controls - sed. fence, shaker grid etc | Labour | 5698 | 5001 | PC sum
|  | Miscellaneous | 3435 | 3015
|  | Plant and Equipment | 2871.55 | 2520
| 1.1.1 subtotal |  | 12004.55 | 10536
1.1.2 | Site establishment, mobilisation & demob | Labour | 21472 | 18655
|  | Miscellaneous | 15655 | 13601
|  | Plant and Equipment | 10064.56 | 8744
| 1.1.2 subtotal |  | 47191.56 | 41000
1.2.1 | Site office, amenities & temp fencing | Labour | 23007 | 19670
|  | Miscellaneous | 17109 | 14627
|  | Plant and Equipment | 10713 | 9159 | allow for wet weather
|  | Subcontract | 5664.61 | 4844
| 1.2.1 subtotal |  | 56493.61 | 48300
1.2.2 | Traffic management incl. TMP & permits | Labour | 17732 | 14725
|  | Miscellaneous | 12179 | 10114
|  | Plant and Equipment | 9103.45 | 7561
| 1.2.2 subtotal |  | 39014.45 | 32400
1.2.3 | Survey & set-out (all works) (refer dwg C-309) | Labour | 7651 | 6485
|  | Miscellaneous | 6093.59 | 5165
| 1.2.3 subtotal |  | 13744.59 | 11650
2.1.1 | Excavation in rock, Class A (jack hammer/rock saw) | Plant and Equipment | 12958 | 11129
|  | Labour | 5857 | 5031
|  | Material | 3354 | 2880
|  | Miscellaneous | 2473.4 | 2124
| 2.1.1 subtotal |  | 24642.4 | 21164
2.1.2 | Batter shaping & topsoil respread 100mm | Plant and Equipment | 25662 | 26611
|  | Labour | 8946 | 7778
| 2.1.2 subtotal |  | 34608 | 34389
2.2.1 | Excavate unsuitable mat. & replace w/ approved fill | Plant and Equipment | 23555 | 20079
|  | Labour | 7785 | 6636
|  | Material | 4963 | 4230
|  | Miscellaneous | 4287 | 3655
| 2.2.1 subtotal |  | 40590 | 34600
2.2.2 | Import & place select fill (VENM cert. req.) | Plant and Equipment | 79978 | 63119
|  | Labour | 30275 | 23893
|  | Material | 20839 | 16446
| 2.2.2 subtotal |  | 131092 | 103458
3.1.1 | Supply & place N32 conc. footings incl. exc. & reo | Material | 67264 | 54942
|  | Labour | 45896 | 37488
|  | Subcontract | 19061.52 | 15570
| 3.1.1 subtotal |  | 132221.52 | 108000
3.1.2 | Supply & fix reinforcement (all grades) | Material | 15744 | 13134
|  | Labour | 10829 | 9034
|  | Subcontract | 4802 | 4006
|  | Plant and Equipment | 4081 | 3403 | incl. cartage
| 3.1.2 subtotal |  | 35456 | 29577
3.1.3 | Kerb & channel B2 barrier type (machine extruded) | Material | 55332 | 46758 | check qty vs dwg rev D
|  | Equipment Hire | 41193 | 34810
|  | Subcontract | 16486.05 | 13932
| 3.1.3 subtotal |  | 113011.05 | 95500
3.1.4 | Supply & place N40 slab on grade 200thk incl. SL82 | Material | 204808 | 171286
|  | Labour | 135372 | 113216
| 3.1.4 subtotal |  | 340180 | 284502
3.1.5 | Concrete footpath 125thk broom finish | Material | 76500 | 64828
|  | Labour | 49143 | 41645
|  | Subcontract | 23143.32 | 19612 | carried from tender est.
| 3.1.5 subtotal |  | 148786.32 | 126085
3.1.6 | Pram ramps to AS1428.1 incl. TGSIs | Material | 16484 | 16580
|  | Labour | 13306.55 | 11470
| 3.1.6 subtotal |  | 29790.55 | 28050
3.1.7 | Vehicle crossings 150thk reinforced | Material | 11730 | 9991
|  | Labour | 7311 | 6227 | quote expires 30/7
|  | Subcontract | 3912.73 | 3333
| 3.1.7 subtotal |  | 22953.73 | 19551
4.1.1 | Guardrail w-beam incl. terminals (public road spec) | Subcontract | 71807 | 61490
|  | Material | 54838.75 | 46960
| 4.1.1 subtotal |  | 126645.75 | 108450
4.1.2 | Chainwire fencing 1.8m incl. gates | Subcontract | 24889 | 21272
|  | Material | 25417 | 21723
|  | Labour | 11198 | 9571
| 4.1.2 subtotal |  | 61504 | 52566
4.1.3 | Reinforced blockwork retaining wall H<1.8m incl. found. | Subcontract | 66678 | 58034
|  | Material | 53909 | 46920
|  | Labour | 32080 | 27922
|  | Plant and Equipment | 16508 | 14368
| 4.1.3 subtotal |  | 169175 | 147244
4.1.4 | Precast L-wall units supply & install | Subcontract | 37075 | 29950
|  | Material | 32555 | 26298
|  | Labour | 16400 | 13249 | sub quote - CivilTech 14/6
|  | Plant and Equipment | 10587.8 | 8553
| 4.1.4 subtotal |  | 96617.8 | 78050
4.1.5 | Structural steel - galv. incl. shop dwgs (S&E) | Subcontract | 62808 | 52330 | quote expires 30/7
|  | Material | 55951 | 46617
|  | Labour | 29765 | 24799
|  | Plant and Equipment | 16973.28 | 14141
| 4.1.5 subtotal |  | 165497.28 | 137887
5.1.1 | Turf - kikuyu rolls incl. estab. watering 12wks | Subcontract | 8560 | 7284
|  | Material | 3726 | 3170
|  | Labour | 2578.75 | 2195
| 5.1.1 subtotal |  | 14864.75 | 12649
5.1.2 | Imported topsoil 100thk spread to verges | Subcontract | 35206 | 30314
|  | Material | 16754 | 14426
|  | Labour | 11450 | 9860
| 5.1.2 subtotal |  | 63410 | 54600
5.1.3 | Garden beds - mulch 75thk & planting as per LA dwgs | Subcontract | 36745 | 30044
|  | Material | 17126 | 14003
|  | Labour | 11511.37 | 9413
| 5.1.3 subtotal |  | 65382.37 | 53460
5.1.4 | Street furniture - seats, bins & bike hoops * | Subcontract | 6426 | 5173
|  | Material | 3735 | 3006
|  | Labour | 1901.87 | 1531
| 5.1.4 subtotal |  | 12062.87 | 9710
5.1.5 | Street trees 100L incl. staking, guard & 12mth maint. | Subcontract | 11201 | 9753
|  | Material | 5579 | 4858
|  | Labour | 3159.58 | 2751 | incl. cartage
| 5.1.5 subtotal |  | 19939.58 | 17362