## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | PRELIMINARIES & SITE ESTABLISHMENT |  |  |  | 165056.36
1.1 | Preliminaries & Site Establishment |  |  |  | 165056.36
1.1.1 | Survey & set-out (all works) | LS | 1 | 8296.96 | 8296.96
1.1.2 | Traffic management incl. TMP & permits | wk | 13 | 3899 | 50687
1.1.3 | Dilapidation surveys & CCTV existing assets * | ea | 3.63 | 3526.47 | 12801.09
1.1.4 | Environmental controls - sed. fence, shaker grid etc | item | 1 | 11834 | 11834
1.1.5 | Site establishment, mobilisation & demob (refer dwg C-301) | item | 1 | 64756.069 | 64756.07
1.1.6 | Site office, amenities & temp fencing (refer dwg C-206) | wk | 19 | 877.96 | 16681.24
2 | DEMOLITION & SITE CLEARING |  |  |  | 155686.06
2.1 | Demolition & Site Clearing |  |  |  | 155686.06
2.1.1 | Clear & grub incl. removal offsite | m2 | 10521.24 | 5 | 52606.2
2.1.2 | Strip topsoil 150mm & stockpile on site | m3 | 4114.1 | 13.04 | 53647.86
2.1.3 | Demolish exist. structures & cart away * | item | 1 | 22522 | 22522
2.1.4 | Remove trees incl. stump grinding (arborist sup.) (refer dwg C-101) | No. | 13 | 2070 | 26910
3 | Concrete Works |  |  |  | 752587.83
3.1 | Concrete Works |  |  |  | 752587.83
3.1.1 | Pram ramps to AS1428.1 incl. TGSIs | No. | 8 | 2710.5 | 21684
3.1.2 | Supply & fix reinforcement (all grades) | tonne | 65 | 2437.77 | 158455.05
3.1.3 | Concrete footpath 125thk broom finish | m² | 876.89 | 86 | 75412.54
3.1.4 | Vehicle crossings 150thk reinforced | m2 | 115.5 | 83 | 9586.5
3.1.5 | Kerb & channel B2 barrier type (machine extruded) | LM | 918 | 85.88 | 78837.84
3.1.6 | Supply & place N32 conc. footings incl. exc. & reo * | m³ | 385 | 563.03 | 216766.55
3.1.7 | Supply & place N40 slab on grade 200thk incl. SL82 | sqm | 2543.7 | 75.4198 | 191845.35
4 | Flexible Pavements & Surfacing |  |  |  | 1123503.83
4.1 | Flexible Pavements & Surfacing |  |  |  | 1123503.83
4.1.1 | Supply & place DGB20 basecourse 150thk | sqm | 16249 | 18.3957 | 298911.73
4.1.2 | Supply & place DGS40 subbase 200thk compacted | m2 | 3106 | 13 | 40378
4.1.3 | Prime & 2 coat seal 14/7 (incl. sweep) | m2 | 2807 | 10 | 28070
4.1.4 | AC10 wearing course 30thk (A15E on approaches) | m2 | 5891.7 | 30.06 | 177104.5
4.1.5 | AC14 intermediate course 50thk (C320) (refer dwg C-107) | m² | 14505 | 39.92 | 579039.6
5 | STRUCTURES & RETAINING |  |  |  | 729896.92
5.1 | Structures & Retaining - Part A |  |  |  | 379660
5.1.1 | Guardrail w-beam incl. terminals (public road spec) | m | 420 | 126 | 52920
5.1.2 | Reinforced blockwork retaining wall H<1.8m incl. found. | m2 | 620 | 527 | 326740
5.2 | Structures & Retaining - Part B |  |  |  | 350236.92
5.2.1 | Precast L-wall units supply & install | m | 188.85 | 682.0343 | 128802.18
5.2.2 | Handrail - galv. tube to AS1657 | lm | 188 | 292.8186 | 55049.9
5.2.3 | Structural steel — galv. incl. shop dwgs (S&E) | t | 35.8 | 4647.6213 | 166384.84
6 | Public Utilities & Services |  |  |  | 328047.5
6.1 | Public Utilities & Services |  |  |  | 328047.5
6.1.1 | Street lighting incl. poles, luminaires & pits | each | 22.2 | 8525 | 189255
6.1.2 | Service crossings - potholing & protection (Telstra/APA) | each | 2 | 3242 | 6484
6.1.3 | DN100 PE watermain S&L incl. fittings & thrust blocks | lm | 327 | 173 | 56571
6.1.4 | Comms conduits P50 x2 incl. pits (NBN spec) | m | 1825 | 41.5 | 75737.5
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 81072.69
P.1 | Provisional Sums & Quantities |  |  |  | 81072.69
P.1.1 | Dayworks - 20t excavator incl. operator | hrs | 70 | 225 | 15750
P.1.2 | Dayworks - labourer incl. small tools | hr | 200 | 88.5 | 17700
P.1.3 | Latent conditions allowance (PROV SUM) | LS | 1 | 41226 | 41226
P.1.4 | Dayworks - project engineer | hrs | 52.6 | 121.61 | 6396.69
|  |  |  | TOTAL | 3335851.19

## Budget
Moss Vale Council Depot Upgrade - External Works
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Wingecarribee Shire Council |  | Prepared: 3/07/2026 ¦ Rev C ¦ AP
Budget method: Cost Centre / Lump Sum
Item Code | Description | Cost Centre | BOQ Amount ($) | Budget ($) | Margin (%) | Notes
1.1.1 | Survey & set-out (all works) | Overheads / Prelims | 8296.96 | 7484 | 9.798% | PC sum
1.1.2 | Traffic management incl. TMP & permits | Overheads / Prelims | 50687 | 43289 | 14.6%
1.1.3 | Dilapidation surveys & CCTV existing assets * | Overheads / Prelims | 12801.09 | 11550 | 9.773% | rate ex GST
1.1.4 | Environmental controls - sed. fence, shaker grid etc | Overheads / Prelims | 11834 | 10450 | 11.7%
1.1.5 | Site establishment, mobilisation & demob (refer dwg C-301) | Overheads / Prelims | 64756.07 | 56514 | 12.73%
1.1.6 | Site office, amenities & temp fencing (refer dwg C-206) | Overheads / Prelims | 16681.24 | 14350 | 13.98%
2.1.1 | Clear & grub incl. removal offsite | Earthworks | 52606.2 | 45832 | 12.88%
2.1.2 | Strip topsoil 150mm & stockpile on site | Earthworks | 53647.86 | 46814 | 12.74% | site mtg 2/7 - qty TBC w/ super
2.1.3 | Demolish exist. structures & cart away * | Earthworks | 22522 | 20800 | 7.646% | check qty vs dwg rev D
2.1.4 | Remove trees incl. stump grinding (arborist sup.) (refer dwg C-101) | Earthworks | 26910 | 23237 | 13.65% | carried from tender est.
3.1.1 | Pram ramps to AS1428.1 incl. TGSIs | Concrete | 21684 | 19200 | 11.46% | quote expires 30/7
3.1.2 | Supply & fix reinforcement (all grades) | Concrete | 158455.05 | 136650 | 13.76% | quote expires 30/7
3.1.3 | Concrete footpath 125thk broom finish | Concrete | 75412.54 | 67000 | 11.16%
3.1.4 | Vehicle crossings 150thk reinforced | Concrete | 9586.5 | 8571 | 10.59%
3.1.5 | Kerb & channel B2 barrier type (machine extruded) | Concrete | 78837.84 | 73460 | 6.821% | carried from tender est.
3.1.6 | Supply & place N32 conc. footings incl. exc. & reo * | Concrete | 216766.55 | 195700 | 9.719% | incl. cartage
3.1.7 | Supply & place N40 slab on grade 200thk incl. SL82 | Concrete | 191845.35 | 174900 | 8.833% | allow for wet weather
4.1.1 | Supply & place DGB20 basecourse 150thk | Pavements & Surfacing | 298911.73 | 262100 | 12.32% | rate ex GST
4.1.2 | Supply & place DGS40 subbase 200thk compacted | Pavements & Surfacing | 40378 | 35375 | 12.39% | site mtg 2/7 - qty TBC w/ super
4.1.3 | Prime & 2 coat seal 14/7 (incl. sweep) | Pavements & Surfacing | 28070 | 25600 | 8.799%
4.1.4 | AC10 wearing course 30thk (A15E on approaches) | Pavements & Surfacing | 177104.5 | 157921 | 10.83% | rate ex GST
4.1.5 | AC14 intermediate course 50thk (C320) (refer dwg C-107) | Pavements & Surfacing | 579039.6 | 519550 | 10.27% | sub quote - CivilTech 14/6
5.1.1 | Guardrail w-beam incl. terminals (public road spec) | Concrete | 52920 | 47800 | 9.675% | incl. cartage
5.1.2 | Reinforced blockwork retaining wall H<1.8m incl. found. | Concrete | 326740 | 310760 | 4.891% | incl. cartage
5.2.1 | Precast L-wall units supply & install | Concrete | 128802.18 | 114650 | 10.99%
5.2.2 | Handrail - galv. tube to AS1657 | Concrete | 55049.9 | 47570 | 13.59% | site mtg 2/7 - qty TBC w/ super
5.2.3 | Structural steel — galv. incl. shop dwgs (S&E) | Concrete | 166384.84 | 148350 | 10.84% | site mtg 2/7 - qty TBC w/ super
6.1.1 | Street lighting incl. poles, luminaires & pits | Utilities & Services | 189255 | 162303 | 14.24% | check qty vs dwg rev D
6.1.2 | Service crossings - potholing & protection (Telstra/APA) | Utilities & Services | 6484 | 5750 | 11.32% | quote expires 30/7
6.1.3 | DN100 PE watermain S&L incl. fittings & thrust blocks | Utilities & Services | 56571 | 51400 | 9.141%
6.1.4 | Comms conduits P50 x2 incl. pits (NBN spec) | Utilities & Services | 75737.5 | 68033 | 10.17% | check qty vs dwg rev D
| TOTALS |  | 3254778.5 | 2912963 | 10.5%