## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | PRELIMINARIES & SITE ESTABLISHMENT |  |  |  | 96494.79
1.1 | Preliminaries & Site Establishment |  |  |  | 96494.79
1.1.1 | Site establishment, mobilisation & demob | item | 1 | 24711.6 | 24711.6
1.1.2 | Traffic management incl. TMP & permits | wk | 11 | 1430.5 | 15735.5
1.1.3 | Survey & set-out (all works) | item | 1 | 12276.4748 | 12276.47
1.1.4 | Site office, amenities & temp fencing | wks | 25 | 1750.8488 | 43771.22
2 | BULK & DETAILED EARTHWORKS |  |  |  | 225711.33
2.1 | Bulk & Detailed Earthworks |  |  |  | 225711.33
2.1.1 | Import & place select fill (VENM cert. req.) | m³ | 2302.64 | 32.831 | 75597.97
2.1.2 | Trim & proof roll subgrade (incl. Level 1 testing) | m² | 19456 | 5.66 | 110120.96
2.1.3 | Excavation in rock, Class A (jack hammer/rock saw) | m³ | 184 | 184.5 | 33948
2.1.4 | Batter shaping & topsoil respread 100mm | m² | 1511.1 | 4 | 6044.4
3 | FLEXIBLE PAVEMENTS & SURFACING |  |  |  | 604651.15
3.1 | Flexible Pavements & Surfacing |  |  |  | 604651.15
3.1.1 | AC14 intermediate course 50thk (C320) | m² | 2695 | 42.92 | 115669.4
3.1.2 | Segmental paving to median (Urbanstone or equiv.) | m2 | 371.4 | 118 | 43825.2
3.1.3 | Supply & place DGB20 basecourse 150thk | m² | 10185 | 20 | 203700
3.1.4 | Longitudinal linemarking & RRPMs as per dwgs | lm | 2709 |  | 7070.49
3.1.5 | Supply & place DGS40 subbase 200thk compacted | m² | 17361.93 | 13.5 | 234386.06
4 | STRUCTURES & RETAINING |  |  |  | 965536.66
4.1 | Structures & Retaining - Part A |  |  |  | 692081.73
4.1.1 | Reinforced blockwork retaining wall H<1.8m incl. found. | m² | 513.88 | 576 | 295994.88
4.1.2 | Structural steel - galv. incl. shop dwgs (S&E) | t | 65 | 4878.5 | 317102.5
4.1.3 | Handrail - galv. tube to AS1657 | lm | 246 | 321.0746 | 78984.35
4.2 | Structures & Retaining - Part B |  |  |  | 273454.93
4.2.1 | Guardrail w-beam incl. terminals (public road spec) | LM | 347 | 151 | 52397
4.2.2 | Chainwire fencing 1.8m incl. gates * | m | 1095.34 | 99.5 | 108986.33
4.2.3 | Precast L-wall units supply & install * | lm | 97.2 | 1153 | 112071.6
5 | Stormwater Drainage |  |  |  | 234014.73
5.1 | Pipelines |  |  |  | 125674.4
5.1.1 | Supply & lay 450dia RCP RRJ Cl.3 (refer dwg C-107) | lm | 370 | 219.27 | 81129.9
5.1.2 | Grated inlet pits SA2 type incl. lintel | No. | 11 | 4049.5 | 44544.5
5.2 | Pits & Structures |  |  |  | 108340.33
5.2.1 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | lm | 369 | 284.5 | 104980.5
5.2.2 | Connect new line to exist. pit incl. core & benching | No. | 1.71 | 1964.815 | 3359.83
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 88606.63
P.1 | Provisional Sums & Quantities |  |  |  | 88606.63
P.1.1 | Rock excavation over & above measured qty (PROV) | m3 | 285.4 | 190 | 54226
P.1.2 | Dayworks - 20t excavator incl. operator | hr | 31.8 | 231 | 7345.8
P.1.3 | Dayworks - labourer incl. small tools | hr | 85.4 | 87.9195 | 7508.33
P.1.4 | Latent conditions allowance (PROV SUM) | LS | 1 | 15587.5 | 15587.5
P.1.5 | Dayworks - project engineer | hr | 26 | 151.5 | 3939
|  |  |  | TOTAL | 2215015.29

## Budget
Bakers Lane Bridge Approaches & Tie-ins
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Snowy Valleys Council |  | Prepared: 30/06/2026 ¦ Rev A ¦ S. Nguyen
Budget method: Cost Centre / Lump Sum
Item Code | Description | Cost Centre | BOQ Amount ($) | Budget ($) | Margin (%) | Notes
1.1.1 | Site establishment, mobilisation & demob | Overheads / Prelims | 24711.6 | 20973 | 15.13% | quote expires 30/7
1.1.2 | Traffic management incl. TMP & permits | Overheads / Prelims | 15735.5 | 13600 | 13.57% | carried from tender est.
1.1.3 | Survey & set-out (all works) | Overheads / Prelims | 12276.47 | 10850 | 11.62% | sub quote - CivilTech 14/6
1.1.4 | Site office, amenities & temp fencing |  | 43771.22 | 36768 | 16% | quote expires 30/7
2.1.1 | Import & place select fill (VENM cert. req.) | Earthworks | 75597.97 | 64250 | 15.01% | allow for wet weather
2.1.2 | Trim & proof roll subgrade (incl. Level 1 testing) | Earthworks | 110120.96 | 88950 | 19.23% | rate ex GST
2.1.3 | Excavation in rock, Class A (jack hammer/rock saw) | Plant & Equip | 33948 | 27900 | 17.82% | carried from tender est.
2.1.4 | Batter shaping & topsoil respread 100mm | Earthworks | 6044.4 | 5300 | 12.32%
3.1.1 | AC14 intermediate course 50thk (C320) | Pavements & Surfacing | 115669.4 | 97223 | 15.95% | rate ex GST
3.1.2 | Segmental paving to median (Urbanstone or equiv.) |  | 43825.2 | 37100 | 15.35%
3.1.3 | Supply & place DGB20 basecourse 150thk | Pavements & Surfacing | 203700 | 165904 | 18.55%
3.1.4 | Longitudinal linemarking & RRPMs as per dwgs | Pavements & Surfacing | 7070.49 | 6078 | 14.04% | quote expires 30/7
3.1.5 | Supply & place DGS40 subbase 200thk compacted | Pavements & Surfacing | 234386.06 | 201827 | 13.89%
4.1.1 | Reinforced blockwork retaining wall H<1.8m incl. found. | Concrete | 295994.88 | 253304 | 14.42%
4.1.2 | Structural steel - galv. incl. shop dwgs (S&E) | Concrete | 317102.5 | 282896 | 10.79%
4.1.3 | Handrail - galv. tube to AS1657 | Concrete | 78984.35 | 63611 | 19.46% | PC sum
4.2.1 | Guardrail w-beam incl. terminals (public road spec) | Concrete | 52397 | 44750 | 14.59%
4.2.2 | Chainwire fencing 1.8m incl. gates * | Concrete | 108986.33 | 96950 | 11.04% | quote expires 30/7
4.2.3 | Precast L-wall units supply & install * | Concrete | 112071.6 | 93906 | 16.21% | carried from tender est.
5.1.1 | Supply & lay 450dia RCP RRJ Cl.3 (refer dwg C-107) | Drainage | 81129.9 | 72229 | 10.97%
5.1.2 | Grated inlet pits SA2 type incl. lintel | Drainage | 44544.5 | 37308 | 16.25% | rate ex GST
5.2.1 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | Drainage | 104980.5 | 82867 | 21.06%
5.2.2 | Connect new line to exist. pit incl. core & benching | Drainage | 3359.83 | 2853 | 15.08%
| TOTALS |  | 2126408.66 | 1807397 | 15%