## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | PRELIMINARIES & SITE ESTABLISHMENT |  |  |  | 78319.75
1.1 | Preliminaries & Site Establishment |  |  |  | 78319.75
1.1.1 | Site office, amenities & temp fencing | wk | 20 | 2136.252 | 42725.04
1.1.2 | Project signage as per spec cl 4.2 | each | 3.2 | 2017 | 6454.4
1.1.3 | Dilapidation surveys & CCTV existing assets | item | 2.41 | 4941.83 | 11909.81
1.1.4 | Survey & set-out (all works) | item | 1 | 17230.5 | 17230.5
2 | DEMOLITION & SITE CLEARING |  |  |  | 138219.95
2.1 | Demolition & Site Clearing |  |  |  | 138219.95
2.1.1 | Saw cut & demolish exist. concrete pavement | m2 | 745.45 | 25 | 18636.25
2.1.2 | Remove trees incl. stump grinding (arborist sup.) | each | 21.9 | 863 | 18899.7
2.1.3 | Clear & grub incl. removal offsite | m2 | 12803 | 6.5 | 83219.5
2.1.4 | Remove exist. kerb & channel & dispose | m | 757 | 17 | 12869
2.1.5 | Strip topsoil 150mm & stockpile on site | m³ | 656.5 | 7 | 4595.5
3 | PUBLIC UTILITIES & SERVICES |  |  |  | 722297.63
3.1 | Wet Services |  |  |  | 450409.39
3.1.1 | Street lighting incl. poles, luminaires & pits | each | 20 | 7089.0107 | 141780.21
3.1.2 | DN150 PVC sewer S&L @ min grade incl. compaction test | m | 1005 | 227.74 | 228878.7
3.1.3 | Electrical conduits 100dia incl. trench & marker tape | m | 1246 | 64.0052 | 79750.48
3.2 | Dry Services / Electrical |  |  |  | 271888.24
3.2.1 | DN100 PE watermain S&L incl. fittings & thrust blocks | m | 806 | 184.67 | 148844.02
3.2.2 | Fire hydrants incl. valve & surface box | No. | 2.48 | 3281 | 8136.88
3.2.3 | Sewer maintenance holes 1050dia precast | No. | 2.1 | 8448.7789 | 17742.44
3.2.4 | Comms conduits P50 x2 incl. pits (NBN spec) | lm | 1833.3 | 53 | 97164.9
4 | CONCRETE WORKS |  |  |  | 907405.51
4.1 | Insitu Concrete |  |  |  | 349944.2
4.1.1 | Concrete footpath 125thk broom finish | m² | 2351.67 | 81.4776 | 191608.43
4.1.2 | Kerb & channel B2 barrier type (machine extruded) | m | 1690 | 80.7161 | 136410.21
4.1.3 | Vehicle crossings 150thk reinforced | m² | 259.29 | 84.56 | 21925.56
4.2 | Kerbs, Paths & Minor Conc. |  |  |  | 557461.31
4.2.1 | Supply & place N32 conc. footings incl. exc. & reo | m³ | 216.3 | 417 | 90197.1
4.2.2 | Supply & place N40 slab on grade 200thk incl. SL82 | m² | 2304.5 | 98 | 225841
4.2.3 | Pram ramps to AS1428.1 incl. TGSIs | No. | 8 | 2286.8012 | 18294.41
4.2.4 | Supply & fix reinforcement (all grades) | t | 105 | 2125.0362 | 223128.8
5 | Flexible Pavements & Surfacing |  |  |  | 1855576.11
5.1 | Flexible Pavements & Surfacing |  |  |  | 1855576.11
5.1.1 | AC10 wearing course 30thk (A15E on approaches) | m² | 12997.44 | 29.73 | 386413.89
5.1.2 | Segmental paving to median (Urbanstone or equiv.) | m² | 785 | 113.5 | 89097.5
5.1.3 | Prime & 2 coat seal 14/7 (incl. sweep) | m2 | 8920 | 8 | 71360
5.1.4 | Supply & place DGS40 subbase 200thk compacted | sqm | 20525 | 20.0976 | 412503.24
5.1.5 | Longitudinal linemarking & RRPMs as per dwgs * | m | 4698 | 4.5 | 21141
5.1.6 | Supply & place DGB20 basecourse 150thk | m2 | 17089.9 | 27 | 461427.3
5.1.7 | AC14 intermediate course 50thk (C320) | m2 | 14479 | 28.5678 | 413633.18
6 | LANDSCAPING & URBAN DESIGN |  |  |  | 101163.88
6.1 | Landscaping & Urban Design |  |  |  | 101163.88
6.1.1 | Street trees 100L incl. staking, guard & 12mth maint. | ea | 79 | 675 | 53325
6.1.2 | Garden beds - mulch 75thk & planting as per LA dwgs | m2 | 124 | 80 | 9920
6.1.3 | Irrigation to medians - drip incl. controller | item | 1 | 18077.5 | 18077.5
6.1.4 | Street furniture - seats, bins & bike hoops | item | 1 | 19841.376 | 19841.38
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 87078.39
P.1 | Provisional Sums & Quantities |  |  |  | 87078.39
P.1.1 | Service relocations - allowance (PROV SUM) | LS | 1 | 40089.5 | 40089.5
P.1.2 | Dayworks - labourer incl. small tools | hrs | 239.4 | 92.18 | 22067.89
P.1.3 | Latent conditions allowance (PROV SUM) | item | 1 | 24921 | 24921
|  |  |  | TOTAL | 3890061.22

## Budget
Nowra CBD Streetscape Renewal - Stage 2 (Junction St)
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Shoalhaven City Council |  | Prepared: 23/06/2026 ¦ Rev B ¦ DK
Budget method: Cost Centre / Resource Breakdown
Item Code | Description | Cost Centre | Resource Category | BOQ ($) | Budget ($) | Notes
1.1.1 | Site office, amenities & temp fencing | Overheads / Prelims | Labour | 19133 | 16323
|  | Overheads / Prelims | Miscellaneous | 13654 | 11649
|  | Overheads / Prelims | Plant and Equipment | 9938.04 | 8478
| 1.1.1 subtotal |  |  | 42725.04 | 36450
1.1.2 | Project signage as per spec cl 4.2 | Overheads / Prelims | Labour | 2718 | 2129
|  | Overheads / Prelims | Miscellaneous | 2305 | 1805
|  | Overheads / Prelims | Plant and Equipment | 1431.4 | 1120
| 1.1.2 subtotal |  |  | 6454.4 | 5054
1.1.3 | Dilapidation surveys & CCTV existing assets | Overheads / Prelims | Labour | 4616 | 3605
|  | Overheads / Prelims | Miscellaneous | 3351 | 2617
|  | Overheads / Prelims | Plant and Equipment | 2719 | 2123
|  | Overheads / Prelims | Subcontract | 1223.81 | 955
| 1.1.3 subtotal |  |  | 11909.81 | 9300
1.1.4 | Survey & set-out (all works) | Overheads / Prelims | Labour | 6906 | 5567 | carried from tender est.
|  | Overheads / Prelims | Miscellaneous | 5241 | 4225
|  | Overheads / Prelims | Plant and Equipment | 3492 | 2814
|  | Overheads / Prelims | Subcontract | 1591.5 | 1282
| 1.1.4 subtotal |  |  | 17230.5 | 13888
2.1.1 | Saw cut & demolish exist. concrete pavement | Earthworks | Plant and Equipment | 9675 | 7632
|  | Earthworks | Labour | 4598 | 3627
|  | Earthworks | Subcontract | 4363.25 | 3441 | check qty vs dwg rev D
| 2.1.1 subtotal |  |  | 18636.25 | 14700
2.1.2 | Remove trees incl. stump grinding (arborist sup.) | Earthworks | Plant and Equipment | 9227 | 7274
|  | Earthworks | Labour | 4893 | 3857
|  | Earthworks | Subcontract | 3840 | 3027
|  | Earthworks | Miscellaneous | 939.7 | 742
| 2.1.2 subtotal |  |  | 18899.7 | 14900
2.1.3 | Clear & grub incl. removal offsite | Earthworks | Plant and Equipment | 56691 | 47311 | carried from tender est.
|  | Earthworks | Labour | 26528.5 | 22139
| 2.1.3 subtotal |  |  | 83219.5 | 69450
2.1.4 | Remove exist. kerb & channel & dispose | Earthworks | Plant and Equipment | 8667 | 7155
|  | Earthworks | Labour | 4202 | 3469
| 2.1.4 subtotal |  |  | 12869 | 10624
2.1.5 | Strip topsoil 150mm & stockpile on site | Earthworks | Plant and Equipment | 2558 | 2057
|  | Earthworks | Labour | 1204 | 968
|  | Earthworks | Subcontract | 833.5 | 670
| 2.1.5 subtotal |  |  | 4595.5 | 3695
3.1.1 | Street lighting incl. poles, luminaires & pits | Utilities & Services | Subcontract | 102156 | 85166 | incl. cartage
|  | Utilities & Services | Material | 23489 | 19582
|  | Utilities & Services | Miscellaneous | 16135.21 | 13452
| 3.1.1 subtotal |  |  | 141780.21 | 118200
3.1.2 | DN150 PVC sewer S&L @ min grade incl. compaction test | Utilities & Services | Subcontract | 194435 | 165952
|  | Utilities & Services | Material | 34443.7 | 29398 | site mtg 2/7 - qty TBC w/ super
| 3.1.2 subtotal |  |  | 228878.7 | 195350
3.1.3 | Electrical conduits 100dia incl. trench & marker tape | Utilities & Services | Subcontract | 61191 | 50738
|  | Utilities & Services | Material | 10933 | 9065
|  | Utilities & Services | Miscellaneous | 7626.48 | 6325
| 3.1.3 subtotal |  |  | 79750.48 | 66128
3.2.1 | DN100 PE watermain S&L incl. fittings & thrust blocks | Utilities & Services | Subcontract | 126385 | 109393 | carried from tender est.
|  | Utilities & Services | Material | 22459.02 | 19439
| 3.2.1 subtotal |  |  | 148844.02 | 128832
3.2.2 | Fire hydrants incl. valve & surface box | Utilities & Services | Subcontract | 6550 | 5353
|  | Utilities & Services | Material | 1586.88 | 1297
| 3.2.2 subtotal |  |  | 8136.88 | 6650
3.2.3 | Sewer maintenance holes 1050dia precast | Utilities & Services | Subcontract | 13464 | 10963
|  | Utilities & Services | Material | 2525 | 2056
|  | Utilities & Services | Miscellaneous | 1753.44 | 1427
| 3.2.3 subtotal |  |  | 17742.44 | 14446
3.2.4 | Comms conduits P50 x2 incl. pits (NBN spec) | Utilities & Services | Subcontract | 78005 | 66315
|  | Utilities & Services | Material | 19159.9 | 16289
| 3.2.4 subtotal |  |  | 97164.9 | 82604
4.1.1 | Concrete footpath 125thk broom finish | Concrete | Material | 105077 | 88401
|  | Concrete | Labour | 57556 | 48422
|  | Concrete | Subcontract | 28975.43 | 24377
| 4.1.1 subtotal |  |  | 191608.43 | 161200
4.1.2 | Kerb & channel B2 barrier type (machine extruded) | Concrete | Material | 86266 | 70829
|  | Concrete | Labour | 50144.21 | 41171
| 4.1.2 subtotal |  |  | 136410.21 | 112000
4.1.3 | Vehicle crossings 150thk reinforced | Concrete | Material | 9518 | 7526
|  | Concrete | Labour | 6236 | 4931
|  | Concrete | Subcontract | 3560 | 2816
|  | Concrete | Plant and Equipment | 2611.56 | 2065
| 4.1.3 subtotal |  |  | 21925.56 | 17338
4.2.1 | Supply & place N32 conc. footings incl. exc. & reo | Concrete | Material | 45069 | 35452
|  | Concrete | Labour | 30487 | 23981
|  | Concrete | Subcontract | 14641.1 | 11517 | allow for wet weather
| 4.2.1 subtotal |  |  | 90197.1 | 70950
4.2.2 | Supply & place N40 slab on grade 200thk incl. SL82 | Concrete | Material | 104200 | 79174
|  | Concrete | Labour | 89126 | 67721
|  | Concrete | Subcontract | 32515 | 24705
| 4.2.2 subtotal |  |  | 225841 | 171600
4.2.3 | Pram ramps to AS1428.1 incl. TGSIs | Concrete | Material | 7927 | 6521
|  | Concrete | Labour | 5877 | 4835
|  | Concrete | Subcontract | 2686 | 2210
|  | Concrete | Plant and Equipment | 1804.41 | 1484 | site mtg 2/7 - qty TBC w/ super
| 4.2.3 subtotal |  |  | 18294.41 | 15050
4.2.4 | Supply & fix reinforcement (all grades) | Concrete | Material | 135953 | 108294
|  | Concrete | Labour | 87175.8 | 69441
| 4.2.4 subtotal |  |  | 223128.8 | 177735
5.1.1 | AC10 wearing course 30thk (A15E on approaches) | Pavements & Surfacing | Subcontract | 214362 | 166175
|  | Pavements & Surfacing | Material | 95035 | 73672 | quote expires 30/7
|  | Pavements & Surfacing | Plant and Equipment | 49193 | 38135
|  | Pavements & Surfacing | Labour | 27823.89 | 21568
| 5.1.1 subtotal |  |  | 386413.89 | 299550
5.1.2 | Segmental paving to median (Urbanstone or equiv.) | Pavements & Surfacing | Subcontract | 59404 | 46404
|  | Pavements & Surfacing | Material | 17551 | 13710
|  | Pavements & Surfacing | Plant and Equipment | 12142.5 | 9486
| 5.1.2 subtotal |  |  | 89097.5 | 69600
5.1.3 | Prime & 2 coat seal 14/7 (incl. sweep) | Pavements & Surfacing | Subcontract | 44781 | 36391
|  | Pavements & Surfacing | Material | 14031 | 11402
|  | Pavements & Surfacing | Plant and Equipment | 7427 | 6036
|  | Pavements & Surfacing | Labour | 5121 | 4161
| 5.1.3 subtotal |  |  | 71360 | 57990
5.1.4 | Supply & place DGS40 subbase 200thk compacted | Pavements & Surfacing | Subcontract | 273218 | 217293
|  | Pavements & Surfacing | Material | 139285.24 | 110774
| 5.1.4 subtotal |  |  | 412503.24 | 328067
5.1.5 | Longitudinal linemarking & RRPMs as per dwgs * | Pavements & Surfacing | Subcontract | 13451 | 11278
|  | Pavements & Surfacing | Material | 5169 | 4334
|  | Pavements & Surfacing | Plant and Equipment | 2521 | 2114
| 5.1.5 subtotal |  |  | 21141 | 17726
5.1.6 | Supply & place DGB20 basecourse 150thk | Pavements & Surfacing | Subcontract | 275825 | 210671
|  | Pavements & Surfacing | Material | 99980 | 76364
|  | Pavements & Surfacing | Plant and Equipment | 51487 | 39325
|  | Pavements & Surfacing | Labour | 34135.3 | 26071 | PC sum
| 5.1.6 subtotal |  |  | 461427.3 | 352431
5.1.7 | AC14 intermediate course 50thk (C320) | Pavements & Surfacing | Subcontract | 273922 | 211782
|  | Pavements & Surfacing | Material | 93972 | 72655
|  | Pavements & Surfacing | Plant and Equipment | 45739.18 | 35363
| 5.1.7 subtotal |  |  | 413633.18 | 319800
6.1.1 | Street trees 100L incl. staking, guard & 12mth maint. | Landscaping | Subcontract | 35474 | 28007 | check qty vs dwg rev D
|  | Landscaping | Material | 17851 | 14093 | check qty vs dwg rev D
| 6.1.1 subtotal |  |  | 53325 | 42100
6.1.2 | Garden beds - mulch 75thk & planting as per LA dwgs | Landscaping | Subcontract | 5352 | 4128
|  | Landscaping | Material | 3035 | 2341
|  | Landscaping | Labour | 1533 | 1181
| 6.1.2 subtotal |  |  | 9920 | 7650
6.1.3 | Irrigation to medians - drip incl. controller | Landscaping | Subcontract | 10910 | 8873 | rate ex GST
|  | Landscaping | Material | 7167.5 | 5829
| 6.1.3 subtotal |  |  | 18077.5 | 14702
6.1.4 | Street furniture - seats, bins & bike hoops | Landscaping | Subcontract | 11440 | 9540
|  | Landscaping | Material | 5274 | 4398
|  | Landscaping | Labour | 3127.38 | 2608
| 6.1.4 subtotal |  |  | 19841.38 | 16546