## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | PRELIMINARIES & SITE ESTABLISHMENT |  |  |  | 48841.58
1.1 | Preliminaries & Site Establishment |  |  |  | 48841.58
1.1.1 | Environmental controls - sed. fence, shaker grid etc | LS | 1 | 6925.5 | 6925.5
1.1.2 | Site establishment, mobilisation & demob | Item | 1 | 22842.5087 | 22842.51
1.1.3 | Survey & set-out (all works) | item | 1 | 7219.5099 | 7219.51
1.1.4 | Dilapidation surveys & CCTV existing assets | item | 3.1 | 3823.89 | 11854.06
2 | Demolition & Site Clearing |  |  |  | 134166.26
2.1 | Demolition & Site Clearing - Part A |  |  |  | 64344.96
2.1.1 | Clear & grub incl. removal offsite | m2 | 12288.5 | 3.3 | 40552.05
2.1.2 | Remove trees incl. stump grinding (arborist sup.) | No. | 24.74 | 961.7183 | 23792.91
2.2 | Demolition & Site Clearing - Part B |  |  |  | 69821.3
2.2.1 | Remove exist. kerb & channel & dispose (refer dwg C-201) | LM | 535 | 24 | 12840
2.2.2 | Demolish exist. structures & cart away | item | 1 | 35265.5086 | 35265.51
2.2.3 | Strip topsoil 150mm & stockpile on site | m3 | 2204 | 9.8529 | 21715.79
3 | BULK & DETAILED EARTHWORKS |  |  |  | 282269.32
3.1 | Bulk Earthworks |  |  |  | 158546.36
3.1.1 | Trim & proof roll subgrade (incl. Level 1 testing) | sqm | 5774.1 | 4.8747 | 28147.01
3.1.2 | Bulk earthworks - cut to fill on site | m3 | 7670.55 | 17 | 130399.35
3.2 | Detailed Earthworks |  |  |  | 123722.96
3.2.1 | Excavate unsuitable mat. & replace w/ approved fill | m³ | 473.6 | 55.15 | 26119.04
3.2.2 | Import & place select fill (VENM cert. req.) | t | 2228.4 | 43.8 | 97603.92
4 | Stormwater Drainage |  |  |  | 290394.39
4.1 | Stormwater Drainage |  |  |  | 290394.39
4.1.1 | Precast headwall to suit 450dia (refer dwg C-209) | each | 3.33 | 3222.5 | 10730.93
4.1.2 | Grated inlet pits SA2 type incl. lintel * | each | 16 | 2973.87 | 47581.92
4.1.3 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | lm | 290 | 284 | 82360
4.1.4 | Supply & lay 450dia RCP RRJ Cl.3 | lm | 131.96 | 274.5 | 36223.02
4.1.5 | Connect new line to exist. pit incl. core & benching * | each | 7.89 | 1846.5799 | 14569.52
4.1.6 | Subsoil drainage 100dia slotted incl. sock & trench | lm | 1117 | 37.8675 | 42298
4.1.7 | Supply & lay 600dia RCP RRJ Cl.4 | lm | 129 | 439 | 56631
5 | CONCRETE WORKS |  |  |  | 507553.39
5.1 | Insitu Concrete |  |  |  | 352401.69
5.1.1 | Supply & place N40 slab on grade 200thk incl. SL82 | m2 | 1950 | 77.3342 | 150801.69
5.1.2 | Supply & fix reinforcement (all grades) (refer dwg C-101) | tonne | 96 | 2100 | 201600
5.2 | Kerbs, Paths & Minor Conc. |  |  |  | 155151.7
5.2.1 | Kerb & channel B2 barrier type (machine extruded) | lm | 1036.9 | 56.0168 | 58083.82
5.2.2 | Concrete footpath 125thk broom finish (refer dwg C-208) | m2 | 1638 | 59.26 | 97067.88
6 | FLEXIBLE PAVEMENTS & SURFACING |  |  |  | 1272469.25
6.1 | Granular Pavements |  |  |  | 422402.55
6.1.1 | AC10 wearing course 30thk (A15E on approaches) | m² | 13799 | 27.74 | 382784.26
6.1.2 | Prime & 2 coat seal 14/7 (incl. sweep) | m² | 4060 | 9.7582 | 39618.29
6.2 | Asphalt & Surfacing |  |  |  | 850066.7
6.2.1 | Supply & place DGB20 basecourse 150thk | m2 | 17050 | 24 | 409200
6.2.2 | AC14 intermediate course 50thk (C320) | m2 | 13263 | 32 | 424416
6.2.3 | Longitudinal linemarking & RRPMs as per dwgs | lm | 2350.1 | 7 | 16450.7
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 73823.23
P.1 | Provisional Sums & Quantities |  |  |  | 73823.23
P.1.1 | Dayworks - project engineer | hr | 35 | 140.8869 | 4931.04
P.1.2 | Dayworks - labourer incl. small tools | hrs | 110 | 83 | 9130
P.1.3 | Contaminated material - excavate, test & dispose (PROV) | m3 | 185.2 | 322.69 | 59762.19
|  |  |  | TOTAL | 2609517.42

## Budget
Maitland Showground Precinct - Carpark & Access
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Maitland City Council |  | Prepared: 30/06/2026 ¦ Rev C ¦ B. Harris
Budget method: Cost Centre / Resource Breakdown
Item Code | Description | Cost Centre | Resource Category | BOQ ($) | Budget ($) | Notes
1.1.1 | Environmental controls - sed. fence, shaker grid etc | Overheads / Prelims | Labour | 4141 | 3516
|  | Overheads / Prelims | Miscellaneous | 2784.5 | 2363
| 1.1.1 subtotal |  |  | 6925.5 | 5879
1.1.2 | Site establishment, mobilisation & demob | Overheads / Prelims | Labour | 9862 | 8118 | allow for wet weather
|  | Overheads / Prelims | Miscellaneous | 6133 | 5048
|  | Overheads / Prelims | Plant and Equipment | 4581 | 3771
|  | Overheads / Prelims | Subcontract | 2266.51 | 1866
| 1.1.2 subtotal |  |  | 22842.51 | 18803
1.1.3 | Survey & set-out (all works) | Overheads / Prelims | Labour | 2608 | 2114 | carried from tender est.
|  | Overheads / Prelims | Miscellaneous | 2381 | 1930
|  | Overheads / Prelims | Plant and Equipment | 1530 | 1240
|  | Overheads / Prelims | Subcontract | 700.51 | 569 | quote expires 30/7
| 1.1.3 subtotal |  |  | 7219.51 | 5853
1.1.4 | Dilapidation surveys & CCTV existing assets | Overheads / Prelims | Labour | 7108 | 5546
|  | Overheads / Prelims | Miscellaneous | 4746.06 | 3704
| 1.1.4 subtotal |  |  | 11854.06 | 9250
2.1.1 | Clear & grub incl. removal offsite | Plant & Equipment | Plant and Equipment | 20584 | 16015
|  | Labour | Labour | 10568 | 8222
|  | Earthworks | Subcontract | 7486 | 5824
|  | Earthworks | Miscellaneous | 1914.05 | 1489 | check qty vs dwg rev D
| 2.1.1 subtotal |  |  | 40552.05 | 31550
2.1.2 | Remove trees incl. stump grinding (arborist sup.) | Earthworks | Plant and Equipment | 12267 | 10965
|  | Earthworks | Labour | 6466 | 5780
|  | Earthworks | Subcontract | 5059.91 | 4523
| 2.1.2 subtotal |  |  | 23792.91 | 21268
2.2.1 | Remove exist. kerb & channel & dispose (refer dwg C-201) | Earthworks | Plant and Equipment | 6450 | 5224
|  | Earthworks | Labour | 3697 | 2994
|  | Earthworks | Subcontract | 2693 | 2182 | check qty vs dwg rev D
| 2.2.1 subtotal |  |  | 12840 | 10400
2.2.2 | Demolish exist. structures & cart away | Plant & Equipment | Plant and Equipment | 16393 | 14166
|  | Labour | Labour | 10551 | 9118 | carried from tender est.
|  | Earthworks | Subcontract | 8321.51 | 7191
| 2.2.2 subtotal |  |  | 35265.51 | 30475
2.2.3 | Strip topsoil 150mm & stockpile on site | Earthworks | Plant and Equipment | 11217 | 9883 | sub quote - CivilTech 14/6
|  | Earthworks | Labour | 5727 | 5046
|  | Earthworks | Subcontract | 3660 | 3225
|  | Earthworks | Miscellaneous | 1111.79 | 980
| 2.2.3 subtotal |  |  | 21715.79 | 19134
3.1.1 | Trim & proof roll subgrade (incl. Level 1 testing) | Earthworks | Plant and Equipment | 16321 | 14384
|  | Earthworks | Labour | 5686 | 5011
|  | Earthworks | Material | 3875 | 3415
|  | Earthworks | Miscellaneous | 2265.01 | 1996 | site mtg 2/7 - qty TBC w/ super
| 3.1.1 subtotal |  |  | 28147.01 | 24806
3.1.2 | Bulk earthworks - cut to fill on site | Earthworks | Plant and Equipment | 80132 | 68918
|  | Earthworks | Labour | 30885 | 26563
|  | Earthworks | Material | 19382.35 | 16670
| 3.1.2 subtotal |  |  | 130399.35 | 112151
3.2.1 | Excavate unsuitable mat. & replace w/ approved fill | Earthworks | Plant and Equipment | 18277 | 15569
|  | Earthworks | Labour | 7842.04 | 6681
| 3.2.1 subtotal |  |  | 26119.04 | 22250
3.2.2 | Import & place select fill (VENM cert. req.) | Earthworks | Plant and Equipment | 56864 | 48881 | allow for wet weather
|  | Earthworks | Labour | 25590 | 21997
|  | Earthworks | Material | 15149.92 | 13022
| 3.2.2 subtotal |  |  | 97603.92 | 83900
4.1.1 | Precast headwall to suit 450dia (refer dwg C-209) | Drainage | Material | 4376 | 3422
|  | Drainage | Labour | 2861 | 2237 | incl. cartage
|  | Drainage | Plant and Equipment | 2487 | 1945
|  | Drainage | Subcontract | 1006.93 | 787 | allow for wet weather
| 4.1.1 subtotal |  |  | 10730.93 | 8391
4.1.2 | Grated inlet pits SA2 type incl. lintel * | Drainage | Material | 27938 | 23486
|  | Labour | Labour | 19643.92 | 16514
| 4.1.2 subtotal |  |  | 47581.92 | 40000
4.1.3 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | Drainage | Material | 41265 | 34561
|  | Drainage | Labour | 24157 | 20232
|  | Drainage | Plant and Equipment | 16938 | 14187
| 4.1.3 subtotal |  |  | 82360 | 68980
4.1.4 | Supply & lay 450dia RCP RRJ Cl.3 | Drainage | Material | 16309 | 14028
|  | Drainage | Labour | 11306 | 9724
|  | Drainage | Plant and Equipment | 8608.02 | 7404 | quote expires 30/7
| 4.1.4 subtotal |  |  | 36223.02 | 31156
4.1.5 | Connect new line to exist. pit incl. core & benching * | Drainage | Material | 6698 | 6000
|  | Drainage | Labour | 3943 | 3532
|  | Drainage | Plant and Equipment | 3928.52 | 3518
| 4.1.5 subtotal |  |  | 14569.52 | 13050
4.1.6 | Subsoil drainage 100dia slotted incl. sock & trench | Drainage | Material | 27310 | 23280
|  | Drainage | Labour | 14988 | 12777 | carried from tender est.
| 4.1.6 subtotal |  |  | 42298 | 36057
4.1.7 | Supply & lay 600dia RCP RRJ Cl.4 | Drainage | Material | 25769 | 21932
|  | Drainage | Labour | 16369 | 13932 | allow for wet weather
|  | Drainage | Plant and Equipment | 14493 | 12336
| 4.1.7 subtotal |  |  | 56631 | 48200
5.1.1 | Supply & place N40 slab on grade 200thk incl. SL82 | Concrete | Material | 77559 | 67941
|  | Labour | Labour | 49440 | 43309
|  | Concrete | Subcontract | 23802.69 | 20850
| 5.1.1 subtotal |  |  | 150801.69 | 132100
5.1.2 | Supply & fix reinforcement (all grades) (refer dwg C-101) | Concrete | Material | 95625 | 79544
|  | Labour | Labour | 54306 | 45173
|  | Concrete | Subcontract | 27759 | 23091
|  | Plant & Equipment | Plant and Equipment | 23910 | 19888
| 5.1.2 subtotal |  |  | 201600 | 167696
5.2.1 | Kerb & channel B2 barrier type (machine extruded) | Concrete | Material | 27829 | 23118
|  | Labour | Labour | 20394 | 16942
|  | Concrete | Subcontract | 9860.82 | 8190
| 5.2.1 subtotal |  |  | 58083.82 | 48250
5.2.2 | Concrete footpath 125thk broom finish (refer dwg C-208) | Concrete | Material | 62927 | 51246
|  | Labour | Labour | 34140.88 | 27804
| 5.2.2 subtotal |  |  | 97067.88 | 79050
6.1.1 | AC10 wearing course 30thk (A15E on approaches) | Pavements & Surfacing | Subcontract | 233943 | 197175
|  | Pavements & Surfacing | Material | 98062 | 82650
|  | Plant & Equipment | Plant and Equipment | 50779.26 | 42799
| 6.1.1 subtotal |  |  | 382784.26 | 322624
6.1.2 | Prime & 2 coat seal 14/7 (incl. sweep) | Pavements & Surfacing | Subcontract | 24851 | 20198
|  | Pavements & Surfacing | Material | 9602 | 7804
|  | Plant & Equipment | Plant and Equipment | 5165.29 | 4198
| 6.1.2 subtotal |  |  | 39618.29 | 32200
6.2.1 | Supply & place DGB20 basecourse 150thk | Pavements & Surfacing | Subcontract | 306704 | 255944
|  | Pavements & Surfacing | Material | 102496 | 85532
| 6.2.1 subtotal |  |  | 409200 | 341476
6.2.2 | AC14 intermediate course 50thk (C320) | Pavements & Surfacing | Subcontract | 319340 | 273005
|  | Pavements & Surfacing | Material | 105076 | 89830
| 6.2.2 subtotal |  |  | 424416 | 362835
6.2.3 | Longitudinal linemarking & RRPMs as per dwgs | Pavements & Surfacing | Subcontract | 10353 | 9340
|  | Pavements & Surfacing | Material | 3909 | 3526
|  | Pavements & Surfacing | Plant and Equipment | 2188.7 | 1975
| 6.2.3 subtotal |  |  | 16450.7 | 14841