## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | Preliminaries & Site Establishment |  |  |  | 158001.84
1.1 | Establishment |  |  |  | 58221.36
1.1.1 | Survey & set-out (all works) | item | 1 | 10601.2286 | 10601.23
1.1.2 | Site office, amenities & temp fencing | wk | 15 | 1918.589 | 28778.84
1.1.3 | Site establishment, mobilisation & demob | LS | 1 | 18841.2883 | 18841.29
1.2 | Ongoing Site Costs |  |  |  | 99780.48
1.2.1 | Traffic management incl. TMP & permits | wk | 25.4 | 3072 | 78028.8
1.2.2 | Environmental controls - sed. fence, shaker grid etc | item | 1 | 12415.4256 | 12415.43
1.2.3 | Dilapidation surveys & CCTV existing assets (refer dwg C-206) | item | 3.5 | 2667.5 | 9336.25
2 | Demolition & Site Clearing |  |  |  | 88483.2
2.1 | Demolition & Site Clearing - Part A |  |  |  | 53210.6
2.1.1 | Remove trees incl. stump grinding (arborist sup.) (refer dwg C-101) | ea | 5.6 | 1985 | 11116
2.1.2 | Saw cut & demolish exist. concrete pavement | m² | 915.1 | 46 | 42094.6
2.2 | Demolition & Site Clearing - Part B |  |  |  | 35272.6
2.2.1 | Clear & grub incl. removal offsite | m² | 5984 | 2 | 11968
2.2.2 | Strip topsoil 150mm & stockpile on site | m3 | 2420 | 9.63 | 23304.6
3 | Bulk & Detailed Earthworks |  |  |  | 538413
3.1 | Bulk Earthworks |  |  |  | 232373.88
3.1.1 | Excavate unsuitable mat. & replace w/ approved fill | m³ | 680 | 43.5682 | 29626.38
3.1.2 | Excavation in rock, Class A (jack hammer/rock saw) | m3 | 135 | 124 | 16740
3.1.3 | Bulk earthworks - cut to fill on site | m³ | 8267 | 22.5 | 186007.5
3.2 | Detailed Earthworks |  |  |  | 306039.12
3.2.1 | Trim & proof roll subgrade (incl. Level 1 testing) | m2 | 11075.5 | 6.5 | 71990.75
3.2.2 | Batter shaping & topsoil respread 100mm | m² | 7749 | 7.92 | 61372.08
3.2.3 | Import & place select fill (VENM cert. req.) | m3 | 4655 | 37.0948 | 172676.29
4 | CONCRETE WORKS |  |  |  | 559892.74
4.1 | Concrete Works |  |  |  | 559892.74
4.1.1 | Vehicle crossings 150thk reinforced (refer dwg C-102) | m2 | 377.24 | 87.64 | 33061.31
4.1.2 | Kerb & channel B2 barrier type (machine extruded) | lm | 1515.3 | 75.5 | 114405.15
4.1.3 | Supply & fix reinforcement (all grades) | tonne | 18 | 1999.5 | 35991
4.1.4 | Supply & place N32 conc. footings incl. exc. & reo | m3 | 230 | 456.23 | 104932.9
4.1.5 | Supply & place N40 slab on grade 200thk incl. SL82 (refer dwg C-104) | sqm | 3095 | 87.7229 | 271502.38
5 | Stormwater Drainage |  |  |  | 194603.62
5.1 | Pipelines |  |  |  | 162816.98
5.1.1 | Junction pits 900x900 precast incl. lid | each | 13.05 | 4269.5 | 55716.98
5.1.2 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding (refer dwg C-204) | lm | 425 | 252 | 107100
5.2 | Pits & Structures |  |  |  | 31786.64
5.2.1 | Precast headwall to suit 450dia (refer dwg C-308) | No. | 4.2 | 6162.68 | 25883.26
5.2.2 | Connect new line to exist. pit incl. core & benching | item | 2 | 2951.69 | 5903.38
6 | Landscaping & Urban Design |  |  |  | 144556
6.1 | Landscaping & Urban Design - Part A |  |  |  | 68074.1
6.1.1 | Imported topsoil 100thk spread to verges | m3 | 2133 | 5 | 10665
6.1.2 | Turf - kikuyu rolls incl. estab. watering 12wks | m² | 1979 | 20.5 | 40569.5
6.1.3 | Irrigation to medians - drip incl. controller | LS | 1 | 16839.6 | 16839.6
6.2 | Landscaping & Urban Design - Part B |  |  |  | 76481.9
6.2.1 | Street furniture - seats, bins & bike hoops * | LS | 1 | 12797 | 12797
6.2.2 | Garden beds - mulch 75thk & planting as per LA dwgs | m2 | 735 | 41.23 | 30304.05
6.2.3 | Street trees 100L incl. staking, guard & 12mth maint. | ea | 54.9 | 608.03 | 33380.85
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 194471.25
P.1 | Provisional Sums & Quantities |  |  |  | 194471.25
P.1.1 | Dayworks - 20t excavator incl. operator | hr | 146.64 | 225.5 | 33067.32
P.1.2 | Dayworks - project engineer | hrs | 75 | 145.11 | 10883.25
P.1.3 | Latent conditions allowance (PROV SUM) | LS | 1 | 39912.6791 | 39912.68
P.1.4 | Rock excavation over & above measured qty (PROV) | m3 | 496 | 223 | 110608
|  |  |  | TOTAL | 1878421.65

## Budget
Ballina Coastal Shared Path - Stage 2
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Ballina Shire Council |  | Prepared: 6/07/2026 ¦ Rev 0 ¦ B. Harris
Budget method: Cost Centre / Lump Sum
Item Code | Description | Cost Centre | BOQ Amount ($) | Budget ($) | Margin (%) | Notes
1.1.1 | Survey & set-out (all works) | Overheads / Prelims | 10601.23 | 9150 | 13.69%
1.1.2 | Site office, amenities & temp fencing | Overheads / Prelims | 28778.84 | 26300 | 8.613% | check qty vs dwg rev D
1.1.3 | Site establishment, mobilisation & demob | Overheads / Prelims | 18841.29 | 15950 | 15.35% | site mtg 2/7 - qty TBC w/ super
1.2.1 | Traffic management incl. TMP & permits | Overheads / Prelims | 78028.8 | 65352 | 16.25% | rate ex GST
1.2.2 | Environmental controls - sed. fence, shaker grid etc | Overheads / Prelims | 12415.43 | 11150 | 10.19% | rate ex GST
1.2.3 | Dilapidation surveys & CCTV existing assets (refer dwg C-206) | Overheads / Prelims | 9336.25 | 8500 | 8.957%
2.1.1 | Remove trees incl. stump grinding (arborist sup.) (refer dwg C-101) | Earthworks | 11116 | 9450 | 14.99%
2.1.2 | Saw cut & demolish exist. concrete pavement | Earthworks | 25257 | 22711 | 10.08% | 60/40 split w/ Plant & Equipment
2.1.2 | Saw cut & demolish exist. concrete pavement | Plant & Equipment | 16837.6 | 15140 | 10.08% | 60/40 split w/ Earthworks
2.2.1 | Clear & grub incl. removal offsite | Earthworks | 11968 | 10150 | 15.19% | carried from tender est.
2.2.2 | Strip topsoil 150mm & stockpile on site | Earthworks | 23304.6 | 21400 | 8.173% | PC sum
3.1.1 | Excavate unsuitable mat. & replace w/ approved fill | Earthworks | 29626.38 | 25700 | 13.25% | allow for wet weather
3.1.2 | Excavation in rock, Class A (jack hammer/rock saw) | Earthworks | 16740 | 14408 | 13.93%
3.1.3 | Bulk earthworks - cut to fill on site | Earthworks | 186007.5 | 153595 | 17.43% | site mtg 2/7 - qty TBC w/ super
3.2.1 | Trim & proof roll subgrade (incl. Level 1 testing) | Earthworks | 57593 | 49682 | 13.74% | 80/20 split w/ Plant & Equipment
3.2.1 | Trim & proof roll subgrade (incl. Level 1 testing) | Plant & Equipment | 14397.75 | 12420 | 13.74% | 80/20 split w/ Earthworks
3.2.2 | Batter shaping & topsoil respread 100mm | Earthworks | 33755 | 31107 | 7.845% | 55/45 split w/ Plant & Equipment
3.2.2 | Batter shaping & topsoil respread 100mm | Plant & Equipment | 27617.08 | 25451 | 7.843% | 55/45 split w/ Earthworks
3.2.3 | Import & place select fill (VENM cert. req.) | Earthworks | 172676.29 | 155986 | 9.666%
4.1.1 | Vehicle crossings 150thk reinforced (refer dwg C-102) | Concrete | 33061.31 | 29051 | 12.13%
4.1.2 | Kerb & channel B2 barrier type (machine extruded) | Concrete | 91524 | 79360 | 13.29% | 80/20 split w/ Labour
4.1.2 | Kerb & channel B2 barrier type (machine extruded) | Labour | 22881.15 | 19840 | 13.29% | 80/20 split w/ Concrete
4.1.3 | Supply & fix reinforcement (all grades) | Concrete | 35991 | 31601 | 12.2% | site mtg 2/7 - qty TBC w/ super
4.1.4 | Supply & place N32 conc. footings incl. exc. & reo | Concrete | 73453 | 66862 | 8.973% | 70/30 split w/ Labour
4.1.4 | Supply & place N32 conc. footings incl. exc. & reo | Labour | 31479.9 | 28655 | 8.974% | 70/30 split w/ Concrete
4.1.5 | Supply & place N40 slab on grade 200thk incl. SL82 (refer dwg C-104) | Concrete | 271502.38 | 241150 | 11.18% | allow for wet weather
5.1.1 | Junction pits 900x900 precast incl. lid | Drainage | 33430 | 29220 | 12.59% | 60/40 split w/ Earthworks
5.1.1 | Junction pits 900x900 precast incl. lid | Earthworks | 22286.98 | 19480 | 12.59% | 60/40 split w/ Drainage
5.1.2 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding (refer dwg C-204) | Drainage | 107100 | 89750 | 16.2%
5.2.1 | Precast headwall to suit 450dia (refer dwg C-308) | Drainage | 25883.26 | 22544 | 12.9% | carried from tender est.
5.2.2 | Connect new line to exist. pit incl. core & benching | Drainage | 5903.38 | 5150 | 12.76% | rate ex GST
6.1.1 | Imported topsoil 100thk spread to verges | Landscaping | 10665 | 9450 | 11.39%
6.1.2 | Turf - kikuyu rolls incl. estab. watering 12wks | Landscaping | 22313 | 19361 | 13.23% | 55/45 split w/ Labour
6.1.2 | Turf - kikuyu rolls incl. estab. watering 12wks | Labour | 18256.5 | 15840 | 13.24% | 55/45 split w/ Landscaping
6.1.3 | Irrigation to medians - drip incl. controller | Landscaping | 16839.6 | 14800 | 12.11% | PC sum
6.2.1 | Street furniture - seats, bins & bike hoops * | Landscaping | 12797 | 11350 | 11.31%
6.2.2 | Garden beds - mulch 75thk & planting as per LA dwgs | Landscaping | 30304.05 | 26000 | 14.2% | rate ex GST
6.2.3 | Street trees 100L incl. staking, guard & 12mth maint. | Landscaping | 33380.85 | 30351 | 9.077%
| TOTALS |  | 1683950.4 | 1473417 | 12.5%