## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | PRELIMINARIES & SITE ESTABLISHMENT |  |  |  | 202539.31
1.1 | Preliminaries & Site Establishment |  |  |  | 202539.31
1.1.1 | Site establishment, mobilisation & demob | item | 1 | 35935.06 | 35935.06
1.1.2 | Traffic management incl. TMP & permits | wk | 29 | 3256.0479 | 94425.39
1.1.3 | Environmental controls - sed. fence, shaker grid etc | item | 1 | 13637.86 | 13637.86
1.1.4 | Site office, amenities & temp fencing | wks | 30 | 1851 | 55530
1.1.5 | Dilapidation surveys & CCTV existing assets | ea | 1 | 3011 | 3011
2 | Demolition & Site Clearing |  |  |  | 132616.64
2.1 | Demolition & Site Clearing |  |  |  | 132616.64
2.1.1 | Remove trees incl. stump grinding (arborist sup.) | each | 13 | 1068 | 13884
2.1.2 | Clear & grub incl. removal offsite | m² | 8575 | 3.5 | 30012.5
2.1.3 | Remove exist. kerb & channel & dispose | lm | 496 | 23 | 11408
2.1.4 | Demolish exist. structures & cart away | item | 1 | 29722 | 29722
2.1.5 | Strip topsoil 150mm & stockpile on site | m³ | 3774 | 12.61 | 47590.14
3 | BULK & DETAILED EARTHWORKS |  |  |  | 734538.54
3.1 | Bulk & Detailed Earthworks |  |  |  | 734538.54
3.1.1 | Trim & proof roll subgrade (incl. Level 1 testing) | m² | 9439.3 | 4.85 | 45780.61
3.1.2 | Excavation in rock, Class A (jack hammer/rock saw) | m³ | 545 | 102.5209 | 55873.89
3.1.3 | Bulk earthworks - cut to fill on site | m3 | 21701.66 | 14 | 303823.24
3.1.4 | Import & place select fill (VENM cert. req.) | m³ | 3947 | 44.6384 | 176187.76
3.1.5 | Batter shaping & topsoil respread 100mm | m2 | 7726 | 7.5 | 57945
3.1.6 | Excavate unsuitable mat. & replace w/ approved fill | m3 | 2375 | 39.9697 | 94928.04
4 | STORMWATER DRAINAGE |  |  |  | 270918.75
4.1 | Stormwater Drainage |  |  |  | 270918.75
4.1.1 | Precast headwall to suit 450dia | each | 6 | 3214 | 19284
4.1.2 | GPT unit supply & install (Rocla CDS or approved equiv.) * | item | 5 | 36370 | 181850
4.1.3 | Supply & lay 450dia RCP RRJ Cl.3 (refer dwg C-308) | m | 63 | 331.4088 | 20878.75
4.1.4 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | lm | 209 | 234 | 48906
5 | Concrete Works |  |  |  | 592052.36
5.1 | Concrete Works |  |  |  | 592052.36
5.1.1 | Supply & place N32 conc. footings incl. exc. & reo | m3 | 219 | 400 | 87600
5.1.2 | Supply & fix reinforcement (all grades) | tonne | 105.68 | 2377 | 251201.36
5.1.3 | Concrete footpath 125thk broom finish | m² | 2875 | 71 | 204125
5.1.4 | Pram ramps to AS1428.1 incl. TGSIs | ea | 20.3 | 2420 | 49126
6 | LANDSCAPING & URBAN DESIGN |  |  |  | 178045.42
6.1 | Landscaping & Urban Design - Part A |  |  |  | 111939.69
6.1.1 | Irrigation to medians - drip incl. controller | item | 1 | 36944.64 | 36944.64
6.1.2 | Turf - kikuyu rolls incl. estab. watering 12wks | m² | 3845.9 | 19.5 | 74995.05
6.2 | Landscaping & Urban Design - Part B |  |  |  | 66105.73
6.2.1 | Garden beds - mulch 75thk & planting as per LA dwgs | m² | 790 | 67.83 | 53585.7
6.2.2 | Street furniture - seats, bins & bike hoops | LS | 1 | 12520.03 | 12520.03
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 157005.01
P.1 | Provisional Sums & Quantities |  |  |  | 157005.01
P.1.1 | Dayworks - 20t excavator incl. operator | hrs | 146.83 | 223.5429 | 32822.8
P.1.2 | Service relocations - allowance (PROV SUM) | item | 1 | 29444 | 29444
P.1.3 | Contaminated material - excavate, test & dispose (PROV) | t | 202 | 320.1208 | 64664.4
P.1.4 | Dayworks - labourer incl. small tools | hr | 230.3 | 101.71 | 23423.81
P.1.5 | Dayworks - project engineer | hr | 50 | 133 | 6650
|  |  |  | TOTAL | 2267716.03

## Budget
Mount Barker Regional Sports Hub - Stage 1
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Mount Barker District Council |  | Prepared: 6/07/2026 ¦ Rev B ¦ S. Nguyen
Budget method: Cost Centre / Resource Breakdown
Item Code | Description | Cost Centre | Resource Category | BOQ ($) | Budget ($) | Notes
1.1.1 | Site establishment, mobilisation & demob | Overheads / Prelims | Labour | 15748 | 13795
|  | Overheads / Prelims | Miscellaneous | 12439 | 10896
|  | Overheads / Prelims | Plant and Equipment | 7748.06 | 6786 | sub quote - CivilTech 14/6
| 1.1.1 subtotal |  |  | 35935.06 | 31477
1.1.2 | Traffic management incl. TMP & permits | Overheads / Prelims | Labour | 37908 | 30591
|  | Overheads / Prelims | Miscellaneous | 28701 | 23161
|  | Overheads / Prelims | Plant and Equipment | 17405 | 14045
|  | Overheads / Prelims | Subcontract | 10411.39 | 8403
| 1.1.2 subtotal |  |  | 94425.39 | 76200
1.1.3 | Environmental controls - sed. fence, shaker grid etc | Overheads / Prelims | Labour | 5586 | 5151 | check qty vs dwg rev D
|  | Overheads / Prelims | Miscellaneous | 4564 | 4209 | incl. cartage
|  | Overheads / Prelims | Plant and Equipment | 3487.86 | 3216 | allow for wet weather
| 1.1.3 subtotal |  |  | 13637.86 | 12576
1.1.4 | Site office, amenities & temp fencing | Overheads / Prelims | Labour | 21282 | 18243
|  | Overheads / Prelims | Miscellaneous | 16061 | 13768
|  | Overheads / Prelims | Plant and Equipment | 11727 | 10052
|  | Overheads / Prelims | Subcontract | 6460 | 5537
| 1.1.4 subtotal |  |  | 55530 | 47600
1.1.5 | Dilapidation surveys & CCTV existing assets | Overheads / Prelims | Labour | 1171 | 1034 | incl. cartage
|  | Overheads / Prelims | Miscellaneous | 1110 | 980
|  | Overheads / Prelims | Plant and Equipment | 730 | 644
| 1.1.5 subtotal |  |  | 3011 | 2658
2.1.1 | Remove trees incl. stump grinding (arborist sup.) | Earthworks | Plant and Equipment | 6695 | 5859
|  | Earthworks | Labour | 3196 | 2797
|  | Earthworks | Subcontract | 3198 | 2799
|  | Earthworks | Miscellaneous | 795 | 695
| 2.1.1 subtotal |  |  | 13884 | 12150
2.1.2 | Clear & grub incl. removal offsite | Earthworks | Plant and Equipment | 14803 | 12331
|  | Earthworks | Labour | 7947 | 6620
|  | Earthworks | Subcontract | 5838 | 4863
|  | Earthworks | Miscellaneous | 1424.5 | 1186
| 2.1.2 subtotal |  |  | 30012.5 | 25000
2.1.3 | Remove exist. kerb & channel & dispose | Earthworks | Plant and Equipment | 5878 | 5115
|  | Earthworks | Labour | 3421 | 2977
|  | Earthworks | Subcontract | 2109 | 1836
| 2.1.3 subtotal |  |  | 11408 | 9928
2.1.4 | Demolish exist. structures & cart away | Earthworks | Plant and Equipment | 16721 | 14374
|  | Earthworks | Labour | 6580 | 5656
|  | Earthworks | Subcontract | 6421 | 5520
| 2.1.4 subtotal |  |  | 29722 | 25550
2.1.5 | Strip topsoil 150mm & stockpile on site | Earthworks | Plant and Equipment | 33593 | 27154
|  | Earthworks | Labour | 13997.14 | 11313
| 2.1.5 subtotal |  |  | 47590.14 | 38467
3.1.1 | Trim & proof roll subgrade (incl. Level 1 testing) | Earthworks | Plant and Equipment | 23607 | 19609
|  | Earthworks | Labour | 11288 | 9376
|  | Earthworks | Material | 6104 | 5070
|  | Earthworks | Miscellaneous | 4781.61 | 3972
| 3.1.1 subtotal |  |  | 45780.61 | 38027
3.1.2 | Excavation in rock, Class A (jack hammer/rock saw) | Earthworks | Plant and Equipment | 35216 | 30268
|  | Earthworks | Labour | 12391 | 10650
|  | Earthworks | Material | 8266.89 | 7105
| 3.1.2 subtotal |  |  | 55873.89 | 48023
3.1.3 | Bulk earthworks - cut to fill on site | Earthworks | Plant and Equipment | 171427 | 140325
|  | Earthworks | Labour | 63292 | 51809 | incl. cartage
|  | Earthworks | Material | 38997 | 31922
|  | Earthworks | Miscellaneous | 30107.24 | 24644
| 3.1.3 subtotal |  |  | 303823.24 | 248700
3.1.4 | Import & place select fill (VENM cert. req.) | Earthworks | Plant and Equipment | 98782 | 78335
|  | Earthworks | Labour | 46935 | 37220 | carried from tender est.
|  | Earthworks | Material | 30470.76 | 24163
| 3.1.4 subtotal |  |  | 176187.76 | 139718
3.1.5 | Batter shaping & topsoil respread 100mm | Earthworks | Plant and Equipment | 36235 | 30957
|  | Earthworks | Labour | 13323 | 11383
|  | Earthworks | Material | 8387 | 7165
| 3.1.5 subtotal |  |  | 57945 | 49505
3.1.6 | Excavate unsuitable mat. & replace w/ approved fill | Earthworks | Plant and Equipment | 59379 | 49166 | sub quote - CivilTech 14/6
|  | Earthworks | Labour | 22187 | 18370
|  | Earthworks | Material | 13362.04 | 11064 | PC sum
| 3.1.6 subtotal |  |  | 94928.04 | 78600
4.1.1 | Precast headwall to suit 450dia | Drainage | Material | 12058 | 10317
|  | Drainage | Labour | 7226 | 6183
| 4.1.1 subtotal |  |  | 19284 | 16500
4.1.2 | GPT unit supply & install (Rocla CDS or approved equiv.) * | Drainage | Material | 118132 | 98666 | site mtg 2/7 - qty TBC w/ super
|  | Drainage | Labour | 63718 | 53219
| 4.1.2 subtotal |  |  | 181850 | 151885
4.1.3 | Supply & lay 450dia RCP RRJ Cl.3 (refer dwg C-308) | Drainage | Material | 9918 | 8565
|  | Drainage | Labour | 6291 | 5433
|  | Drainage | Plant and Equipment | 4669.75 | 4033
| 4.1.3 subtotal |  |  | 20878.75 | 18031
4.1.4 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | Drainage | Material | 19959 | 16172
|  | Drainage | Labour | 14676 | 11891
|  | Drainage | Plant and Equipment | 9946 | 8059
|  | Drainage | Subcontract | 4325 | 3504
| 4.1.4 subtotal |  |  | 48906 | 39626
5.1.1 | Supply & place N32 conc. footings incl. exc. & reo | Concrete | Material | 45577 | 37876
|  | Concrete | Labour | 28838 | 23966
|  | Concrete | Subcontract | 13185 | 10958
| 5.1.1 subtotal |  |  | 87600 | 72800
5.1.2 | Supply & fix reinforcement (all grades) | Concrete | Material | 152573 | 128977
|  | Concrete | Labour | 98628.36 | 83375
| 5.1.2 subtotal |  |  | 251201.36 | 212352
5.1.3 | Concrete footpath 125thk broom finish | Concrete | Material | 93064 | 77399
|  | Concrete | Labour | 57981 | 48221
|  | Concrete | Subcontract | 33351 | 27737
|  | Concrete | Plant and Equipment | 19729 | 16408 | site mtg 2/7 - qty TBC w/ super
| 5.1.3 subtotal |  |  | 204125 | 169765
5.1.4 | Pram ramps to AS1428.1 incl. TGSIs | Concrete | Material | 32089 | 28200 | quote expires 30/7
|  | Concrete | Labour | 17037 | 14972
| 5.1.4 subtotal |  |  | 49126 | 43172
6.1.1 | Irrigation to medians - drip incl. controller | Landscaping | Subcontract | 24014 | 20526
|  | Landscaping | Material | 12930.64 | 11053
| 6.1.1 subtotal |  |  | 36944.64 | 31579
6.1.2 | Turf - kikuyu rolls incl. estab. watering 12wks | Landscaping | Subcontract | 43443 | 39714
|  | Landscaping | Material | 18829 | 17213 | rate ex GST
|  | Landscaping | Labour | 12723.05 | 11630
| 6.1.2 subtotal |  |  | 74995.05 | 68557
6.2.1 | Garden beds - mulch 75thk & planting as per LA dwgs | Landscaping | Subcontract | 32630 | 26528
|  | Landscaping | Material | 12701 | 10326 | site mtg 2/7 - qty TBC w/ super
|  | Landscaping | Labour | 8254.7 | 6710
| 6.2.1 subtotal |  |  | 53585.7 | 43564
6.2.2 | Street furniture - seats, bins & bike hoops | Landscaping | Subcontract | 7162 | 5726
|  | Landscaping | Material | 3336 | 2667
|  | Landscaping | Labour | 2022.03 | 1618
| 6.2.2 subtotal |  |  | 12520.03 | 10011
INDIRECT / OFF-BOQ COSTS - no BOQ line item, cost centre only
| Head office overhead allocation (2.5%) | Overheads / Prelims | Miscellaneous |  | 19299
|  | Overheads / Prelims | Labour |  | 12743
| subtotal |  |  |  | 32042
| Site utes, fuel & tolls | Plant & Equipment | Plant and Equipment |  | 27014
| subtotal |  |  |  | 27014
| Bank guarantee / performance bond fees | Insurances & Bonds | Miscellaneous |  | 19289 | quote expires 30/7
| subtotal |  |  |  | 19289
| External QA / NATA testing over BOQ allowance | Overheads / Prelims | Subcontract |  | 8252
|  | Overheads / Prelims | Miscellaneous |  | 3587
| subtotal |  |  |  | 11839
| Plant & vehicle registrations and insurances | Insurances & Bonds | Miscellaneous |  | 14353 | rate ex GST
| subtotal |  |  |  | 14353
| IT, comms & project software subscriptions | Overheads / Prelims | Miscellaneous |  | 11976
| subtotal |  |  |  | 11976