## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | Preliminaries & Site Establishment |  |  |  | 96234.83
1.1 | Preliminaries & Site Establishment |  |  |  | 96234.83
1.1.1 | Survey & set-out (all works) | item | 1 | 18417.5 | 18417.5
1.1.2 | Site establishment, mobilisation & demob | item | 1 | 44708 | 58567.48
1.1.3 | Traffic management incl. TMP & permits | wk | 8.02 | 1754.2212 | 14068.85
1.1.4 | Project signage as per spec cl 4.2 | each | 3 | 1727 | 5181
2 | BULK & DETAILED EARTHWORKS |  |  |  | 510096.96
2.1 | Bulk Earthworks |  |  |  | 276550.96
2.1.1 | Excavation in rock, Class A (jack hammer/rock saw) | m3 | 467 | 177.2002 | 82752.49
2.1.2 | Trim & proof roll subgrade (incl. Level 1 testing) | sqm | 6240.9 | 6.6599 | 41563.77
2.1.3 | Bulk earthworks - cut to fill on site | m3 | 6618.9 | 23 | 152234.7
2.2 | Detailed Earthworks |  |  |  | 233546
2.2.1 | Excavate unsuitable mat. & replace w/ approved fill | m3 | 348.18 | 58 | 20194.44
2.2.2 | Import & place select fill (VENM cert. req.) | m³ | 4283.1 | 43.2851 | 185394.41
2.2.3 | Batter shaping & topsoil respread 100mm | m2 | 7965 | 3.51 | 27957.15
3 | Flexible Pavements & Surfacing |  |  |  | 489501.59
3.1 | Flexible Pavements & Surfacing |  |  |  | 489501.59
3.1.1 | AC10 wearing course 30thk (A15E on approaches) | m2 | 13230.8 | 23.8236 | 315205.29
3.1.2 | Prime & 2 coat seal 14/7 (incl. sweep) | m2 | 7125 | 10 | 71250
3.1.3 | Segmental paving to median (Urbanstone or equiv.) | m2 | 534 | 163 | 87042
3.1.4 | Longitudinal linemarking & RRPMs as per dwgs | lm | 2462.2 | 6.5 | 16004.3
4 | CONCRETE WORKS |  |  |  | 465961.8
4.1 | Insitu Concrete |  |  |  | 103468.36
4.1.1 | Pram ramps to AS1428.1 incl. TGSIs | each | 3 | 1573.6 | 4720.8
4.1.2 | Concrete footpath 125thk broom finish | m2 | 1292 | 76.43 | 98747.56
4.2 | Kerbs, Paths & Minor Conc. |  |  |  | 362493.44
4.2.1 | Supply & place N40 slab on grade 200thk incl. SL82 | m² | 2861.59 | 110.1823 | 315296.57
4.2.2 | Kerb & channel B2 barrier type (machine extruded) * | lm | 869 | 54.3117 | 47196.87
5 | Structures & Retaining |  |  |  | 726042.26
5.1 | Structures & Retaining |  |  |  | 726042.26
5.1.1 | Precast L-wall units supply & install | each | 175 | 1306.1704 | 228579.82
5.1.2 | Handrail - galv. tube to AS1657 | m | 187 | 188.5 | 35249.5
5.1.3 | Guardrail w-beam incl. terminals (public road spec) (refer dwg C-404) | m | 309.9 | 105.08 | 32564.29
5.1.4 | Chainwire fencing 1.8m incl. gates | lm | 276.8 | 91 | 25188.8
5.1.5 | Structural steel - galv. incl. shop dwgs (S&E) | t | 11 | 5214 | 57354
5.1.6 | Reinforced blockwork retaining wall H<1.8m incl. found. | m2 | 536.9 | 646.5 | 347105.85
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 267898.2
P.1 | Provisional Sums & Quantities |  |  |  | 267898.2
P.1.1 | Contaminated material - excavate, test & dispose (PROV) | t | 369.74 | 378.35 | 139891.13
P.1.2 | Rock excavation over & above measured qty (PROV) | m³ | 212.42 | 260 | 55229.2
P.1.3 | Service relocations - allowance (PROV SUM) | item | 1 | 45256.0846 | 45256.08
P.1.4 | Dayworks - 20t excavator incl. operator | hr | 115 | 184.0845 | 21169.72
P.1.5 | Dayworks - project engineer | hrs | 39.4 | 161.22 | 6352.07
9.1.1 | Supply & install wheel stops | each | 24 | 68 | 1632
|  |  |  | TOTAL | 2555735.64

## Budget
Gundagai Saleyards Hardstand Upgrade
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Cootamundra-Gundagai Regional Council |  | Prepared: 3/07/2026 ¦ Rev B ¦ estimating team
Budget method: WBS / Lump Sum
Item Code | Description | BOQ Amount ($) | Budget ($) | Margin (%) | Notes
1.1.1 | Survey & set-out (all works) | 18417.5 | 15869 | 13.84%
1.1.2 | Site establishment, mobilisation & demob | 44708 | 42716 | 4.456% | allow for wet weather
1.1.3 | Traffic management incl. TMP & permits | 14068.85 | 12515 | 11.04% | allow for wet weather
1.1.4 | Project signage as per spec cl 4.2 | 5181 | 4787 | 7.605% | check qty vs dwg rev D
2.1.1 | Excavation in rock, Class A (jack hammer/rock saw) | 82752.49 | 78123 | 5.594% | check qty vs dwg rev D
2.1.2 | Trim & proof roll subgrade (incl. Level 1 testing) | 41563.77 | 36831 | 11.39% | carried from tender est.
2.1.3 | Bulk earthworks - cut to fill on site | 152234.7 | 130792 | 14.09%
2.2.1 | Excavate unsuitable mat. & replace w/ approved fill | 20194.44 | 18094 | 10.4%
2.2.2 | Import & place select fill (VENM cert. req.) | 185394.41 | 160200 | 13.59%
2.2.3 | Batter shaping & topsoil respread 100mm | 27957.15 | 29635 | -6.002% | allow for wet weather
3.1.1 | AC10 wearing course 30thk (A15E on approaches) | 315205.29 | 268250 | 14.9%
3.1.2 | Prime & 2 coat seal 14/7 (incl. sweep) | 71250 | 64635 | 9.284% | PC sum
3.1.3 | Segmental paving to median (Urbanstone or equiv.) | 87042 | 79850 | 8.263% | rate ex GST
3.1.4 | Longitudinal linemarking & RRPMs as per dwgs | 16004.3 | 14023 | 12.38%
4.1.1 | Pram ramps to AS1428.1 incl. TGSIs | 4720.8 | 4111 | 12.92% | check qty vs dwg rev D
4.1.2 | Concrete footpath 125thk broom finish | 98747.56 | 91519 | 7.32% | PC sum
4.2.1 | Supply & place N40 slab on grade 200thk incl. SL82 | 315296.57 | 267641 | 15.11% | check qty vs dwg rev D
4.2.2 | Kerb & channel B2 barrier type (machine extruded) * | 47196.87 | 41410 | 12.26% | quote expires 30/7
5.1.1 | Precast L-wall units supply & install | 228579.82 | 192128 | 15.95% | allow for wet weather
5.1.2 | Handrail - galv. tube to AS1657 | 35249.5 | 29709 | 15.72%
5.1.3 | Guardrail w-beam incl. terminals (public road spec) (refer dwg C-404) | 32564.29 | 28200 | 13.4%
5.1.4 | Chainwire fencing 1.8m incl. gates | 25188.8 | 22028 | 12.55%
5.1.5 | Structural steel - galv. incl. shop dwgs (S&E) | 57354 | 51839 | 9.616%
5.1.6 | Reinforced blockwork retaining wall H<1.8m incl. found. | 347105.85 | 310198 | 10.63%
9.1.1 | Supply & install wheel stops | 1632 | 1430 | 12.38% | incl. cartage
| TOTALS | 2275609.96 | 1996533 | 12.26%