## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | PRELIMINARIES & SITE ESTABLISHMENT |  |  |  | 136403.22
1.1 | Preliminaries & Site Establishment |  |  |  | 136403.22
1.1.1 | Environmental controls - sed. fence, shaker grid etc | item | 1 | 12647.0451 | 12647.05
1.1.2 | Survey & set-out (all works) (refer dwg C-404) | LS | 1 | 17782 | 17782
1.1.3 | Traffic management incl. TMP & permits | wk | 12.5 | 3980 | 49750
1.1.4 | Site establishment, mobilisation & demob | LS | 1 | 56224.17 | 56224.17
2 | DEMOLITION & SITE CLEARING |  |  |  | 146984.74
2.1 | Demolition & Site Clearing - Part A |  |  |  | 65918.74
2.1.1 | Clear & grub incl. removal offsite (refer dwg C-309) | sqm | 4568.4 | 2.54 | 11603.74
2.1.2 | Strip topsoil 150mm & stockpile on site | m³ | 3105 | 10 | 31050
2.1.1 | Remove exist. kerb & channel & dispose | LM | 846 | 27.5 | 23265
2.2 | Demolition & Site Clearing - Part B | m2 | 1850 | 12.5 | 81066
2.2.1 | Saw cut & demolish exist. concrete pavement | sqm | 1208 | 43 | 51944
2.2.2 | Remove trees incl. stump grinding (arborist sup.) | ea | 10 | 579 | 5790
2.2.3 | Demolish exist. structures & cart away | LS | 1 | 23332 | 23332
3 | Bulk & Detailed Earthworks |  |  |  | 535492.79
3.1 | Bulk Earthworks |  |  |  | 414402.71
3.1.1 | Excavate unsuitable mat. & replace w/ approved fill | m3 | 2290 | 49.67 | 113744.3
3.1.2 | Excavation in rock, Class A (jack hammer/rock saw) (refer dwg C-208) | m3 | 562.1 | 152.67 | 85815.81
3.1.3 | Import & place select fill (VENM cert. req.) | m3 | 6318.9 | 34 | 214842.6
3.2 | Detailed Earthworks |  |  |  | 121090.08
3.2.1 | Trim & proof roll subgrade (incl. Level 1 testing) | m2 | 7811 | 6.469 | 50529.36
3.2.2 | Bulk earthworks - cut to fill on site | m³ | 5136.3 | 9.3735 | 48145.11
3.2.3 | Batter shaping & topsoil respread 100mm | m² | 2754.2 | 8.1387 | 22415.61
4 | FLEXIBLE PAVEMENTS & SURFACING |  |  |  | 1368618.17
4.1 | Granular Pavements |  |  |  | 804199.87
4.1.1 | Prime & 2 coat seal 14/7 (incl. sweep) * | m² | 8003 | 7.9265 | 63435.78
4.1.2 | Supply & place DGS40 subbase 200thk compacted | sqm | 17786 | 12.4441 | 221330.76
4.1.3 | AC14 intermediate course 50thk (C320) | m2 | 14863.8 | 34.9462 | 519433.33
4.2 | Asphalt & Surfacing |  |  |  | 564418.3
4.2.1 | AC10 wearing course 30thk (A15E on approaches) | m² | 13557 | 21 | 284697
4.2.2 | Longitudinal linemarking & RRPMs as per dwgs | LM | 3330 | 8.5129 | 28347.96
4.2.3 | Supply & place DGB20 basecourse 150thk | m² | 15225.52 | 16.51 | 251373.34
5 | Structures & Retaining |  |  |  | 955779.16
5.1 | Structures & Retaining - Part A |  |  |  | 191322.98
5.1.1 | Precast L-wall units supply & install (refer dwg C-405) | lm | 100 | 1080.5 | 108050
5.1.2 | Chainwire fencing 1.8m incl. gates | lm | 1198 | 69.51 | 83272.98
5.2 | Structures & Retaining - Part B |  |  |  | 764456.18
5.2.1 | Guardrail w-beam incl. terminals (public road spec) | m | 696 | 148.5 | 103356
5.2.2 | Structural steel - galv. incl. shop dwgs (S&E) | t | 63 | 5152.8854 | 324631.78
5.2.3 | Reinforced blockwork retaining wall H<1.8m incl. found. | m² | 573.2 | 587 | 336468.4
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 62176.18
P.1 | Provisional Sums & Quantities |  |  |  | 62176.18
P.1.1 | Dayworks - 20t excavator incl. operator | hr | 52 | 197 | 10244
P.1.2 | Dayworks - project engineer | hr | 79 | 125 | 9875
P.1.3 | Latent conditions allowance (PROV SUM) | LS | 1 | 42057.18 | 42057.18
|  |  |  | TOTAL | 3205454.26

## Budget
Windellama Road Safety Upgrades (Curves 3-9)
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Goulburn Mulwaree Council |  | Prepared: 23/06/2026 ¦ Rev 0 ¦ ML
Budget method: Cost Centre / Lump Sum
Item Code | Description | Cost Centre | BOQ Amount ($) | Budget ($) | Margin (%) | Notes
1.1.1 | Environmental controls - sed. fence, shaker grid etc | Overheads / Prelims | 12647.05 | 9900 | 21.72% | quote expires 30/7
1.1.2 | Survey & set-out (all works) (refer dwg C-404) | Overheads / Prelims | 17782 | 14200 | 20.14%
1.1.3 | Traffic management incl. TMP & permits | Overheads / Prelims | 49750 | 39859 | 19.88% | allow for wet weather
1.1.4 | Site establishment, mobilisation & demob | Overheads / Prelims | 56224.17 | 47000 | 16.41% | site mtg 2/7 - qty TBC w/ super
2.1.1 | Clear & grub incl. removal offsite (refer dwg C-309) | Earthworks | 11603.74 | 9567 | 17.55% | rate ex GST
2.1.2 | Strip topsoil 150mm & stockpile on site | Earthworks | 31050 | 24114 | 22.34%
2.1.3 | Remove exist. kerb & channel & dispose | Earthworks | 23265 | 18086 | 22.26%
2.2.1 | Saw cut & demolish exist. concrete pavement | Earthworks | 51944 | 40900 | 21.26% | PC sum
2.2.2 | Remove trees incl. stump grinding (arborist sup.) | Earthworks | 5790 | 4744 | 18.07% | allow for wet weather
2.2.3 | Demolish exist. structures & cart away | Earthworks | 23332 | 19032 | 18.43% | allow for wet weather
3.1.1 | Excavate unsuitable mat. & replace w/ approved fill | Earthworks | 113744.3 | 94565 | 16.86%
3.1.2 | Excavation in rock, Class A (jack hammer/rock saw) (refer dwg C-208) | Earthworks | 85815.81 | 69230 | 19.33% | carried from tender est.
3.1.3 | Import & place select fill (VENM cert. req.) | Earthworks | 214842.6 | 165563 | 22.94% | quote expires 30/7
3.2.1 | Trim & proof roll subgrade (incl. Level 1 testing) | Earthworks | 50529.36 | 43762 | 13.39% | check qty vs dwg rev D
3.2.2 | Bulk earthworks - cut to fill on site | Earthworks | 48145.11 | 39997 | 16.92% | sub quote - CivilTech 14/6
3.2.3 | Batter shaping & topsoil respread 100mm | Earthworks | 22415.61 | 17986 | 19.76% | PC sum
4.1.1 | Prime & 2 coat seal 14/7 (incl. sweep) * | Pavements & Surfacing | 63435.78 | 48472 | 23.59% | allow for wet weather
4.1.2 | Supply & place DGS40 subbase 200thk compacted | Pavements & Surfacing | 221330.76 | 182100 | 17.72% | quote expires 30/7
4.1.3 | AC14 intermediate course 50thk (C320) | Pavements & Surfacing | 519433.33 | 428550 | 17.5%
4.2.1 | AC10 wearing course 30thk (A15E on approaches) | Pavements & Surfacing | 284697 | 239424 | 15.9% | site mtg 2/7 - qty TBC w/ super
4.2.2 | Longitudinal linemarking & RRPMs as per dwgs | Pavements & Surfacing | 28347.96 | 22503 | 20.62% | carried from tender est.
4.2.3 | Supply & place DGB20 basecourse 150thk | Pavements & Surfacing | 251373.34 | 195950 | 22.05% | incl. cartage
5.1.1 | Precast L-wall units supply & install (refer dwg C-405) | Concrete | 108050 | 90000 | 16.71% | check qty vs dwg rev D
5.1.2 | Chainwire fencing 1.8m incl. gates | Concrete | 83272.98 | 64671 | 22.34%
5.2.1 | Guardrail w-beam incl. terminals (public road spec) | Concrete | 103356 | 87200 | 15.63%
5.2.2 | Structural steel - galv. incl. shop dwgs (S&E) | Concrete | 324631.78 | 265413 | 18.24%
5.2.3 | Reinforced blockwork retaining wall H<1.8m incl. found. | Concrete | 336468.4 | 263266 | 21.76% | incl. cartage
4.2.5 | Guide posts & delineators | Concrete | 5280 | 4650 | 11.93% | carried from tender est.
| TOTALS |  | 3148558.08 | 2550704 | 18.99%