## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | Preliminaries & Site Establishment |  |  |  | 221809.09
1.1 | Preliminaries & Site Establishment |  |  |  | 221809.09
1.1.1 | Site office, amenities & temp fencing | wks | 36 | 1308.7118 | 47113.62
1.1.2 | Traffic management incl. TMP & permits | wk | 30 | 3633.8859 | 109016.58
1.1.3 | Dilapidation surveys & CCTV existing assets * | item | 3.07 | 2234.09 | 6858.66
1.1.4 | Environmental controls - sed. fence, shaker grid etc | LS | 1 | 10413.97 | 10413.97
1.1.5 | Project signage as per spec cl 4.2 | each | 5 | 964 | 4820
1.1.6 | Site establishment, mobilisation & demob | LS | 1 | 36486.2587 | 36486.26
1.1.7 | Survey & set-out (all works) | LS | 1 | 7100 | 7100
2 | Bulk & Detailed Earthworks |  |  |  | 273867.56
2.1 | Bulk & Detailed Earthworks |  |  |  | 273867.56
2.1.1 | Bulk earthworks - cut to fill on site | m³ | 11018.7 | 16.6319 | 183261.92
2.1.2 | Import & place select fill (VENM cert. req.) | m3 | 600 | 58 | 34800
2.1.3 | Excavate unsuitable mat. & replace w/ approved fill | m3 |  | Rate Only
2.1.4 | Excavation in rock, Class A (jack hammer/rock saw) | m³ | 259.73 | 214.8602 | 55805.64
3 | Stormwater Drainage |  |  |  | 303821.92
3.1 | Pipelines |  |  |  | 164798.89
3.1.1 | GPT unit supply & install (Rocla CDS or approved equiv.) | each | 2.2 | 36103.5 | 79427.7
3.1.2 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | lm | 316.6 | 269.65 | 85371.19
3.2 | Pits & Structures |  |  |  | 139023.03
3.2.1 | Junction pits 900x900 precast incl. lid | no. | 10.67 | 3059 | 32639.53
3.2.2 | Connect new line to exist. pit incl. core & benching | No. | 6 | 3056 | 18336
3.2.3 | Supply & lay 600dia RCP RRJ Cl.4 | lm | 205 | 429.5 | 88047.5
4 | Flexible Pavements & Surfacing |  |  |  | 446856.74
4.1 | Flexible Pavements & Surfacing |  |  |  | 446856.74
4.1.1 | Longitudinal linemarking & RRPMs as per dwgs | LM | 3251 | 7.9075 | 25707.28
4.1.2 | Supply & place DGS40 subbase 200thk compacted | m² | 16912.09 | 13.5843 | 229738.9
4.1.3 | Prime & 2 coat seal 14/7 (incl. sweep) | m² | 14587.3 | 9.67 | 141059.19
4.1.4 | Segmental paving to median (Urbanstone or equiv.) | m² | 347 | 145.1048 | 50351.37
5 | Structures & Retaining |  |  |  | 582254.56
5.1 | Structures & Retaining |  |  |  | 582254.56
5.1.1 | Structural steel - galv. incl. shop dwgs (S&E) | tonne | 42.8 | 4509.1 | 192989.48
5.1.2 | Reinforced blockwork retaining wall H<1.8m incl. found. | m² | 539.3 | 461 | 248617.3
5.1.3 | Guardrail w-beam incl. terminals (public road spec) | LM | 598 | 106.0068 | 63392.07
5.1.4 | Chainwire fencing 1.8m incl. gates | lm | 1002.8 | 77.04 | 77255.71
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 117332.92
P.1 | Provisional Sums & Quantities |  |  |  | 117332.92
P.1.1 | Dayworks - labourer incl. small tools | hrs | 215.4 | 103.5 | 22293.9
P.1.2 | Dayworks - project engineer | hrs | 55 | 137.03 | 7536.65
P.1.3 | Contaminated material - excavate, test & dispose (PROV) | t | 275 | 228.0268 | 62707.37
P.1.4 | Rock excavation over & above measured qty (PROV) | m³ | 145 | 171 | 24795
|  |  |  | TOTAL | 1945942.79

## Budget
Berrima Quarry Access Road Upgrade
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Boral Resources (NSW) |  | Prepared: 6/07/2026 ¦ Rev C ¦ ML
Budget method: Cost Centre / Resource Breakdown
Item Code | Description | Cost Centre | Resource Category | BOQ ($) | Budget ($) | Notes
1.1.1 | Site office, amenities & temp fencing | Overheads / Prelims | Labour | 19949 | 16330 | site mtg 2/7 - qty TBC w/ super
|  | Overheads / Prelims | Miscellaneous | 16584 | 13575
|  | Overheads / Prelims | Plant and Equipment | 10580.62 | 8661
| 1.1.1 subtotal |  |  | 47113.62 | 38566
1.1.2 | Traffic management incl. TMP & permits | Overheads / Prelims | Labour | 43998 | 37918
|  | Overheads / Prelims | Miscellaneous | 34049 | 29343
|  | Overheads / Prelims | Plant and Equipment | 20151 | 17366
|  | Overheads / Prelims | Subcontract | 10818.58 | 9323
| 1.1.2 subtotal |  |  | 109016.58 | 93950
1.1.3 | Dilapidation surveys & CCTV existing assets * | Overheads / Prelims | Labour | 2934 | 2444
|  | Overheads / Prelims | Miscellaneous | 2292 | 1909 | sub quote - CivilTech 14/6
|  | Overheads / Prelims | Plant and Equipment | 1632.66 | 1359
| 1.1.3 subtotal |  |  | 6858.66 | 5712
1.1.4 | Environmental controls - sed. fence, shaker grid etc | Overheads / Prelims | Labour | 4018 | 3376
|  | Overheads / Prelims | Miscellaneous | 3418 | 2872
|  | Overheads / Prelims | Plant and Equipment | 1982 | 1666
|  | Overheads / Prelims | Subcontract | 995.97 | 836 | rate ex GST
| 1.1.4 subtotal |  |  | 10413.97 | 8750
1.1.5 | Project signage as per spec cl 4.2 | Overheads / Prelims | Labour | 2219 | 1836
|  | Overheads / Prelims | Miscellaneous | 1493 | 1236 | PC sum
|  | Overheads / Prelims | Plant and Equipment | 1108 | 917 | sub quote - CivilTech 14/6
| 1.1.5 subtotal |  |  | 4820 | 3989
1.1.6 | Site establishment, mobilisation & demob | Overheads / Prelims | Labour | 20597 | 17725
|  | Overheads / Prelims | Miscellaneous | 15889.26 | 13675
| 1.1.6 subtotal |  |  | 36486.26 | 31400
1.1.7 | Survey & set-out (all works) | Overheads / Prelims | Labour | 3061 | 2645
|  | Overheads / Prelims | Miscellaneous | 2446 | 2113
|  | Overheads / Prelims | Plant and Equipment | 1593 | 1377
| 1.1.7 subtotal |  |  | 7100 | 6135
2.1.1 | Bulk earthworks - cut to fill on site | Earthworks | Plant and Equipment | 104386 | incl. in 1.2.1
|  | Earthworks | Labour | 47363 | 0
|  | Earthworks | Material | 31512.92 | 0
| 2.1.1 subtotal |  |  | 183261.92 | 0
2.1.2 | Import & place select fill (VENM cert. req.) | Earthworks | Plant and Equipment | 19018 | 16362 | site mtg 2/7 - qty TBC w/ super
|  | Earthworks | Labour | 7948 | 6838
|  | Earthworks | Material | 4052 | 3486
|  | Earthworks | Miscellaneous | 3782 | 3253
| 2.1.2 subtotal |  |  | 34800 | 29939
2.1.3 | Excavate unsuitable mat. & replace w/ approved fill | Earthworks | Plant and Equipment | 53248 | 45705
|  | Earthworks | Labour | 24342 | 20894
|  | Earthworks | Material | 14242.5 | 12225 | PC sum
| 2.1.3 subtotal |  |  | 91832.5 | 78824
2.1.4 | Excavation in rock, Class A (jack hammer/rock saw) | Earthworks | Plant and Equipment | 31429 | 27061 | check qty vs dwg rev D
|  | Earthworks | Labour | 15976 | 13756
|  | Earthworks | Material | 8400.64 | 7233
| 2.1.4 subtotal |  |  | 55805.64 | 48050
3.1.1 | GPT unit supply & install (Rocla CDS or approved equiv.) | Drainage | Material | 37634 | 40645
|  | Drainage | Labour | 22769 | 24590
|  | Drainage | Plant and Equipment | 19024.7 | 20547
| 3.1.1 subtotal |  |  | 79427.7 | 85782
3.1.2 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | Drainage | Material | 53996 | 58315
|  | Drainage | Labour | 31375.19 | 33886
| 3.1.2 subtotal |  |  | 85371.19 | 92201
3.2.1 | Junction pits 900x900 precast incl. lid | Drainage | Material | 15100 | 16308
|  | Drainage | Labour | 10700 | 11556
|  | Drainage | Plant and Equipment | 6839.53 | 7387 | quote expires 30/7
| 3.2.1 subtotal |  |  | 32639.53 | 35251
3.2.2 | Connect new line to exist. pit incl. core & benching | Drainage | Material | 11185 | 12080
|  | Drainage | Labour | 7151 | 7722
| 3.2.2 subtotal |  |  | 18336 | 19802
3.2.3 | Supply & lay 600dia RCP RRJ Cl.4 | Drainage | Material | 39935 | 43130
|  | Drainage | Labour | 22343 | 24131
|  | Drainage | Plant and Equipment | 17782 | 19205
|  | Drainage | Subcontract | 7987.5 | 8625 | PC sum
| 3.2.3 subtotal |  |  | 88047.5 | 95091
4.1.1 | Longitudinal linemarking & RRPMs as per dwgs | Pavements & Surfacing | Subcontract | 18397 | 15639
|  | Pavements & Surfacing | Material | 7310.28 | 6215
| 4.1.1 subtotal |  |  | 25707.28 | 21854
4.1.2 | Supply & place DGS40 subbase 200thk compacted | Pavements & Surfacing | Subcontract | 137022 | 116721
|  | Pavements & Surfacing | Material | 50216 | 42776
|  | Pavements & Surfacing | Plant and Equipment | 25997 | 22145
|  | Pavements & Surfacing | Labour | 16503.9 | 14058
| 4.1.2 subtotal |  |  | 229738.9 | 195700
4.1.3 | Prime & 2 coat seal 14/7 (incl. sweep) | Pavements & Surfacing | Subcontract | 101228 | 93543
|  | Pavements & Surfacing | Material | 39831.19 | 36807
| 4.1.3 subtotal |  |  | 141059.19 | 130350
4.1.4 | Segmental paving to median (Urbanstone or equiv.) | Pavements & Surfacing | Subcontract | 35706 | 27231
|  | Pavements & Surfacing | Material | 14645.37 | 11169
| 4.1.4 subtotal |  |  | 50351.37 | 38400
5.1.1 | Structural steel - galv. incl. shop dwgs (S&E) | Concrete | Subcontract | 85622 | 73713
|  | Concrete | Material | 74225 | 63902
|  | Concrete | Labour | 33142.48 | 28533
| 5.1.1 subtotal |  |  | 192989.48 | 166148
5.1.2 | Reinforced blockwork retaining wall H<1.8m incl. found. | Concrete | Subcontract | 114416 | 100187
|  | Concrete | Material | 86893 | 76087
|  | Concrete | Labour | 47308.3 | 41426
| 5.1.2 subtotal |  |  | 248617.3 | 217700
5.1.3 | Guardrail w-beam incl. terminals (public road spec) | Concrete | Subcontract | 29767 | 25568
|  | Concrete | Material | 22281 | 19138
|  | Concrete | Labour | 11344.07 | 9744 | rate ex GST
| 5.1.3 subtotal |  |  | 63392.07 | 54450
5.1.4 | Chainwire fencing 1.8m incl. gates | Concrete | Subcontract | 30869 | 25760 | incl. cartage
|  | Concrete | Material | 23394 | 19522
|  | Concrete | Labour | 15992 | 13345
|  | Concrete | Plant and Equipment | 7000.71 | 5843
| 5.1.4 subtotal |  |  | 77255.71 | 64470