## Summary
SITE DIARY REPORT — MULTI-DAY
01 Apr 2026 – 03 Apr 2026 ¦ 3 Days (Thu–Sat)
PROJECT INFORMATION
| Project | Varicon Q2 2024 Job Name
| Job Number | Q22024/06/24
| Client | Varicon
| Job Address | 217 Flinders Street, Melbourne, VIC, Australia
AGGREGATED TOTALS — ACROSS DATE RANGE
7 | 38h | 10 ¦ 3 | 8 | 5 | 6 | 2
Employees | Work Time | Equipment (Active¦SD) | Labour | Materials | Tasks | Dockets
DAY-BY-DAY OVERVIEW
Date | Employees | Work Time | Equipment | Stand Down | Labour | Materials | Tasks | Status
Thu, 01 Apr 2026 | 3 | 12h 0m | 4 | 1 | 3 | 2 | 2 | Approved
Fri, 02 Apr 2026 | 4 | 18h 30m | 6 | 2 | 5 | 3 | 4 | Pending
Sat, 03 Apr 2026 | 0 | 0h 0m | 0 | 0 | 0 | 0 | 0 | Pending
APPROVAL STATUS
Date | Day | Approved By | Approved Date | Status
01 Apr 2026 | Thursday | Michael Chen | 01 Apr 2026, 06:30 PM | Approved
02 Apr 2026 | Friday | - | - | Pending
03 Apr 2026 | Saturday | - | - | Pending
Generated: 05 Apr 2026 ¦ Multi-Day Site Diary Report

## Notes
NOTES / INSTRUCTIONS
# | Date | Note Section | Description | Created By | Created At | File / Attachment
1 | 01 Apr | Equipment | Inspect all excavators before operation. Safety briefing at 7:00 AM. | - | - | -
2 | 02 Apr | Equipment | Task description | - | - | -
3 | 02 Apr | Equipment | Lorem Ipsum | - | - | -
4 | 02 Apr | Equipment | This is long notes title test case scenario where the student is asked | - | - | -

## Plant & Equipment
PLANT & EQUIPMENT 10 Active ¦ 3 Stand Down ¦ 28h Total
# | Date | Equipment Detail | Operated By | Attachment | Total Duration | Task | Duration | Status
1 | 01 Apr | 55T Excavator | James Wilson | Bucket 1.2m | 8h 0m | Foundation dig | - | Active
2 | 01 Apr | Backhoe Loader | - | - | - | - | - | Stand Down
3 | 01 Apr | CAT 320 Excavator | Tim Rogers | Ripper | 6h 0m | Trench work | - | Active
4 | 01 Apr | Compactor | David Lee | - | 4h 0m | Road base | - | Active
5 | 02 Apr | 11-Name | - | - | - | - | - | Active
6 | 02 Apr | 55T Excavator | - | - | - | - | - | Stand Down
7 | 02 Apr | Backhoe Loader | - | - | - | - | - | Stand Down
8 | 02 Apr | Unknown Equipment | - | - | - | - | - | Active
9 | 02 Apr | Equip81 | - | - | - | - | - | Active
10 | 02 Apr | Crane 50T | Mark Taylor | Jib ext. | 10h 0m | Steel erection | - | Active

## Photos
SITE PHOTOS
# | Date | Photo Title | Description | Taken By | Taken At | File / Image
No Photos Available

## Timecards
TIMECARDS 7 Employees ¦ 22h Total
# | Date | Employee | Clocked In | Clocked Out | Approved In | Approved Out | Allowance | Task | Duration
1 | 01 Apr | James Wilson | 06:00 AM | 02:00 PM | 06:00 AM | 02:00 PM | - | Foundation dig | 8h 0m
2 | 01 Apr | Tim Rogers | 07:00 AM | 03:00 PM | 07:00 AM | 03:00 PM | - | Trench work | 8h 0m
3 | 01 Apr | David Lee | 08:00 AM | 12:00 PM | 08:00 AM | 12:00 PM | Lunch | Road base | 4h 0m
4 | 02 Apr | Anu Prazz | 01:00 AM | 03:00 AM | 01:00 AM | 03:00 AM | - | - | 2h 0m
5 | 02 Apr | Ap Ap | 07:45 PM | 11:45 PM | - | - | - | - | -
6 | 02 Apr | Prabin Waiba | 07:45 AM | 11:45 AM | - | - | - | - | -
7 | 02 Apr | Mark Taylor | 06:00 AM | 04:00 PM | - | - | - | Steel erection | -

## Labour
LABOUR 8 Labour ¦ 52h Total
# | Date | Supplier | Resource / Role | Cost Centre | # Labour x Duration
1 | 01 Apr | Allied Contractors | General Labourer x2 | Foundation Works | 2 x 8h = 16h
2 | 01 Apr | Varicon Staging | Plant Operator | Varicon Staging | 1 x 8h = 8h
3 | 01 Apr | Varicon Staging | Supervisor | Varicon Staging | 1 x 9h = 9h
4 | 02 Apr | Varicon Staging | 0744 Truck Driver | Varicon Staging | -
5 | 02 Apr | Varicon Staging | Director - Overtime 1.5x | Varicon Staging | -
6 | 02 Apr | Bayside Wholesale | 0744 Truck Driver | Bayside Wholesale | -

## Materials
MATERIALS 5 Materials
# | Date | Resource / Material | Cost Centre | Quantity
1 | 01 Apr | Concrete Mix 40MPa | Foundation Works | 12 m³
2 | 01 Apr | Reinforcing Steel | Foundation Works | 2.5 tonnes
3 | 01 Apr | Formwork Plywood | Foundation Works | 30 sheets
4 | 02 Apr | 20mm Crushed Rocks | Varicon Staging | -
5 | 02 Apr | Bar-Brick | Varicon Staging | -

## Dockets
DOCKETS 2 Dockets
# | Date | Docket Number | Supplier | Status | Purchase Order | Docket Status
1 | 01 Apr | DK-20260401-001 | Boral Concrete | Delivered | PO-2024-1145 | Verified
2 | 02 Apr | - | - | - | - | -

## Miscellaneous
MISCELLANEOUS 5 Resources
# | Date | Supplier | Resource / Task | Cost Centre | # Qty x Duration
1 | 01 Apr | Site Services Co | Skip Bin Hire | Foundation Works | 1 x Full Day
2 | 01 Apr | Varicon Staging | Traffic Control | Varicon Staging | 2 x 8h
3 | 02 Apr | Varicon Staging | Delivery (Delivery) | Varicon Staging | -
4 | 02 Apr | Bayside Wholesale | 01RDO (01RDO) | Bayside Wholesale | -
5 | 02 Apr | Kinnet & Jones | - | Kinnet & Jones | -

## Tasks
TASKS 6 Tasks
# | Date | Task | Cost Centre | Notes & Attachment
1 | 01 Apr | (1) Foundation Excavation | Foundation Works | Completed to 2.4m depth
2 | 01 Apr | (2) Rebar Installation | Foundation Works | N16 bars placed
3 | 01 Apr | (3) Concrete Pour | Foundation Works | Pad footings east wing
4 | 01 Apr | (4) Formwork Setup | Foundation Works | -
5 | 02 Apr | (1) Daywork Docket | - | -
6 | 02 Apr | (3) Subcontract Phase 2 | - | -

## Weather
WEATHER SUMMARY
# | Date | Sky | Rainfall | Wind | Temperature | Weather Delay
1 | 01 Apr | Clear | None | Light NW 10km/h | 14°C – 22°C | None
2 | 02 Apr | - | - | - | - | -
3 | 03 Apr | - | - | - | - | -