## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | PRELIMINARIES & SITE ESTABLISHMENT |  |  |  | 168539.88
1.1 | Preliminaries & Site Establishment |  |  |  | 168539.88
1.1.1 | Traffic management incl. TMP & permits | wk | 17.9 | 3743.74 | 67012.95
1.1.2 | Site office, amenities & temp fencing | wks | 22 | 1537 | 33814
1.1.3 | Project signage as per spec cl 4.2 * | ea | 5 | 1157.8104 | 5789.05
1.1.4 | Dilapidation surveys & CCTV existing assets | item | 1 | 1839.7891 | 1839.79
1.1.5 | Site establishment, mobilisation & demob | Item | 1 | 41932 | 41932
1.1.6 | Environmental controls - sed. fence, shaker grid etc | item | 1 | 11488.0942 | 11488.09
1.1.7 | Survey & set-out (all works) * | LS | 1 | 6664 | 6664
2 | BULK & DETAILED EARTHWORKS |  |  |  | 560371.94
2.1 | Bulk & Detailed Earthworks |  |  |  | 560371.94
2.1.1 | Trim & proof roll subgrade (incl. Level 1 testing) | m² | 3522.4 | 6.5 | 22895.6
2.1.2 | Batter shaping & topsoil respread 100mm | m² | 8326 | 4.1939 | 34918.41
2.1.3 | Excavation in rock, Class A (jack hammer/rock saw) | m3 | 502 | 226 | 113452
2.1.4 | Excavate unsuitable mat. & replace w/ approved fill | m³ | 989.27 | 67.5 | 66775.73
2.1.5 | Import & place select fill (VENM cert. req.) | t | 3085 | 48.12 | 148450.2
2.1.6 | Bulk earthworks - cut to fill on site | m³ | 9660 | 18 | 173880
3 | CONCRETE WORKS |  |  |  | 541096.89
3.1 | Insitu Concrete |  |  |  | 261307.24
3.1.1 | Kerb & channel B2 barrier type (machine extruded) | lm | 1373.25 | 69.72 | 95742.99
3.1.2 | Supply & place N32 conc. footings incl. exc. & reo | m3 | 395 | 419.15 | 165564.25
3.2 | Kerbs, Paths & Minor Conc. |  |  |  | 279789.65
3.2.1 | Concrete footpath 125thk broom finish | m2 | 2267.8 | 82 | 185959.6
3.2.2 | Vehicle crossings 150thk reinforced | m2 | 391.8 | 101.6614 | 39830.94
3.2.3 | Pram ramps to AS1428.1 incl. TGSIs | No. | 21.31 | 2533.98 | 53999.11
4 | Flexible Pavements & Surfacing |  |  |  | 300912.15
4.1 | Flexible Pavements & Surfacing |  |  |  | 300912.15
4.1.1 | Supply & place DGS40 subbase 200thk compacted (refer dwg C-405) | sqm | 6178 | 23.75 | 146727.5
4.1.2 | Segmental paving to median (Urbanstone or equiv.) | m² | 895.1 | 105.6 | 94522.56
4.1.3 | Prime & 2 coat seal 14/7 (incl. sweep) * | m² | 1631 | 11.5 | 18756.5
4.1.4 | AC14 intermediate course 50thk (C320) | m2 | 1511.97 | 27.0545 | 40905.59
5 | PUBLIC UTILITIES & SERVICES |  |  |  | 367716.82
5.1 | Wet Services |  |  |  | 78914.61
5.1.1 | Street lighting incl. poles, luminaires & pits | No. | 5 | 7195 | 35975
5.1.2 | Sewer maintenance holes 1050dia precast (refer dwg C-306) | each | 5.18 | 8289.5 | 42939.61
5.2 | Dry Services / Electrical |  |  |  | 288802.21
5.2.1 | Comms conduits P50 x2 incl. pits (NBN spec) | m | 1248.4 | 49.2911 | 61535.01
5.2.2 | DN150 PVC sewer S&L @ min grade incl. compaction test | m | 1027 | 186 | 191022
5.2.3 | DN100 PE watermain S&L incl. fittings & thrust blocks | lm | 244.9 | 148 | 36245.2
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 151577.35
P.1 | Provisional Sums & Quantities |  |  |  | 151577.35
P.1.1 | Rock excavation over & above measured qty (PROV) | m3 | 145 | 121.1576 | 17567.85
P.1.2 | Latent conditions allowance (PROV SUM) | LS | 1 | 17742 | 17742
P.1.3 | Service relocations - allowance (PROV SUM) | item | 1 | 54483.26 | 54483.26
P.1.4 | Contaminated material - excavate, test & dispose (PROV) | t | 140 | 360.46 | 50464.4
P.1.5 | Dayworks - project engineer | hr | 78.61 | 144 | 11319.84
|  |  |  | TOTAL | 2090215.03

## Budget
Penrith Lakes Access Improvements
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Penrith City Council |  | Prepared: 12/06/2026 ¦ Rev B ¦ AP
Budget method: Cost Centre / Resource Breakdown
Item Code | Description | Cost Centre | Resource Category | BOQ ($) | Budget ($) | Notes
1.1.1 | Traffic management incl. TMP & permits | Overheads / Prelims | Labour | 35074 | 28539
|  | Overheads / Prelims | Miscellaneous | 31938.95 | 25987
| 1.1.1 subtotal |  |  | 67012.95 | 54526
1.1.2 | Site office, amenities & temp fencing | Overheads / Prelims | Labour | 12828 | 11020 | site mtg 2/7 - qty TBC w/ super
|  | Overheads / Prelims | Miscellaneous | 10125 | 8699
|  | Overheads / Prelims | Plant and Equipment | 7756 | 6663 | carried from tender est.
|  | Overheads / Prelims | Subcontract | 3105 | 2668
| 1.1.2 subtotal |  |  | 33814 | 29050
1.1.3 | Project signage as per spec cl 4.2 * | Overheads / Prelims | Labour | 2754 | 2282
|  | Overheads / Prelims | Miscellaneous | 1771 | 1467
|  | Overheads / Prelims | Plant and Equipment | 1264.05 | 1048
| 1.1.3 subtotal |  |  | 5789.05 | 4797
1.1.4 | Dilapidation surveys & CCTV existing assets | Overheads / Prelims | Labour | 688 | 522
|  | Overheads / Prelims | Miscellaneous | 525 | 398
|  | Overheads / Prelims | Plant and Equipment | 422 | 320
|  | Overheads / Prelims | Subcontract | 204.79 | 157
| 1.1.4 subtotal |  |  | 1839.79 | 1397
1.1.5 | Site establishment, mobilisation & demob | Overheads / Prelims | Labour | 24654 | 18984
|  | Overheads / Prelims | Miscellaneous | 17278 | 13304
| 1.1.5 subtotal |  |  | 41932 | 32288
1.1.6 | Environmental controls - sed. fence, shaker grid etc | Overheads / Prelims | Labour | 4668 | 3926
|  | Overheads / Prelims | Miscellaneous | 3412 | 2870
|  | Overheads / Prelims | Plant and Equipment | 2294 | 1929
|  | Overheads / Prelims | Subcontract | 1114.09 | 937
| 1.1.6 subtotal |  |  | 11488.09 | 9662
1.1.7 | Survey & set-out (all works) * | Overheads / Prelims | Labour | 3169 | 2495 | incl. cartage
|  | Overheads / Prelims | Miscellaneous | 1949 | 1535 | carried from tender est.
|  | Overheads / Prelims | Plant and Equipment | 1546 | 1218
| 1.1.7 subtotal |  |  | 6664 | 5248
2.1.1 | Trim & proof roll subgrade (incl. Level 1 testing) | Earthworks | Plant and Equipment | 12158 | 9148
|  | Earthworks | Labour | 5284 | 3975
|  | Earthworks | Material | 3127 | 2353
|  | Earthworks | Miscellaneous | 2326.6 | 1750
| 2.1.1 subtotal |  |  | 22895.6 | 17226
2.1.2 | Batter shaping & topsoil respread 100mm | Earthworks | Plant and Equipment | 20423 | 16527
|  | Earthworks | Labour | 8725 | 7060
|  | Earthworks | Material | 5770.41 | 4670
| 2.1.2 subtotal |  |  | 34918.41 | 28257
2.1.3 | Excavation in rock, Class A (jack hammer/rock saw) | Earthworks | Plant and Equipment | 64498 | 52411
|  | Earthworks | Labour | 23245 | 18889
|  | Earthworks | Material | 15887 | 12910
|  | Earthworks | Miscellaneous | 9822 | 7981 | quote expires 30/7
| 2.1.3 subtotal |  |  | 113452 | 92191
2.1.4 | Excavate unsuitable mat. & replace w/ approved fill | Earthworks | Plant and Equipment | 42584 | 34260
|  | Earthworks | Labour | 14510 | 11674 | rate ex GST
|  | Earthworks | Material | 9681.73 | 7789
| 2.1.4 subtotal |  |  | 66775.73 | 53723
2.1.5 | Import & place select fill (VENM cert. req.) | Earthworks | Plant and Equipment | 109765 | 77009
|  | Earthworks | Labour | 38685.2 | 27141 | site mtg 2/7 - qty TBC w/ super
| 2.1.5 subtotal |  |  | 148450.2 | 104150
2.1.6 | Bulk earthworks - cut to fill on site | Earthworks | Plant and Equipment | 110832 | 91412
|  | Earthworks | Labour | 41561 | 34279 | allow for wet weather
|  | Earthworks | Material | 21487 | 17721
| 2.1.6 subtotal |  |  | 173880 | 143412
3.1.1 | Kerb & channel B2 barrier type (machine extruded) | Concrete | Material | 44907 | 36233 | rate ex GST
|  | Concrete | Labour | 29111 | 23489
|  | Concrete | Subcontract | 13218 | 10665
|  | Concrete | Plant and Equipment | 8506.99 | 6863
| 3.1.1 subtotal |  |  | 95742.99 | 77250
3.1.2 | Supply & place N32 conc. footings incl. exc. & reo | Concrete | Material | 74727 | 61511
|  | Concrete | Labour | 47983 | 39497
|  | Concrete | Subcontract | 24647 | 20288
|  | Concrete | Plant and Equipment | 18207.25 | 14987
| 3.1.2 subtotal |  |  | 165564.25 | 136283
3.2.1 | Concrete footpath 125thk broom finish | Concrete | Material | 84661 | 66481
|  | Concrete | Labour | 53996 | 42401
|  | Concrete | Subcontract | 27661 | 21721
|  | Concrete | Plant and Equipment | 19641.6 | 15422
| 3.2.1 subtotal |  |  | 185959.6 | 146025
3.2.2 | Vehicle crossings 150thk reinforced | Concrete | Material | 25117 | 21488
|  | Concrete | Labour | 14713.94 | 12589
| 3.2.2 subtotal |  |  | 39830.94 | 34077
3.2.3 | Pram ramps to AS1428.1 incl. TGSIs | Concrete | Material | 31250 | 23293 | carried from tender est.
|  | Concrete | Labour | 22749.11 | 16957 | sub quote - CivilTech 14/6
| 3.2.3 subtotal |  |  | 53999.11 | 40250
4.1.1 | Supply & place DGS40 subbase 200thk compacted (refer dwg C-405) | Pavements & Surfacing | Subcontract | 104459 | 81017
|  | Pavements & Surfacing | Material | 42268.5 | 32783
| 4.1.1 subtotal |  |  | 146727.5 | 113800
4.1.2 | Segmental paving to median (Urbanstone or equiv.) | Pavements & Surfacing | Subcontract | 60809 | 49376 | quote expires 30/7
|  | Pavements & Surfacing | Material | 21957 | 17829
|  | Pavements & Surfacing | Plant and Equipment | 11756.56 | 9546
| 4.1.2 subtotal |  |  | 94522.56 | 76751
4.1.3 | Prime & 2 coat seal 14/7 (incl. sweep) * | Pavements & Surfacing | Subcontract | 12061 | 8984
|  | Pavements & Surfacing | Material | 4232 | 3153
|  | Pavements & Surfacing | Plant and Equipment | 2463.5 | 1835
| 4.1.3 subtotal |  |  | 18756.5 | 13972
4.1.4 | AC14 intermediate course 50thk (C320) | Pavements & Surfacing | Subcontract | 28499 | 22747
|  | Pavements & Surfacing | Material | 12406.59 | 9903
| 4.1.4 subtotal |  |  | 40905.59 | 32650
5.1.1 | Street lighting incl. poles, luminaires & pits | Utilities & Services | Subcontract | 26488 | 21499 | incl. cartage
|  | Utilities & Services | Material | 6079 | 4934
|  | Utilities & Services | Miscellaneous | 3408 | 2767
| 5.1.1 subtotal |  |  | 35975 | 29200
5.1.2 | Sewer maintenance holes 1050dia precast (refer dwg C-306) | Utilities & Services | Subcontract | 30770 | 23361
|  | Utilities & Services | Material | 7497 | 5692
|  | Utilities & Services | Miscellaneous | 4672.61 | 3547 | carried from tender est.
| 5.1.2 subtotal |  |  | 42939.61 | 32600
5.2.1 | Comms conduits P50 x2 incl. pits (NBN spec) | Utilities & Services | Subcontract | 51654 | 43229 | site mtg 2/7 - qty TBC w/ super
|  | Utilities & Services | Material | 9881.01 | 8270
| 5.2.1 subtotal |  |  | 61535.01 | 51499
5.2.2 | DN150 PVC sewer S&L @ min grade incl. compaction test | Utilities & Services | Subcontract | 137362 | 109547 | site mtg 2/7 - qty TBC w/ super
|  | Utilities & Services | Material | 33484 | 26703
|  | Utilities & Services | Miscellaneous | 20176 | 16091 | rate ex GST
| 5.2.2 subtotal |  |  | 191022 | 152341
5.2.3 | DN100 PE watermain S&L incl. fittings & thrust blocks | Utilities & Services | Subcontract | 27146 | 21677
|  | Utilities & Services | Material | 5454 | 4355
|  | Utilities & Services | Miscellaneous | 3645.2 | 2911
| 5.2.3 subtotal |  |  | 36245.2 | 28943
INDIRECT / OFF-BOQ COSTS - no BOQ line item, cost centre only
| Site utes, fuel & tolls | Plant & Equipment | Overheads |  | 18645
|  | Plant & Equipment | Overheads |  | 13112
| subtotal |  |  |  | 31757
| Staff accommodation & living away allowance | Overheads / Prelims | Labour | 12999 |  | rate ex GST
|  | Overheads / Prelims | Miscellaneous | 9381
| subtotal |  |  | 22380 | 0
| HSEQ advisor site visits & audits | Overheads / Prelims | Labour |  | 11574
|  | Overheads / Prelims | Miscellaneous |  | 8618
|  | Overheads / Prelims | Miscellaneous |  | -4500
| subtotal |  |  |  | 15692
| Plant & vehicle registrations and insurances | Insurances & Bonds | Miscellaneous |  | 9733 | allow for wet weather
|  | Insurances & Bonds | Labour |  | 7708 | allow for wet weather
| subtotal |  |  |  | 17441
| External QA / NATA testing over BOQ allowance | Overheads / Prelims | Subcontract |  | 14503 | PC sum
| subtotal |  |  |  | 14503