## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | Preliminaries & Site Establishment |  |  |  | 83935.28
1.1 | Preliminaries & Site Establishment |  |  |  | 83935.28
1.1.1 | Traffic management incl. TMP & permits | wk | 16.9 | 1577 | 26651.3
1.1.2 | Project signage as per spec cl 4.2 | each | 1.51 | 1689.8883 | 2551.73
1.1.3 | Survey & set-out (all works) | item | 1 | 18476.5345 | 18476.53
1.1.4 | Environmental controls - sed. fence, shaker grid etc | item | 1 | 9704.62 | 9704.62
1.1.5 | Site office, amenities & temp fencing | wks | 12.2 | 2176.32 | 26551.1
2 | Bulk & Detailed Earthworks |  |  |  | 543196.74
2.1 | Bulk Earthworks |  |  |  | 237910
2.1.1 | Batter shaping & topsoil respread 100mm | m² | 3941 | 5 | 19705
2.1.2 | Import & place select fill (VENM cert. req.) | t | 6500 | 33.57 | 218205
2.2 | Detailed Earthworks |  |  |  | 305286.74
2.2.1 | Excavation in rock, Class A (jack hammer/rock saw) | m3 | 128.2 | 212.9036 | 27294.24
2.2.2 | Trim & proof roll subgrade (incl. Level 1 testing) | m2 | 23375 | 6 | 140250
2.2.3 | Bulk earthworks - cut to fill on site | m3 | 7871 | 17.5 | 137742.5
3 | Stormwater Drainage |  |  |  | 174816.69
3.1 | Stormwater Drainage |  |  |  | 174816.69
3.1.1 | Precast headwall to suit 450dia | ea | 5 | 3411 | 17055
3.1.2 | Grated inlet pits SA2 type incl. lintel (refer dwg C-204) | each | 8 | 4078.5 | 32628
3.1.3 | GPT unit supply & install (Rocla CDS or approved equiv.) | each | 3 | 29211.8095 | 87635.43
3.1.4 | Supply & lay 600dia RCP RRJ Cl.4 | lm | 79 | 354.8349 | 28031.96
3.1.5 | Subsoil drainage 100dia slotted incl. sock & trench | lm | 210 | 45.0776 | 9466.3
4 | FLEXIBLE PAVEMENTS & SURFACING |  |  |  | 648606.03
4.1 | Flexible Pavements & Surfacing |  |  |  | 648606.03
4.1.1 | Prime & 2 coat seal 14/7 (incl. sweep) * | m2 | 17408 | 7.0057 | 121955.23
4.1.2 | AC14 intermediate course 50thk (C320) | m² | 5904.87 | 38.4264 | 226902.9
4.1.3 | Supply & place DGS40 subbase 200thk compacted | sqm | 6600 | 12.3725 | 81658.5
4.1.4 | Segmental paving to median (Urbanstone or equiv.) | m2 | 428 | 150 | 64200
4.1.5 | AC10 wearing course 30thk (A15E on approaches) | m² | 5125 | 30.0272 | 153889.4
5 | Public Utilities & Services |  |  |  | 720644.34
5.1 | Wet Services |  |  |  | 187746.98
5.1.1 | Sewer maintenance holes 1050dia precast | each | 5 | 5304 | 26520
5.1.2 | DN100 PE watermain S&L incl. fittings & thrust blocks | m | 978.9 | 159.7926 | 156420.98
5.1.3 | Service crossings - potholing & protection (Telstra/APA) | item | 3.6 | 1335 | 4806
5.2 | Dry Services / Electrical |  |  |  | 532897.36
5.2.1 | DN150 PVC sewer S&L @ min grade incl. compaction test | m | 859.6 | 186 | 159885.6
5.2.2 | Street lighting incl. poles, luminaires & pits | No. | 25 | 9609.36 | 240234
5.2.3 | Fire hydrants incl. valve & surface box (refer dwg C-303) | No. | 2.4 | 3650.1311 | 8760.31
5.2.4 | Electrical conduits 100dia incl. trench & marker tape | m | 1910 | 64.9306 | 124017.45
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 59936.84
P.1 | Provisional Sums & Quantities |  |  |  | 59936.84
P.1.1 | Dayworks - labourer incl. small tools | hrs | 85.87 | 104.82 | 9000.89
P.1.2 | Contaminated material - excavate, test & dispose (PROV) | t | 142.5 | 222.5 | 31706.25
P.1.3 | Service relocations - allowance (PROV SUM) | item | 1 | 19229.7 | 19229.7
|  |  |  | TOTAL | 2231135.92

## Budget
Orange Regional Airport - Apron Extension
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Orange City Council |  | Prepared: 6/07/2026 ¦ Rev B ¦ AP
Budget method: Cost Centre / Lump Sum
Item Code | Description | Cost Centre | BOQ Amount ($) | Budget ($) | Margin (%) | Notes
1.1.1 | Traffic management incl. TMP & permits | Overheads / Prelims | 26651.3 | 23500 | 11.82% | incl. cartage
1.1.2 | Project signage as per spec cl 4.2 | Overheads / Prelims | 2551.73 | 2133 | 16.41%
1.1.3 | Survey & set-out (all works) | Overheads / Prelims | 18476.53 | 14942 | 19.13% | PC sum
1.1.4 | Environmental controls - sed. fence, shaker grid etc | Overheads / Prelims | 9704.62 | 8253 | 14.96% | carried from tender est.
1.1.5 | Site office, amenities & temp fencing | Overheads / Prelims | 26551.1 | 22294 | 16.03% | quote expires 30/7
2.1.1 | Batter shaping & topsoil respread 100mm | Earthworks | 19705 | 16062 | 18.49% | carried from tender est.
2.1.2 | Import & place select fill (VENM cert. req.) | Earthworks | 218205 | 184791 | 15.31% | rate ex GST
2.2.1 | Excavation in rock, Class A (jack hammer/rock saw) | Earthworks | 27294.24 | 23297 | 14.64% | carried from tender est.
2.2.2 | Trim & proof roll subgrade (incl. Level 1 testing) | Earthworks | 140250 | 117050 | 16.54%
2.2.3 | Bulk earthworks - cut to fill on site | Earthworks | 96420 | 79835 | 17.2% | 70/30 split w/ Plant & Equipment
2.2.3 | Bulk earthworks - cut to fill on site | Plant & Equipment | 41322.5 | 34215 | 17.2% | 70/30 split w/ Earthworks
3.1.1 | Precast headwall to suit 450dia | Drainage | 17055 | 14598 | 14.41% | carried from tender est.
3.1.2 | Grated inlet pits SA2 type incl. lintel (refer dwg C-204) | Drainage | 32628 | 27436 | 15.91%
3.1.3 | GPT unit supply & install (Rocla CDS or approved equiv.) | Drainage | 87635.43 | 71843 | 18.02%
3.1.4 | Supply & lay 600dia RCP RRJ Cl.4 | Drainage | 28031.96 | 23452 | 16.34% | PC sum
3.1.5 | Subsoil drainage 100dia slotted incl. sock & trench | Drainage | 9466.3 | 8050 | 14.96% | sub quote - CivilTech 14/6
4.1.1 | Prime & 2 coat seal 14/7 (incl. sweep) * | Pavements & Surfacing | 85369 | 69475 | 18.62% | 70/30 split w/ Plant & Equipment
4.1.1 | Prime & 2 coat seal 14/7 (incl. sweep) * | Plant & Equipment | 36586.23 | 29775 | 18.62% | 70/30 split w/ Pavements & Surfacing
4.1.2 | AC14 intermediate course 50thk (C320) | Pavements & Surfacing | 124797 | 109522 | 12.24% | 55/45 split w/ Plant & Equipment
4.1.2 | AC14 intermediate course 50thk (C320) | Plant & Equipment | 102105.9 | 89609 | 12.24% | 55/45 split w/ Pavements & Surfacing
4.1.3 | Supply & place DGS40 subbase 200thk compacted | Pavements & Surfacing | 81658.5 | 68148 | 16.55% | site mtg 2/7 - qty TBC w/ super
4.1.4 | Segmental paving to median (Urbanstone or equiv.) | Pavements & Surfacing | 64200 | 52995 | 17.45% | quote expires 30/7
4.1.5 | AC10 wearing course 30thk (A15E on approaches) | Pavements & Surfacing | 153889.4 | 128200 | 16.69%
5.1.1 | Sewer maintenance holes 1050dia precast | Utilities & Services | 26520 | 20821 | 21.49% | sub quote - CivilTech 14/6
5.1.2 | DN100 PE watermain S&L incl. fittings & thrust blocks | Utilities & Services | 93853 | 80332 | 14.41% | 60/40 split w/ Earthworks
5.1.2 | DN100 PE watermain S&L incl. fittings & thrust blocks | Earthworks | 62567.98 | 53555 | 14.41% | 60/40 split w/ Utilities & Services
5.1.3 | Service crossings - potholing & protection (Telstra/APA) | Utilities & Services | 4806 | 4100 | 14.69% | check qty vs dwg rev D
5.2.1 | DN150 PVC sewer S&L @ min grade incl. compaction test | Utilities & Services | 127908 | 104640 | 18.19% | 80/20 split w/ Earthworks
5.2.1 | DN150 PVC sewer S&L @ min grade incl. compaction test | Earthworks | 31977.6 | 26160 | 18.19% | 80/20 split w/ Utilities & Services
5.2.2 | Street lighting incl. poles, luminaires & pits | Utilities & Services | 144140 | 116634 | 19.08% | 60/40 split w/ Earthworks
5.2.2 | Street lighting incl. poles, luminaires & pits | Earthworks | 96094 | 77756 | 19.08% | 60/40 split w/ Utilities & Services
5.2.3 | Fire hydrants incl. valve & surface box (refer dwg C-303) | Utilities & Services | 8760.31 | 7300 | 16.67%
5.2.4 | Electrical conduits 100dia incl. trench & marker tape | Utilities & Services | 124017.45 | 91391 | 26.31% | PC sum
| TOTALS |  | 2171199.08 | 1802164 | 17%