## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | PRELIMINARIES & SITE ESTABLISHMENT |  |  |  | 137360.64
1.1 | Establishment |  |  |  | 63313
1.1.1 | Environmental controls - sed. fence, shaker grid etc | item | 1 | 11173 | 11173
1.1.2 | Site office, amenities & temp fencing * | wks | 30 | 1738 | 52140
1.2 | Ongoing Site Costs |  |  |  | 74047.64
1.2.1 | Dilapidation surveys & CCTV existing assets | ea | 2 | 5071 | 10142
1.2.2 | Site establishment, mobilisation & demob | Item | 1 | 25685.78 | 25685.78
1.2.3 | Traffic management incl. TMP & permits | wk | 10 | 3821.9862 | 38219.86
2 | BULK & DETAILED EARTHWORKS |  |  |  | 871095.89
2.1 | Bulk Earthworks |  |  |  | 323269.75
2.1.1 | Trim & proof roll subgrade (incl. Level 1 testing) | m² | 20704.33 | 5 | 103521.65
2.1.2 | Batter shaping & topsoil respread 100mm | m² | 3965 | 7.34 | 29103.1
2.1.3 | Import & place select fill (VENM cert. req.) | m³ | 5866 | 32.5 | 190645
2.2 | Detailed Earthworks |  |  |  | 547826.14
2.2.1 | Excavation in rock, Class A (jack hammer/rock saw) | m³ | 65.6 | 232 | 15219.2
2.2.2 | Excavate unsuitable mat. & replace w/ approved fill | m³ | 2215 | 49 | 108535
2.2.3 | Bulk earthworks - cut to fill on site (refer dwg C-209) | m3 | 19984.54 | 21.22 | 424071.94
3 | STORMWATER DRAINAGE |  |  |  | 294332.66
3.1 | Pipelines |  |  |  | 207333.64
3.1.1 | Subsoil drainage 100dia slotted incl. sock & trench | m | 845.51 | 47.8417 | 40450.64
3.1.2 | GPT unit supply & install (Rocla CDS or approved equiv.) | each | 5 | 33376.6 | 166883
3.2 | Pits & Structures |  |  |  | 86999.02
3.2.1 | Precast headwall to suit 450dia (refer dwg C-404) | No. | 5 | 6217 | 31085
3.2.2 | Junction pits 900x900 precast incl. lid | each | 14.7 | 3803.675 | 55914.02
4 | CONCRETE WORKS |  |  |  | 543057.4
4.1 | Concrete Works |  |  |  | 543057.4
4.1.1 | Supply & place N32 conc. footings incl. exc. & reo | m³ | 189 | 425.5 | 80419.5
4.1.2 | Kerb & channel B2 barrier type (machine extruded) | LM | 379.7 | 65.31 | 24798.21
4.1.3 | Vehicle crossings 150thk reinforced | m² | 373.67 | 122.7459 | 45866.46
4.1.4 | Concrete footpath 125thk broom finish | m2 | 2857.41 | 78.25 | 223592.33
4.1.5 | Supply & fix reinforcement (all grades) | t | 60 | 2203 | 132180
4.1.6 | Pram ramps to AS1428.1 incl. TGSIs | No. | 20 | 1810.0451 | 36200.9
5 | FLEXIBLE PAVEMENTS & SURFACING |  |  |  | 1403778.06
5.1 | Granular Pavements |  |  |  | 423203.58
5.1.1 | Longitudinal linemarking & RRPMs as per dwgs | lm | 2289.9 | 8.9636 | 20525.75
5.1.2 | Supply & place DGS40 subbase 200thk compacted | sqm | 18964.9 | 11.23 | 212975.83
5.1.3 | AC14 intermediate course 50thk (C320) | m² | 7026 | 27 | 189702
5.2 | Asphalt & Surfacing |  |  |  | 980574.48
5.2.1 | Supply & place DGB20 basecourse 150thk | m² | 20337 | 22.47 | 456972.39
5.2.2 | Segmental paving to median (Urbanstone or equiv.) | m² | 527.5 | 108.3491 | 57154.15
5.2.3 | Prime & 2 coat seal 14/7 (incl. sweep) | m² | 11968.19 | 9 | 107713.71
5.2.4 | AC10 wearing course 30thk (A15E on approaches) | m² | 11387.34 | 31.5029 | 358734.23
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 133445.84
P.1 | Provisional Sums & Quantities |  |  |  | 133445.84
P.1.1 | Contaminated material - excavate, test & dispose (PROV) | m3 | 85 | 319 | 27115
P.1.2 | Service relocations - allowance (PROV SUM) | LS | 1 | 58414 | 58414
P.1.3 | Rock excavation over & above measured qty (PROV) | m3 | 276.5 | 133.6439 | 36952.54
P.1.4 | Dayworks - project engineer | hr | 80 | 137.0538 | 10964.3
|  |  |  | TOTAL | 3383070.49

## Budget
Cooma Saleyards Truck Wash & Hardstand
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Snowy Monaro Regional Council |  | Prepared: 23/06/2026 ¦ Rev C ¦ B. Harris
Budget method: Cost Centre / Resource Breakdown
Item Code | Description | Cost Centre | Resource Category | BOQ ($) | Budget ($) | Notes
1.1.1 | Environmental controls - sed. fence, shaker grid etc | Overheads / Prelims | Labour | 4719 | 4297
|  | Overheads / Prelims | Miscellaneous | 4112 | 3744
|  | Overheads / Prelims | Plant and Equipment | 2342 | 2133
| 1.1.1 subtotal |  |  | 11173 | 10174
1.1.2 | Site office, amenities & temp fencing * | Overheads / Prelims | Labour | 19963 | 17938
|  | Overheads / Prelims | Miscellaneous | 15468 | 13899
|  | Overheads / Prelims | Plant and Equipment | 11320 | 10172 | sub quote - CivilTech 14/6
|  | Overheads / Prelims | Subcontract | 5389 | 4841
| 1.1.2 subtotal |  |  | 52140 | 46850
1.2.1 | Dilapidation surveys & CCTV existing assets | Overheads / Prelims | Labour | 4547 | 3878
|  | Overheads / Prelims | Miscellaneous | 3270 | 2789
|  | Overheads / Prelims | Plant and Equipment | 2325 | 1983
| 1.2.1 subtotal |  |  | 10142 | 8650
1.2.2 | Site establishment, mobilisation & demob | Overheads / Prelims | Labour | 10397 | 9637 | incl. cartage
|  | Overheads / Prelims | Miscellaneous | 8487 | 7867
|  | Overheads / Prelims | Plant and Equipment | 4344 | 4026
|  | Overheads / Prelims | Subcontract | 2457.78 | 2278
| 1.2.2 subtotal |  |  | 25685.78 | 23808
1.2.3 | Traffic management incl. TMP & permits | Overheads / Prelims | Labour | 13324 | 11487
|  | Overheads / Prelims | Miscellaneous | 12466 | 10747
|  | Overheads / Prelims | Plant and Equipment | 8445 | 7281 | site mtg 2/7 - qty TBC w/ super
|  | Overheads / Prelims | Subcontract | 3984.86 | 3435
| 1.2.3 subtotal |  |  | 38219.86 | 32950
2.1.1 | Trim & proof roll subgrade (incl. Level 1 testing) | Earthworks | Plant and Equipment | 63395 | 57182
|  | Earthworks | Labour | 25041 | 22586
|  | Earthworks | Material | 15085.65 | 13607
| 2.1.1 subtotal |  |  | 103521.65 | 93375
2.1.2 | Batter shaping & topsoil respread 100mm | Earthworks | Plant and Equipment | 18441 | 16602
|  | Earthworks | Labour | 7029 | 6328
|  | Earthworks | Material | 3633.1 | 3270
| 2.1.2 subtotal |  |  | 29103.1 | 26200
2.1.3 | Import & place select fill (VENM cert. req.) | Plant & Equipment | Plant and Equipment | 142209 | 130353 | allow for wet weather
|  | Labour | Labour | 48436 | 44397
| 2.1.3 subtotal |  |  | 190645 | 174750
2.2.1 | Excavation in rock, Class A (jack hammer/rock saw) | Earthworks | Plant and Equipment | 9232 | 7996 | quote expires 30/7
|  | Earthworks | Labour | 3849 | 3334
|  | Earthworks | Material | 2138.2 | 1851
| 2.2.1 subtotal |  |  | 15219.2 | 13181
2.2.2 | Excavate unsuitable mat. & replace w/ approved fill | Earthworks | Plant and Equipment | 80416 | 72961
|  | Earthworks | Labour | 28119 | 25513
| 2.2.2 subtotal |  |  | 108535 | 98474
2.2.3 | Bulk earthworks - cut to fill on site (refer dwg C-209) | Plant & Equipment | Plant and Equipment | 263331 | 281764
|  | Labour | Labour | 96576 | 103336
|  | Earthworks | Material | 64164.94 | 68656 | incl. cartage
| 2.2.3 subtotal |  |  | 424071.94 | 453756
3.1.1 | Subsoil drainage 100dia slotted incl. sock & trench | Drainage | Material | 18944 | 16485
|  | Drainage | Labour | 11833 | 10297
|  | Drainage | Plant and Equipment | 9673.64 | 8418
| 3.1.1 subtotal |  |  | 40450.64 | 35200
3.1.2 | GPT unit supply & install (Rocla CDS or approved equiv.) | Drainage | Material | 75537 | see 2.1.1
|  | Labour | Labour | 51609 | 48070 | PC sum
|  | Plant & Equipment | Plant and Equipment | 39737 | 37012
| 3.1.2 subtotal |  |  | 166883 | 85082
3.2.1 | Precast headwall to suit 450dia (refer dwg C-404) | Drainage | Material | 13714 | 12186
|  | Drainage | Labour | 7164 | 6366
|  | Drainage | Plant and Equipment | 7160 | 6362
|  | Drainage | Subcontract | 3047 | 2709
| 3.2.1 subtotal |  |  | 31085 | 27623
3.2.2 | Junction pits 900x900 precast incl. lid | Drainage | Material | 33358 | 29871
|  | Drainage | Labour | 22556.02 | 20198
| 3.2.2 subtotal |  |  | 55914.02 | 50069
4.1.1 | Supply & place N32 conc. footings incl. exc. & reo | Concrete | Material | 41079 | 36395
|  | Concrete | Labour | 27374 | 24253
|  | Concrete | Subcontract | 11966.5 | 10602
| 4.1.1 subtotal |  |  | 80419.5 | 71250
4.1.2 | Kerb & channel B2 barrier type (machine extruded) | Concrete | Material | 12779 | 11571
|  | Concrete | Labour | 7956 | 7204
|  | Concrete | Subcontract | 4063.21 | 3678
| 4.1.2 subtotal |  |  | 24798.21 | 22453
4.1.3 | Vehicle crossings 150thk reinforced | Concrete | Material | 28662 | 25215
|  | Concrete | Labour | 17204.46 | 15135 | PC sum
| 4.1.3 subtotal |  |  | 45866.46 | 40350
4.1.4 | Concrete footpath 125thk broom finish | Concrete | Material | 119638 | 107362 | sub quote - CivilTech 14/6
|  | Labour | Labour | 67174 | 60282
|  | Concrete | Subcontract | 36780.33 | 33006
| 4.1.4 subtotal |  |  | 223592.33 | 200650
4.1.5 | Supply & fix reinforcement (all grades) | Concrete | Material | 61192 | 55295
|  | Concrete | Labour | 42845 | 38716 | quote expires 30/7
|  | Concrete | Subcontract | 16614 | 15013
|  | Concrete | Plant and Equipment | 11529 | 10417
| 4.1.5 subtotal |  |  | 132180 | 119441
4.1.6 | Pram ramps to AS1428.1 incl. TGSIs | Concrete | Material | 21466 | 19731
|  | Concrete | Labour | 14734.9 | 13544
| 4.1.6 subtotal |  |  | 36200.9 | 33275
5.1.1 | Longitudinal linemarking & RRPMs as per dwgs | Pavements & Surfacing | Subcontract | 12066 | 10725
|  | Pavements & Surfacing | Material | 5396 | 4796
|  | Pavements & Surfacing | Plant and Equipment | 3063.75 | 2722
| 5.1.1 subtotal |  |  | 20525.75 | 18243
5.1.2 | Supply & place DGS40 subbase 200thk compacted | Pavements & Surfacing | Subcontract | 130210 | 109708
|  | Pavements & Surfacing | Material | 42419 | 35740
|  | Pavements & Surfacing | Plant and Equipment | 25586 | 21558
|  | Pavements & Surfacing | Labour | 14760.83 | 12437
| 5.1.2 subtotal |  |  | 212975.83 | 179443
5.1.3 | AC14 intermediate course 50thk (C320) | Pavements & Surfacing | Subcontract | 98910 | 86813
|  | Pavements & Surfacing | Material | 49858 | 43760
|  | Plant & Equipment | Plant and Equipment | 26607 | 23353
|  | Labour | Labour | 14327 | 12574
| 5.1.3 subtotal |  |  | 189702 | 166500
5.2.1 | Supply & place DGB20 basecourse 150thk | Pavements & Surfacing | Subcontract | 291264 | 255081
|  | Pavements & Surfacing | Material | 107083 | 93780
|  | Plant & Equipment | Plant and Equipment | 58625.39 | 51342
| 5.2.1 subtotal |  |  | 456972.39 | 400203
5.2.2 | Segmental paving to median (Urbanstone or equiv.) | Pavements & Surfacing | Subcontract | 35357 | 30963
|  | Pavements & Surfacing | Material | 14966 | 13106
|  | Pavements & Surfacing | Plant and Equipment | 6831.15 | 5981
| 5.2.2 subtotal |  |  | 57154.15 | 50050
5.2.3 | Prime & 2 coat seal 14/7 (incl. sweep) | Pavements & Surfacing | Subcontract | 68276 | 66207
|  | Pavements & Surfacing | Material | 25912 | 25127
|  | Plant & Equipment | Plant and Equipment | 13525.71 | 13116
| 5.2.3 subtotal |  |  | 107713.71 | 104450
5.2.4 | AC10 wearing course 30thk (A15E on approaches) | Pavements & Surfacing | Subcontract | 256837 | 223803
|  | Pavements & Surfacing | Material | 101897.23 | 88791
| 5.2.4 subtotal |  |  | 358734.23 | 312594