## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | PRELIMINARIES & SITE ESTABLISHMENT |  |  |  | 74858.34
1.1 | Preliminaries & Site Establishment |  |  |  | 74858.34
1.1.1 | Project signage as per spec cl 4.2 * | ea | 1.1 | 1098.49 | 1208.34
1.1.2 | Site office, amenities & temp fencing | week | 36 | 1249.75 | 44991
1.1.3 | Site establishment, mobilisation & demob | Item | 1 | 26250 | 26250
1.1.4 | Dilapidation surveys & CCTV existing assets | ea | 1 | 2409 | 2409
2 | Bulk & Detailed Earthworks |  |  |  | 450897.44
2.1 | Bulk Earthworks |  |  |  | 196199.73
2.1.1 | Bulk earthworks - cut to fill on site | m3 | 15598.9 | 11.0423 | 172247.73
2.1.2 | Trim & proof roll subgrade (incl. Level 1 testing) | m2 | 3992 | 6 | 23952
2.2 | Detailed Earthworks |  |  |  | 254697.71
2.2.1 | Excavate unsuitable mat. & replace w/ approved fill | m³ | 272 | 40 | 10880
2.2.2 | Batter shaping & topsoil respread 100mm | m² | 2956 | 3.7028 | 10945.48
2.2.3 | Import & place select fill (VENM cert. req.) | m³ | 4440 | 52.4487 | 232872.23
3 | STORMWATER DRAINAGE |  |  |  | 179315.88
3.1 | Stormwater Drainage |  |  |  | 179315.88
3.1.1 | GPT unit supply & install (Rocla CDS or approved equiv.) | each | 1.98 | 31317.5 | 62008.65
3.1.2 | Junction pits 900x900 precast incl. lid | ea | 6.5 | 3359 | 21833.5
3.1.3 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | m | 184.6 | 250.0284 | 46155.24
3.1.4 | Grated inlet pits SA2 type incl. lintel | No. | 10.66 | 4626.5 | 49318.49
4 | PUBLIC UTILITIES & SERVICES |  |  |  | 389041.53
4.1 | Public Utilities & Services |  |  |  | 389041.53
4.1.1 | Fire hydrants incl. valve & surface box | ea | 7.4 | 2723 | 20150.2
4.1.2 | Electrical conduits 100dia incl. trench & marker tape | m | 1348.9 | 49.15 | 66298.44
4.1.3 | Sewer maintenance holes 1050dia precast | each | 7.9 | 8059.07 | 63666.65
4.1.4 | Service crossings - potholing & protection (Telstra/APA) | each | 10 | 3196 | 31960
4.1.5 | Street lighting incl. poles, luminaires & pits | each | 15.1 | 6430.63 | 97102.51
4.1.6 | DN150 PVC sewer S&L @ min grade incl. compaction test | lm | 107 | 150.4397 | 16097.05
4.1.7 | DN100 PE watermain S&L incl. fittings & thrust blocks | lm | 697.15 | 134.5 | 93766.68
5 | CONCRETE WORKS |  |  |  | 463643.72
5.1 | Insitu Concrete |  |  |  | 186943.49
5.1.1 | Kerb & channel B2 barrier type (machine extruded) | lm | 2271 | 56.67 | 128697.57
5.1.2 | Concrete footpath 125thk broom finish | m2 | 901.5 | 64.61 | 58245.92
5.2 | Kerbs, Paths & Minor Conc. |  |  |  | 276700.23
5.2.1 | Supply & fix reinforcement (all grades) | t | 105.3 | 2501.15 | 263371.1
5.2.2 | Pram ramps to AS1428.1 incl. TGSIs | No. | 7.32 | 1820.92 | 13329.13
6 | Flexible Pavements & Surfacing |  |  |  | 1230876.94
6.1 | Flexible Pavements & Surfacing |  |  |  | 1230876.94
6.1.1 | Supply & place DGB20 basecourse 150thk | sqm | 12632.4 | 18.1176 | 228868.77
6.1.2 | AC14 intermediate course 50thk (C320) | m2 | 10711.3 | 25 | 267782.5
6.1.3 | AC10 wearing course 30thk (A15E on approaches) | m2 | 14662 | 33.5 | 491177
6.1.4 | Supply & place DGS40 subbase 200thk compacted | m2 | 6306.67 | 13.8589 | 87403.51
6.1.5 | Segmental paving to median (Urbanstone or equiv.) | m2 | 893.6 | 99.3791 | 88805.16
6.1.6 | Prime & 2 coat seal 14/7 (incl. sweep) | m2 | 8355 | 8 | 66840
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 84389.64
P.1 | Provisional Sums & Quantities |  |  |  | 84389.64
P.1.1 | Service relocations - allowance (PROV SUM) | LS | 1 | 24626.5433 | 24626.54
P.1.2 | Latent conditions allowance (PROV SUM) | item | 1 | 35037.2 | 35037.2
P.1.3 | Dayworks - 20t excavator incl. operator | hr | 118.62 | 208.4463 | 24725.9
|  |  |  | TOTAL | 2873023.49

## Budget
Geelong Northern Growth Area - Trunk Infrastructure
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: City of Greater Geelong |  | Prepared: 23/06/2026 ¦ Rev 0 ¦ S. Nguyen
Budget method: Cost Centre + Zones / Lump Sum
Item Code | Description | Cost Centre | Zone | BOQ Amount ($) | Budget ($) | Margin (%) | Notes
1.1.1 | Project signage as per spec cl 4.2 * | Overheads / Prelims | Project Wide | 1208.34 | 1047 | 13.35%
1.1.2 | Site office, amenities & temp fencing | Overheads / Prelims | Project Wide | 44991 | 35083 | 22.02% | rate ex GST
1.1.3 | Site establishment, mobilisation & demob | Overheads / Prelims | Project Wide | 26250 | 20022 | 23.73%
1.1.4 | Dilapidation surveys & CCTV existing assets | Overheads / Prelims | Project Wide | 2409 | 1897 | 21.25% | PC sum
2.1.1 | Bulk earthworks - cut to fill on site | Earthworks | Zone A | 120573 | 99890 | 17.15% | 70% Zone A
2.1.1 | Bulk earthworks - cut to fill on site | Earthworks | Zone B | 51674.73 | 42810 | 17.15% | 30% Zone B
2.1.2 | Trim & proof roll subgrade (incl. Level 1 testing) | Earthworks | Zone B | 23952 | 19832 | 17.2%
2.2.1 | Excavate unsuitable mat. & replace w/ approved fill | Earthworks | Zone C | 10880 | 8410 | 22.7%
2.2.2 | Batter shaping & topsoil respread 100mm | Earthworks | Zone C | 10945.48 | 9158 | 16.33% | sub quote - CivilTech 14/6
2.2.3 | Import & place select fill (VENM cert. req.) | Earthworks | Zone C | 139723 | 119124 | 14.74% | 60% Zone C
2.2.3 | Import & place select fill (VENM cert. req.) | Earthworks | Zone A | 93149.23 | 79416 | 14.74% | 40% Zone A
3.1.1 | GPT unit supply & install (Rocla CDS or approved equiv.) | Drainage | Zone A | 62008.65 | 51950 | 16.22% | carried from tender est.
3.1.2 | Junction pits 900x900 precast incl. lid | Drainage | Zone B | 21833.5 | 18349 | 15.96% | allow for wet weather
3.1.3 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | Drainage | Zone C | 46155.24 | 38203 | 17.23% | incl. cartage
3.1.4 | Grated inlet pits SA2 type incl. lintel | Drainage | Zone C | 49318.49 | 41450 | 15.95% | check qty vs dwg rev D
4.1.1 | Fire hydrants incl. valve & surface box | Utilities & Services | Zone A | 20150.2 | 17200 | 14.64%
4.1.2 | Electrical conduits 100dia incl. trench & marker tape | Utilities & Services | Zone A | 66298.44 | 54338 | 18.04%
4.1.3 | Sewer maintenance holes 1050dia precast | Utilities & Services | Zone A | 31833 | 26496 | 16.77% | 50% Zone A
4.1.3 | Sewer maintenance holes 1050dia precast | Utilities & Services | Zone D | 31833.65 | 26497 | 16.76% | 50% Zone D
4.1.4 | Service crossings - potholing & protection (Telstra/APA) | Utilities & Services | Zone A | 31960 | 26232 | 17.92% | incl. cartage
4.1.5 | Street lighting incl. poles, luminaires & pits | Utilities & Services | Zone A | 58262 | 51122 | 12.25% | 60% Zone A
4.1.5 | Street lighting incl. poles, luminaires & pits | Utilities & Services | Zone D | 38840.51 | 34081 | 12.25% | 40% Zone D
4.1.6 | DN150 PVC sewer S&L @ min grade incl. compaction test | Utilities & Services | Zone A | 16097.05 | 13116 | 18.52%
4.1.7 | DN100 PE watermain S&L incl. fittings & thrust blocks | Utilities & Services | Zone D | 46883 | 39250 | 16.28% | 50% Zone D
4.1.7 | DN100 PE watermain S&L incl. fittings & thrust blocks | Utilities & Services | Zone A | 46883.68 | 39250 | 16.28% | 50% Zone A
5.1.1 | Kerb & channel B2 barrier type (machine extruded) | Concrete | Zone B | 64349 | 54050 | 16% | 50% Zone B
5.1.1 | Kerb & channel B2 barrier type (machine extruded) | Concrete | Zone C | 64348.57 | 54050 | 16% | 50% Zone C
5.1.2 | Concrete footpath 125thk broom finish | Concrete | Zone C | 58245.92 | 48600 | 16.56%
5.2.1 | Supply & fix reinforcement (all grades) | Concrete | Zone B | 263371.1 | 212732 | 19.23%
5.2.2 | Pram ramps to AS1428.1 incl. TGSIs | Concrete | Zone B | 13329.13 | 11400 | 14.47%
6.1.1 | Supply & place DGB20 basecourse 150thk | Pavements & Surfacing | Zone C | 228868.77 | 188350 | 17.7%
6.1.2 | AC14 intermediate course 50thk (C320) | Pavements & Surfacing | Zone C | 267782.5 | 218900 | 18.25%
6.1.3 | AC10 wearing course 30thk (A15E on approaches) | Pavements & Surfacing | Zone B | 491177 | 396679 | 19.24% | PC sum
6.1.4 | Supply & place DGS40 subbase 200thk compacted | Pavements & Surfacing | Zone B | 87403.51 | 69400 | 20.6% | carried from tender est.
6.1.5 | Segmental paving to median (Urbanstone or equiv.) | Pavements & Surfacing | Zone D | 62164 | 52010 | 16.33% | 70% Zone D
6.1.5 | Segmental paving to median (Urbanstone or equiv.) | Pavements & Surfacing | Zone C | 26641.16 | 22290 | 16.33% | 30% Zone C
6.1.6 | Prime & 2 coat seal 14/7 (incl. sweep) | Pavements & Surfacing | Zone D | 66840 | 57880 | 13.41%
| TOTALS |  |  | 2788633.85 | 2300564 | 17.5%