## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | Preliminaries & Site Establishment |  |  |  | 116009.22
1.1 | Preliminaries & Site Establishment |  |  |  | 116009.22
1.1.1 | Environmental controls - sed. fence, shaker grid etc | item | 1 | 8816 | 8816
1.1.2 | Site establishment, mobilisation & demob | LS | 1 | 60680.2957 | 60680.3
1.1.3 | Dilapidation surveys & CCTV existing assets | ea | 5 | 4964 | 24820
1.1.4 | Site office, amenities & temp fencing | week | 15 | 1239.4 | 18591
1.1.5 | Project signage as per spec cl 4.2 | No. | 3.18 | 975.4476 | 3101.92
2 | Demolition & Site Clearing |  |  |  | 136143.56
2.1 | Demolition & Site Clearing - Part A |  |  |  | 58048.29
2.1.1 | Demolish exist. structures & cart away | LS | 1 | 30277 | 30277
2.1.2 | Saw cut & demolish exist. concrete pavement | sqm | 1089.07 | 25.5 | 27771.29
2.2 | Demolition & Site Clearing - Part B |  |  |  | 78095.27
2.2.1 | Remove trees incl. stump grinding (arborist sup.) (refer dwg C-101) | No. | 27.54 | 2588 | 71273.52
2.2.2 | Remove exist. kerb & channel & dispose | m | 325 | 20.99 | 6821.75
3 | BULK & DETAILED EARTHWORKS |  |  |  | 585112.86
3.1 | Bulk & Detailed Earthworks |  |  |  | 585112.86
3.1.1 | Trim & proof roll subgrade (incl. Level 1 testing) | m² | 3538.68 | 4.2914 | 15185.89
3.1.2 | Bulk earthworks - cut to fill on site | m3 | 13300 | 19.2029 | 255398.57
3.1.3 | Import & place select fill (VENM cert. req.) | t | 2625.14 | 50 | 131257
3.1.4 | Excavate unsuitable mat. & replace w/ approved fill | m³ | 857 | 66 | 56562
3.1.5 | Excavation in rock, Class A (jack hammer/rock saw) | m3 | 475.11 | 189.06 | 89824.3
3.1.6 | Batter shaping & topsoil respread 100mm | m² | 8018.5 | 4.6 | 36885.1
4 | CONCRETE WORKS |  |  |  | 736871.23
4.1 | Concrete Works |  |  |  | 736871.23
4.1.1 | Concrete footpath 125thk broom finish | m2 | 3173 | 80 | 253840
4.1.2 | Supply & fix reinforcement (all grades) * | tonne | 73.78 | 2571.55 | 189728.96
4.1.3 | Pram ramps to AS1428.1 incl. TGSIs | ea | 3.16 | 2045.3315 | 6463.25
4.1.4 | Kerb & channel B2 barrier type (machine extruded) * | m | 1847.93 | 67.26 | 124291.77
4.1.5 | Supply & place N40 slab on grade 200thk incl. SL82 | m2 | 1855 | 83.64 | 155152.2
4.1.6 | Vehicle crossings 150thk reinforced | m² | 63 | 117.3817 | 7395.05
5 | Flexible Pavements & Surfacing |  |  |  | 1315722.1
5.1 | Granular Pavements |  |  |  | 673296.44
5.1.1 | Prime & 2 coat seal 14/7 (incl. sweep) | m² | 11393 | 11.73 | 133639.89
5.1.2 | AC10 wearing course 30thk (A15E on approaches) | m2 | 2145 | 25.1231 | 53889.05
5.1.3 | Supply & place DGS40 subbase 200thk compacted | sqm | 19430.7 | 25 | 485767.5
5.2 | Asphalt & Surfacing |  |  |  | 642425.66
5.2.1 | Longitudinal linemarking & RRPMs as per dwgs | m | 4414 | 6.5545 | 28931.56
5.2.2 | Segmental paving to median (Urbanstone or equiv.) | m² | 590 | 141 | 83190
5.2.3 | Supply & place DGB20 basecourse 150thk | m2 | 17976.41 | 29.5 | 530304.1
6 | Structures & Retaining |  |  |  | 929549.64
6.1 | Structures & Retaining - Part A |  |  |  | 417749.05
6.1.1 | Handrail - galv. tube to AS1657 | m | 280 | 223.1769 | 62489.53
6.1.2 | Reinforced blockwork retaining wall H<1.8m incl. found. | m | 756 | 469.92 | 355259.52
6.2 | Structures & Retaining - Part B |  |  |  | 511800.59
6.2.1 | Guardrail w-beam incl. terminals (public road spec) | m | 609 | 154 | 93786
6.2.2 | Precast L-wall units supply & install | m | 229 | 1388 | 317852
6.2.3 | Structural steel - galv. incl. shop dwgs (S&E) | tonne | 27.06 | 3701.5 | 100162.59
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 149199.84
P.1 | Provisional Sums & Quantities |  |  |  | 149199.84
P.1.1 | Dayworks - project engineer | hrs | 30 | 152.5 | 4575
P.1.2 | Contaminated material - excavate, test & dispose (PROV) | m3 | 393.29 | 266.36 | 104756.72
P.1.3 | Latent conditions allowance (PROV SUM) | LS | 1 | 27147.7244 | 27147.72
P.1.4 | Dayworks - 20t excavator incl. operator | hr | 70 | 181.72 | 12720.4
|  |  |  | TOTAL | 3968608.45

## Budget
Dubbo Bridge St Reconstruction (CH 120 - CH 980)
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Dubbo Regional Council |  | Prepared: 3/07/2026 ¦ Rev C ¦ S. Nguyen
Budget method: Cost Centre + Zones / Lump Sum
Item Code | Description | Cost Centre | Zone | BOQ Amount ($) | Budget ($) | Margin (%) | Notes
1.1.1 | Environmental controls - sed. fence, shaker grid etc | Overheads / Prelims | Project Wide | 8816 | 7082 | 19.67% | PC sum
1.1.2 | Site establishment, mobilisation & demob | Overheads / Prelims | Project Wide | 60680.3 | 53700 | 11.5%
1.1.3 | Dilapidation surveys & CCTV existing assets | Overheads / Prelims | Project Wide | 24820 | 21097 | 15% | incl. cartage
1.1.4 | Site office, amenities & temp fencing | Overheads / Prelims | Project Wide | 18591 | 15900 | 14.47% | sub quote - CivilTech 14/6
1.1.5 | Project signage as per spec cl 4.2 | Overheads / Prelims | Project Wide | 3101.92 | 2471 | 20.34% | PC sum
2.1.1 | Demolish exist. structures & cart away | Earthworks | Zone B | 30277 | 25356 | 16.25% | quote expires 30/7
2.1.2 | Saw cut & demolish exist. concrete pavement | Earthworks | Zone B | 27771.29 | 23421 | 15.66% | sub quote - CivilTech 14/6
2.2.1 | Remove trees incl. stump grinding (arborist sup.) (refer dwg C-101) | Earthworks | Zone A | 71273.52 | 62534 | 12.26% | carried from tender est.
2.2.2 | Remove exist. kerb & channel & dispose | Earthworks | Zone A | 6821.75 | 5531 | 18.92% | allow for wet weather
3.1.1 | Trim & proof roll subgrade (incl. Level 1 testing) | Earthworks | Zone C | 15185.89 | 12436 | 18.11% | carried from tender est.
3.1.2 | Bulk earthworks - cut to fill on site | Earthworks | Zone C | 255398.57 | 218380 | 14.49%
3.1.3 | Import & place select fill (VENM cert. req.) | Earthworks | Zone E | 91880 | 76720 | 16.5% | 70% Zone C
3.1.3 | Import & place select fill (VENM cert. req.) | Earthworks | Zone B | 39377 | 32880 | 16.5% | 30% Zone B
3.1.4 | Excavate unsuitable mat. & replace w/ approved fill | Earthworks | Zone B | 56562 | 46950 | 16.99%
3.1.5 | Excavation in rock, Class A (jack hammer/rock saw) | Earthworks | Zone A | 89824.3 | 77079 | 14.19% | check qty vs dwg rev D
3.1.6 | Batter shaping & topsoil respread 100mm | Earthworks | Zone A | 36885.1 | 31186 | 15.45% | incl. cartage
4.1.1 | Concrete footpath 125thk broom finish | Concrete | Zone B | 253840 | 229632 | 9.537%
4.1.2 | Supply & fix reinforcement (all grades) * | Concrete | Zone C | 89764 | 79600 | 11.32% | 50% Zone C
4.1.2 | Supply & fix reinforcement (all grades) * | Concrete | Zone B | 94864.96 | 79600 | 16.09% | 50% Zone B
4.1.3 | Pram ramps to AS1428.1 incl. TGSIs | Concrete | Zone B | 6463.25 | 5400 | 16.45% | quote expires 30/7
4.1.4 | Kerb & channel B2 barrier type (machine extruded) * | Concrete | Zone B | 87004 | 72380 | 16.81% | 70% Zone B
4.1.4 | Kerb & channel B2 barrier type (machine extruded) * | Concrete | Zn C | 37287.77 | 31020 | 16.81% | 30% Zone C
4.1.5 | Supply & place N40 slab on grade 200thk incl. SL82 | Concrete | Zone B | 155152.2 | 130900 | 15.63% | allow for wet weather
4.1.6 | Vehicle crossings 150thk reinforced | Concrete | Zone B | 7395.05 | 5893 | 20.31% | check qty vs dwg rev D
5.1.1 | Prime & 2 coat seal 14/7 (incl. sweep) | Pavements & Surfacing | Zone B | 133639.89 | 107300 | 19.71% | incl. cartage
5.1.2 | AC10 wearing course 30thk (A15E on approaches) | Pavements & Surfacing | Zone D | 53889.05 | 45900 | 14.82%
5.1.3 | Supply & place DGS40 subbase 200thk compacted | Pavements & Surfacing | Zone B | 194307 | 164720 | 15.23% | 40% Zone B
5.1.3 | Supply & place DGS40 subbase 200thk compacted | Pavements & Surfacing | Zone C | 170019 | 144130 | 15.23% | 35% Zone C
5.1.3 | Supply & place DGS40 subbase 200thk compacted | Pavements & Surfacing | Zone D | 121441.5 | 102950 | 15.23% | 25% Zone D
5.2.1 | Longitudinal linemarking & RRPMs as per dwgs | Pavements & Surfacing | Zone D | 28931.56 | 24960 | 13.73% | sub quote - CivilTech 14/6
5.2.2 | Segmental paving to median (Urbanstone or equiv.) | Pavements & Surfacing | Zone B | 83190 | 68431 | 17.74% | quote expires 30/7
5.2.3 | Supply & place DGB20 basecourse 150thk | Pavements & Surfacing | Zone D | 238637 | 205358 | 13.95% | 45% Zone D
5.2.3 | Supply & place DGB20 basecourse 150thk | Pavements & Surfacing | Zone C | 185606 | 159722 | 13.95% | 35% Zone C
5.2.3 | Supply & place DGB20 basecourse 150thk | Pavements & Surfacing | Zone B | 106061.1 | 91270 | 13.95% | 20% Zone B
6.1.1 | Handrail - galv. tube to AS1657 | Concrete | Zone D | 62489.53 | 52206 | 16.46%
6.1.2 | Reinforced blockwork retaining wall H<1.8m incl. found. | Concrete | Zone B | 355259.52 | 311264 | 12.38%
6.2.1 | Guardrail w-beam incl. terminals (public road spec) | Concrete | Zone D | 93786 | 77350 | 17.53% | quote expires 30/7
6.2.2 | Precast L-wall units supply & install | Concrete | Zone D | 222496 | 183837 | 17.38% | 70% Zone D
6.2.2 | Precast L-wall units supply & install | Concrete | Zone B | 95356 | 78787 | 17.38% | 30% Zone B
6.2.3 | Structural steel - galv. incl. shop dwgs (S&E) | Concrete | Zone D | 100162.59 | 81150 | 18.98% | carried from tender est.
| TOTALS |  |  | 3814308.61 | 3246483 | 14.89%