## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | Preliminaries & Site Establishment |  |  |  | 57831.54
1.1 | Establishment |  |  |  | 44040.78
1.1.1 | Environmental controls - sed. fence, shaker grid etc | LS | 1 | 8385.78 | 8385.78
1.1.2 | Site office, amenities & temp fencing | wk | 30 | 1188.5 | 35655
1.2 | Ongoing Site Costs |  |  |  | 13790.76
1.2.1 | Survey & set-out (all works) | item | 1 | 10356.5 | 10356.5
1.2.2 | Dilapidation surveys & CCTV existing assets | ea | 1.06 | 3239.87 | 3434.26
2 | Demolition & Site Clearing |  |  |  | 87794.75
2.1 | Demolition & Site Clearing |  |  |  | 87794.75
2.1.1 | Demolish exist. structures & cart away | LS | 1 | 18350.7231 | 18350.72
2.1.2 | Clear & grub incl. removal offsite | m² | 7204.42 | 2.2 | 15849.72
2.1.3 | Strip topsoil 150mm & stockpile on site | m³ | 2229.9 | 11.7769 | 26261.31
2.1.4 | Remove exist. kerb & channel & dispose | lm | 358 | 23.5 | 8413
2.1.5 | Remove trees incl. stump grinding (arborist sup.) | each | 11 | 1720 | 18920
3 | BULK & DETAILED EARTHWORKS |  |  |  | 292884.6
3.1 | Bulk & Detailed Earthworks |  |  |  | 292884.6
3.1.1 | Trim & proof roll subgrade (incl. Level 1 testing) | m² | 8852.92 | 3.38 | 29922.87
3.1.2 | Import & place select fill (VENM cert. req.) (refer dwg C-306) | t | 3109.2 | 36.3389 | 112984.91
3.1.3 | Excavate unsuitable mat. & replace w/ approved fill | m3 | 1571 | 60 | 94260
3.1.4 | Batter shaping & topsoil respread 100mm | m² | 8178.91 | 4 | 32715.64
3.1.5 | Excavation in rock, Class A (jack hammer/rock saw) | m³ | 188 | 122.3467 | 23001.18
4 | STRUCTURES & RETAINING |  |  |  | 824179.43
4.1 | Structures & Retaining |  |  |  | 824179.43
4.1.1 | Reinforced blockwork retaining wall H<1.8m incl. found. | m2 | 600 | 717.0954 | 430257.24
4.1.2 | Guardrail w-beam incl. terminals (public road spec) | m | 544 | 133.57 | 72662.08
4.1.3 | Precast L-wall units supply & install | each | 140 | 938 | 131320
4.1.4 | Chainwire fencing 1.8m incl. gates | m | 808.72 | 107.44 | 86888.88
4.1.5 | Structural steel — galv. incl. shop dwgs (S&E) | tonne | 15.5 | 3606.62 | 55902.61
4.1.6 | Handrail - galv. tube to AS1657 | m | 222.2 | 212.19 | 47148.62
5 | LANDSCAPING & URBAN DESIGN |  |  |  | 206802.74
5.1 | Landscaping & Urban Design - Part A |  |  |  | 97225.74
5.1.1 | Turf - kikuyu rolls incl. estab. watering 12wks | m2 | 4298.4 | 15.79 | 67871.74
5.1.2 | Irrigation to medians - drip incl. controller | item | 1 | 29354 | 29354
5.2 | Landscaping & Urban Design - Part B |  |  |  | 109577
5.2.1 | Garden beds - mulch 75thk & planting as per LA dwgs | m² | 1192 | 62 | 73904
5.2.2 | Street trees 100L incl. staking, guard & 12mth maint. * | No. | 66 | 540.5 | 35673
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 131690.64
P.1 | Provisional Sums & Quantities |  |  |  | 131690.64
P.1.1 | Service relocations - allowance (PROV SUM) | LS | 1 | 19577.5 | 19577.5
P.1.2 | Latent conditions allowance (PROV SUM) | item | 1 | 30149.24 | 30149.24
P.1.3 | Rock excavation over & above measured qty (PROV) | m3 | 486 | 168.65 | 81963.9
|  |  |  | TOTAL | 1601183.7

## Budget
Sunshine Coast Foreshore Renewal - Stage 2
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Sunshine Coast Council |  | Prepared: 12/06/2026 ¦ Rev B ¦ S. Nguyen
Budget method: Cost Centre + Zones / Resource Breakdown
Item Code | Description | Cost Centre | Zone | Resource Category | BOQ ($) | Budget ($) | Notes
1.1.1 | Environmental controls - sed. fence, shaker grid etc | Overheads / Prelims | Project Wide | Labour | 3355 | 2841
|  | Overheads / Prelims | Project Wide | Miscellaneous | 2608 | 2208
|  | Overheads / Prelims | Project Wide | Plant and Equipment | 1630 | 1380
|  | Overheads / Prelims | Project Wide | Subcontract | 792.78 | 671
| 1.1.1 subtotal |  |  |  | 8385.78 | 7100
1.1.2 | Site office, amenities & temp fencing | Overheads / Prelims | Project Wide | Labour | 21047 | 18522 | allow for wet weather
|  | Overheads / Prelims | Project Wide | Miscellaneous | 14608 | 12855
| 1.1.2 subtotal |  |  |  | 35655 | 31377
1.2.1 | Survey & set-out (all works) | Overheads / Prelims | Project Wide | Labour | 4385 | 3810
|  | Overheads / Prelims | Project Wide | Miscellaneous | 3035 | 2638
|  | Overheads / Prelims | Project Wide | Plant and Equipment | 1867 | 1623
|  | Overheads / Prelims | Project Wide | Subcontract | 1069.5 | 929
| 1.2.1 subtotal |  |  |  | 10356.5 | 9000
1.2.2 | Dilapidation surveys & CCTV existing assets | Overheads / Prelims | Project Wide | Labour | 1438 | 1269
|  | Overheads / Prelims | Project Wide | Miscellaneous | 997 | 880
|  | Overheads / Prelims | Project Wide | Plant and Equipment | 610 | 539
|  | Overheads / Prelims | Project Wide | Subcontract | 389.26 | 342 | check qty vs dwg rev D
| 1.2.2 subtotal |  |  |  | 3434.26 | 3030
2.1.1 | Demolish exist. structures & cart away | Earthworks | Zone B | Plant and Equipment | 12994 | 11200
|  | Earthworks | Zone B | Labour | 5356.72 | 4617
| 2.1.1 subtotal |  |  |  | 18350.72 | 15817
2.1.2 | Clear & grub incl. removal offsite | Earthworks | Zone A | Plant and Equipment | 8126 | 6719
|  | Earthworks | Zone A | Labour | 3984 | 3294
|  | Earthworks | Zone A | Subcontract | 3739.72 | 3092
| 2.1.2 subtotal |  |  |  | 15849.72 | 13105
2.1.3 | Strip topsoil 150mm & stockpile on site | Earthworks | Zone B | Plant and Equipment | 12944 | 10506
|  | Earthworks | Zone B | Labour | 6477 | 5257
|  | Earthworks | Zone B | Subcontract | 6840.31 | 5551
| 2.1.3 subtotal |  |  |  | 26261.31 | 21314
2.1.4 | Remove exist. kerb & channel & dispose | Earthworks | Zone A | Plant and Equipment | 4455 | 3699 | allow for wet weather
|  | Earthworks | Zone A | Labour | 2051 | 1703
|  | Earthworks | Zone A | Subcontract | 1513 | 1256 | allow for wet weather
|  | Earthworks | Zone A | Miscellaneous | 394 | 328
| 2.1.4 subtotal |  |  |  | 8413 | 6986
2.1.5 | Remove trees incl. stump grinding (arborist sup.) | Earthworks | Zone B | Plant and Equipment | 9253 | 7947
|  | Earthworks | Zone B | Labour | 4785 | 4109
|  | Earthworks | Zone B | Subcontract | 3718 | 3193
|  | Earthworks | Zone B | Miscellaneous | 1164 | 1001
| 2.1.5 subtotal |  |  |  | 18920 | 16250
3.1.1 | Trim & proof roll subgrade (incl. Level 1 testing) | Earthworks | Zone C | Plant and Equipment | 21622 | 19040
|  | Earthworks | Zone C | Labour | 8300.87 | 7310
| 3.1.1 subtotal |  |  |  | 29922.87 | 26350
3.1.2 | Import & place select fill (VENM cert. req.) (refer dwg C-306) | Earthworks | Zone C | Plant and Equipment | 72229 | 63257
|  | Earthworks | Zone C | Labour | 24791 | 21711 | quote expires 30/7
|  | Earthworks | Zone C | Material | 15964.91 | 13982
| 3.1.2 subtotal |  |  |  | 112984.91 | 98950
3.1.3 | Excavate unsuitable mat. & replace w/ approved fill | Earthworks | Zone C | Plant and Equipment | 48241 | 41152
|  | Earthworks | Zone C | Labour | 21093 | 17994 | carried from tender est.
|  | Earthworks | Zone C | Material | 14997 | 12794
|  | Earthworks | Zone C | Miscellaneous | 9929 | 8469 | rate ex GST
| 3.1.3 subtotal |  |  |  | 94260 | 80409
3.1.4 | Batter shaping & topsoil respread 100mm | Earthworks | Zone C | Plant and Equipment | 13630 | 12352
|  | Earthworks | Zone A | Plant and Equipment | 5842 | 5293 | incl. cartage
|  | Earthworks | Zone C | Labour | 6016 | 5452 | quote expires 30/7
|  | Earthworks | Zone A | Labour | 2578 | 2336
|  | Earthworks | Zone C | Material | 3255 | 2949
|  | Earthworks | Zone A | Material | 1394.64 | 1264 | site mtg 2/7 - qty TBC w/ super
| 3.1.4 subtotal |  |  |  | 32715.64 | 29646
3.1.5 | Excavation in rock, Class A (jack hammer/rock saw) | Earthworks | Zone C | Plant and Equipment | 13953 | 12131
|  | Earthworks | Zone C | Labour | 5870 | 5104
|  | Earthworks | Zone C | Material | 3178.18 | 2763
| 3.1.5 subtotal |  |  |  | 23001.18 | 19998
4.1.1 | Reinforced blockwork retaining wall H<1.8m incl. found. | Concrete | Zone D | Subcontract | 175194 | 156746
|  | Concrete | Zone D | Material | 132682 | 118710
|  | Concrete | Zone D | Labour | 74844 | 66962
|  | Concrete | Zone D | Plant and Equipment | 47537.24 | 42532
| 4.1.1 subtotal |  |  |  | 430257.24 | 384950
4.1.2 | Guardrail w-beam incl. terminals (public road spec) | Concrete | Zone B | Subcontract | 20582 | 17900
|  | Concrete | Zone D | Subcontract | 20583 | 17900
|  | Concrete | Zone B | Material | 15749 | 13696
|  | Concrete | Zone D | Material | 15748.08 | 13695 | carried from tender est.
| 4.1.2 subtotal |  |  |  | 72662.08 | 63191
4.1.3 | Precast L-wall units supply & install | Concrete | Zone B | Subcontract | 62819 | 56950
|  | Concrete | Zone B | Material | 41698 | 37802
|  | Concrete | Zone B | Labour | 26803 | 24298 | sub quote - CivilTech 14/6
| 4.1.3 subtotal |  |  |  | 131320 | 119050
4.1.4 | Chainwire fencing 1.8m incl. gates | Concrete | Zone D | Subcontract | 25418 | 23199
|  | Concrete | Zone B | Subcontract | 10894 | 9942
|  | Concrete | Zone D | Material | 24782 | 22618
|  | Concrete | Zone B | Material | 10621 | 9693
|  | Concrete | Zone D | Labour | 10622 | 9694
|  | Concrete | Zone B | Labour | 4551.88 | 4154
| 4.1.4 subtotal |  |  |  | 86888.88 | 79300
4.1.5 | Structural steel — galv. incl. shop dwgs (S&E) | Concrete | Zone D | Subcontract | 17800 | 16033 | quote expires 30/7
|  | Concrete | Zone B | Subcontract | 11867 | 10688
|  | Concrete | Zone D | Material | 15741 | 14177
|  | Concrete | Zone B | Material | 10494.61 | 9452
| 4.1.5 subtotal |  |  |  | 55902.61 | 50350
4.1.6 | Handrail - galv. tube to AS1657 | Concrete | Zone B | Subcontract | 12847 | 11409
|  | Concrete | Zone D | Subcontract | 8564 | 7606
|  | Concrete | Zone B | Material | 9826 | 8726
|  | Concrete | Zone D | Material | 6550 | 5818
|  | Concrete | Zone B | Labour | 5617 | 4989
|  | Concrete | Zone D | Labour | 3744.62 | 3326 | check qty vs dwg rev D
| 4.1.6 subtotal |  |  |  | 47148.62 | 41874
5.1.1 | Turf - kikuyu rolls incl. estab. watering 12wks | Landscaping | Zone C | Subcontract | 24020 | 20262
|  | Landscaping | Zone D | Subcontract | 10295 | 8683
|  | Landscaping | Zone C | Material | 14446 | 12186
|  | Landscaping | Zone D | Material | 6191 | 5222
|  | Landscaping | Zone C | Labour | 9044 | 7628
|  | Landscaping | Zone D | Labour | 3875.74 | 3269
| 5.1.1 subtotal |  |  |  | 67871.74 | 57250
5.1.2 | Irrigation to medians - drip incl. controller | Landscaping | Zone C | Subcontract | 15873 | 13437
|  | Landscaping | Zone C | Material | 8202 | 6943
|  | Landscaping | Zone C | Labour | 5279 | 4470
| 5.1.2 subtotal |  |  |  | 29354 | 24850
5.2.1 | Garden beds - mulch 75thk & planting as per LA dwgs | Landscaping | Zone D | Subcontract | 41664 | 35066
|  | Landscaping | Zone D | Material | 21838 | 18379
|  | Landscaping | Zone D | Labour | 10402 | 8755
| 5.2.1 subtotal |  |  |  | 73904 | 62200
5.2.2 | Street trees 100L incl. staking, guard & 12mth maint. * | Landscaping | Zone C | Subcontract | 23655 | 20424
|  | Landscaping | Zone C | Material | 12018 | 10376
| 5.2.2 subtotal |  |  |  | 35673 | 30800