## BOQ
Item Code | Description | Unit | Qty | Rate ($) | Amount ($)
1 | PRELIMINARIES & SITE ESTABLISHMENT |  |  |  | 98116.09
1.1 | Preliminaries & Site Establishment |  |  |  | 98116.09
1.1.1 | Project signage as per spec cl 4.2 | each | 2 | 2244 | 4488
1.1.2 | Site office, amenities & temp fencing | wks | 18.4 | 1995.5 | 36717.2
1.1.3 | Dilapidation surveys & CCTV existing assets * | item | 2.78 | 3789.7615 | 10535.54
1.1.4 | Environmental controls - sed. fence, shaker grid etc | item | 1 | 11917.5967 | 11917.6
1.1.5 | Site establishment, mobilisation & demob | item | 1 | 20343.1534 | 20343.15
1.1.6 | Survey & set-out (all works) | LS | 1 | 14114.6002 | 14114.6
2 | DEMOLITION & SITE CLEARING |  |  |  | 117621.9
2.1 | Demolition & Site Clearing |  |  |  | 117621.9
2.1.1 | Remove exist. kerb & channel & dispose (refer dwg C-201) | m | 631 | 15 | 9465
2.1.2 | Remove trees incl. stump grinding (arborist sup.) | each | 10.9 | 1625.51 | 17718.06
2.1.3 | Strip topsoil 150mm & stockpile on site | m³ | 3440 | 8 | 27520
2.1.4 | Demolish exist. structures & cart away | LS | 1 | 37541 | 37541
2.1.5 | Saw cut & demolish exist. concrete pavement | m2 | 324 | 32 | 10368
2.1.6 | Clear & grub incl. removal offsite | m² | 5435 | 2.7617 | 15009.84
3 | Bulk & Detailed Earthworks |  |  |  | 476078.21
3.1 | Bulk & Detailed Earthworks |  |  |  | 476078.21
3.1.1 | Batter shaping & topsoil respread 100mm | m² | 2914.58 | 5.5 | 16030.19
3.1.2 | Import & place select fill (VENM cert. req.) | t | 815 | 53.1327 | 43303.15
3.1.3 | Excavate unsuitable mat. & replace w/ approved fill | m³ | 575 | 67 | 38525
3.1.4 | Excavation in rock, Class A (jack hammer/rock saw) | m³ | 476 | 188 | 89488
3.1.5 | Bulk earthworks - cut to fill on site | m³ | 19418 | 13 | 252434
3.1.6 | Trim & proof roll subgrade (incl. Level 1 testing) | m2 | 9452.57 | 3.84 | 36297.87
4 | Concrete Works |  |  |  | 465994.91
4.1 | Insitu Concrete |  |  |  | 345983.49
4.1.1 | Supply & fix reinforcement (all grades) | tonne | 55 | 2062 | 113410
4.1.2 | Supply & place N32 conc. footings incl. exc. & reo | m3 | 471 | 493.7866 | 232573.49
4.2 | Kerbs, Paths & Minor Conc. |  |  |  | 120011.42
4.2.1 | Vehicle crossings 150thk reinforced | m² | 289 | 119 | 34391
4.2.2 | Concrete footpath 125thk broom finish (refer dwg C-105) | m² | 316 | 63.5 | 20066
4.2.3 | Kerb & channel B2 barrier type (machine extruded) | lm | 1059.7 | 61.8613 | 65554.42
5 | Stormwater Drainage |  |  |  | 255388.67
5.1 | Pipelines |  |  |  | 73278.38
5.1.1 | Supply & lay 450dia RCP RRJ Cl.3 | lm | 196.47 | 250.46 | 49207.88
5.1.2 | Grated inlet pits SA2 type incl. lintel | each | 4.5 | 5349 | 24070.5
5.2 | Pits & Structures |  |  |  | 182110.29
5.2.1 | Junction pits 900x900 precast incl. lid | ea | 20 | 4483 | 89660
5.2.2 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | m | 452.6 | 204.2649 | 92450.29
6 | LANDSCAPING & URBAN DESIGN |  |  |  | 199922.96
6.1 | Landscaping & Urban Design - Part A |  |  |  | 115759.36
6.1.1 | Turf - kikuyu rolls incl. estab. watering 12wks | sqm | 5161 | 20.6637 | 106645.36
6.1.2 | Garden beds - mulch 75thk & planting as per LA dwgs | m2 | 217 | 42 | 9114
6.2 | Landscaping & Urban Design - Part B |  |  |  | 84163.6
6.2.1 | Street furniture - seats, bins & bike hoops * | item | 1 | 21312 | 21312
6.2.2 | Imported topsoil 100thk spread to verges | m3 | 4489.4 | 14 | 62851.6
P | PROVISIONAL ITEMS & DAYWORKS |  |  |  | 80292.74
P.1 | Provisional Sums & Quantities |  |  |  | 80292.74
P.1.1 | Latent conditions allowance (PROV SUM) | LS | 1 | 42126 | 42126
P.1.2 | Service relocations - allowance (PROV SUM) | LS | 1 | 34863 | 34863
P.1.3 | Dayworks - project engineer | hrs | 21 | 157.3208 | 3303.74
|  |  |  | TOTAL | 1693415.48

## Budget
Bendigo GovHub - External Works & Carpark
INTERNAL COST BUDGET - CONFIDENTIAL - NOT FOR ISSUE
Client: Regional Development Victoria |  | Prepared: 23/06/2026 ¦ Rev 0 ¦ estimating team
Budget method: Cost Centre + Zones / Resource Breakdown
Item Code | Description | Cost Centre | Zone | Resource Category | BOQ ($) | Budget ($) | Notes
1.1.1 | Project signage as per spec cl 4.2 | Overheads / Prelims | Project Wide | Labour | 2775 | 2304 | check qty vs dwg rev D
|  | Overheads / Prelims | Project Wide | Miscellaneous | 1713 | 1423
| 1.1.1 subtotal |  |  |  | 4488 | 3727
1.1.2 | Site office, amenities & temp fencing | Overheads / Prelims | Project Wide | Labour | 13860 | 11410
|  | Overheads / Prelims | Project Wide | Miscellaneous | 13652 | 11239
|  | Overheads / Prelims | Project Wide | Plant and Equipment | 9205.2 | 7577
| 1.1.2 subtotal |  |  |  | 36717.2 | 30226
1.1.3 | Dilapidation surveys & CCTV existing assets * | Overheads / Prelims | Project Wide | Labour | 6140 | 5129
|  | Overheads / Prelims | Project Wide | Miscellaneous | 4395.54 | 3671
| 1.1.3 subtotal |  |  |  | 10535.54 | 8800
1.1.4 | Environmental controls - sed. fence, shaker grid etc | Overheads / Prelims | Project Wide | Labour | 5030 | 4453 | quote expires 30/7
|  | Overheads / Prelims | Project Wide | Miscellaneous | 3579 | 3168
|  | Overheads / Prelims | Project Wide | Plant and Equipment | 2193 | 1941
|  | Overheads / Prelims | Project Wide | Subcontract | 1115.6 | 988
| 1.1.4 subtotal |  |  |  | 11917.6 | 10550
1.1.5 | Site establishment, mobilisation & demob | Overheads / Prelims | Project Wide | Labour | 8575 | 7777
|  | Overheads / Prelims | Project Wide | Miscellaneous | 7031 | 6376
|  | Overheads / Prelims | Project Wide | Plant and Equipment | 4737.15 | 4297
| 1.1.5 subtotal |  |  |  | 20343.15 | 18450
1.1.6 | Survey & set-out (all works) | Overheads / Prelims | Project Wide | Labour | 6028 | 5468
|  | Overheads / Prelims | Project Wide | Miscellaneous | 5072 | 4601
|  | Overheads / Prelims | Project Wide | Plant and Equipment | 3014.6 | 2734
| 1.1.6 subtotal |  |  |  | 14114.6 | 12803
2.1.1 | Remove exist. kerb & channel & dispose (refer dwg C-201) | Earthworks | Zone B | Plant and Equipment | 4648 | 3854
|  | Earthworks | Zone B | Labour | 2291 | 1900
|  | Earthworks | Zone B | Subcontract | 2060 | 1709
|  | Earthworks | Zone B | Miscellaneous | 466 | 386
| 2.1.1 subtotal |  |  |  | 9465 | 7849
2.1.2 | Remove trees incl. stump grinding (arborist sup.) | Earthworks | Zone A | Plant and Equipment | 12316 | 10622
|  | Earthworks | Zone A | Labour | 5402.06 | 4659
| 2.1.2 subtotal |  |  |  | 17718.06 | 15281
2.1.3 | Strip topsoil 150mm & stockpile on site | Earthworks | Zone B | Plant and Equipment | 17524 | 14391
|  | Earthworks | Zone B | Labour | 9996 | 8209
| 2.1.3 subtotal |  |  |  | 27520 | 22600
2.1.4 | Demolish exist. structures & cart away | Earthworks | Zone B | Plant and Equipment | 18971 | 16738
|  | Earthworks | Zone B | Labour | 9870 | 8708 | allow for wet weather
|  | Earthworks | Zone B | Subcontract | 8700 | 7675 | PC sum
| 2.1.4 subtotal |  |  |  | 37541 | 33121
2.1.5 | Saw cut & demolish exist. concrete pavement | Earthworks | Zone B | Plant and Equipment | 5311 | 4655
|  | Earthworks | Zone B | Labour | 2848 | 2496
|  | Earthworks | Zone B | Subcontract | 2209 | 1936
| 2.1.5 subtotal |  |  |  | 10368 | 9087
2.1.6 | Clear & grub incl. removal offsite | Earthworks | Zone B | Plant and Equipment | 6822 | 5500 | incl. cartage
|  | Earthworks | Zone B | Labour | 4227 | 3407
|  | Earthworks | Zone B | Subcontract | 3227 | 2601
|  | Earthworks | Zone B | Miscellaneous | 733.84 | 592
| 2.1.6 subtotal |  |  |  | 15009.84 | 12100
3.1.1 | Batter shaping & topsoil respread 100mm | Earthworks | Zone A | Plant and Equipment | 8225 | 7203
|  | Earthworks | Zone A | Labour | 4007 | 3510
|  | Earthworks | Zone A | Material | 2337 | 2047
|  | Earthworks | Zone A | Miscellaneous | 1461.19 | 1279
| 3.1.1 subtotal |  |  |  | 16030.19 | 14039
3.1.2 | Import & place select fill (VENM cert. req.) | Earthworks | Zone C | Plant and Equipment | 27603 | 24090 | incl. cartage
|  | Earthworks | Zone C | Labour | 9562 | 8345
|  | Earthworks | Zone C | Material | 6138.15 | 5356
| 3.1.2 subtotal |  |  |  | 43303.15 | 37791
3.1.3 | Excavate unsuitable mat. & replace w/ approved fill | Earthworks | Zone A | Plant and Equipment | 28538 | 24667
|  | Earthworks | Zone A | Labour | 9987 | 8633 | carried from tender est.
| 3.1.3 subtotal |  |  |  | 38525 | 33300
3.1.4 | Excavation in rock, Class A (jack hammer/rock saw) | Earthworks | Zone B | Plant and Equipment | 62394 | 54558 | PC sum
|  | Earthworks | Zone B | Labour | 27094 | 23692
| 3.1.4 subtotal |  |  |  | 89488 | 78250
3.1.5 | Bulk earthworks - cut to fill on site | Earthworks | Zone A | Plant and Equipment | 153770 | 133587
|  | Earthworks | Zone A | Labour | 59557 | 51740
|  | Earthworks | Zone A | Material | 39107 | 33973 | rate ex GST
| 3.1.5 subtotal |  |  |  | 252434 | 219300
3.1.6 | Trim & proof roll subgrade (incl. Level 1 testing) | Earthworks | Zone B | Plant and Equipment | 14670 | 12447
|  | Earthworks | Zone B | Plant and Equipment | 6287 | 5335
|  | Earthworks | Zone B | Labour | 5496 | 4664 | allow for wet weather
|  | Earthworks | Zone A | Labour | 2356 | 1999
|  | Earthworks | Zone B | Material | 3158 | 2680
|  | Earthworks | Zone A | Material | 1354 | 1149 | check qty vs dwg rev D
|  | Earthworks | Zone B | Miscellaneous | 2084 | 1768 | site mtg 2/7 - qty TBC w/ super
|  | Earthworks | Zone A | Miscellaneous | 892.87 | 758
| 3.1.6 subtotal |  |  |  | 36297.87 | 30800
4.1.1 | Supply & fix reinforcement (all grades) | Concrete | Zone C | Material | 35571 | 37705
|  | Concrete | Zone B | Material | 35571 | 37706
|  | Concrete | Zone C | Labour | 21134 | 22401
|  | Concrete | Zone B | Labour | 21134 | 22403
| 4.1.1 subtotal |  |  |  | 113410 | 120215
4.1.2 | Supply & place N32 conc. footings incl. exc. & reo | Concrete | Zone C | Material | 137160 | 116145
|  | Concrete | Zone C | Labour | 95413.49 | 80795 | site mtg 2/7 - qty TBC w/ super
| 4.1.2 subtotal |  |  |  | 232573.49 | 196940
4.2.1 | Vehicle crossings 150thk reinforced | Concrete | Zone B | Material | 18149 | 15704
|  | Concrete | Zone B | Labour | 10618 | 9188
|  | Concrete | Zone B | Subcontract | 5624 | 4867
| 4.2.1 subtotal |  |  |  | 34391 | 29759
4.2.2 | Concrete footpath 125thk broom finish (refer dwg C-105) | Concrete | Zone C | Material | 12219 | 10481
|  | Concrete | Zone C | Labour | 7847 | 6730 | quote expires 30/7
| 4.2.2 subtotal |  |  |  | 20066 | 17211
4.2.3 | Kerb & channel B2 barrier type (machine extruded) | Concrete |  | Material | 24073 | 20297
|  | Concrete |  | Material | 10317 | 8699
|  | Concrete |  | Labour | 15142 | 12767
|  | Concrete |  | Labour | 6489 | 5471 | rate ex GST
|  | Concrete |  | Subcontract | 6673 | 5627
|  | Concrete |  | Subcontract | 2860.42 | 2411
| 4.2.3 subtotal |  |  |  | 65554.42 | 55272
5.1.1 | Supply & lay 450dia RCP RRJ Cl.3 | Drainage | Zone C | Material | 10470 | 9036
|  | Drainage | Zone A | Material | 10471 | 9035
|  | Drainage | Zone C | Labour | 7766 | 6702
|  | Drainage | Zone A | Labour | 7767 | 6702
|  | Drainage | Zone C | Plant and Equipment | 6367 | 5494
|  | Drainage | Zone A | Plant and Equipment | 6366.88 | 5494
| 5.1.1 subtotal |  |  |  | 49207.88 | 42463
5.1.2 | Grated inlet pits SA2 type incl. lintel | Drainage | Zone C | Material | 10089 | 8893
|  | Drainage | Zone C | Labour | 6730 | 5932
|  | Drainage | Zone C | Plant and Equipment | 4916 | 4333
|  | Drainage | Zone C | Subcontract | 2335.5 | 2059
| 5.1.2 subtotal |  |  |  | 24070.5 | 21217
5.2.1 | Junction pits 900x900 precast incl. lid | Drainage | Zone B | Material | 18752 | 16688
|  | Drainage | Zone A | Material | 18752 | 16689 | sub quote - CivilTech 14/6
|  | Drainage | Zone B | Labour | 11930 | 10618
|  | Drainage | Zone A | Labour | 11931 | 10617
|  | Drainage | Zone B | Plant and Equipment | 9328 | 8302 | carried from tender est.
|  | Drainage | Zone A | Plant and Equipment | 9328 | 8301
|  | Drainage | Zone B | Subcontract | 4820 | 4289
|  | Drainage | Zone A | Subcontract | 4819 | 4289
| 5.2.1 subtotal |  |  |  | 89660 | 79793
5.2.2 | Supply & lay 375dia RCP RRJ Cl.2-3 incl. bedding | Drainage | Zone B | Material | 21982 | 18342
|  | Drainage | Zone A | Material | 21981 | 18342 | carried from tender est.
|  | Drainage | Zone B | Labour | 12772 | 10658
|  | Drainage | Zone A | Labour | 12773 | 10657
|  | Drainage | Zone B | Plant and Equipment | 11471 | 9572
|  | Drainage | Zone A | Plant and Equipment | 11471.29 | 9572
| 5.2.2 subtotal |  |  |  | 92450.29 | 77143
6.1.1 | Turf - kikuyu rolls incl. estab. watering 12wks | Landscaping | Zone C | Subcontract | 34481 | 29504
|  | Landscaping | Zone D | Subcontract | 34481 | 29503
|  | Landscaping | Zone C | Material | 18842 | 16122
|  | Landscaping | Zone D | Material | 18841.36 | 16121 | check qty vs dwg rev D
| 6.1.1 subtotal |  |  |  | 106645.36 | 91250
6.1.2 | Garden beds - mulch 75thk & planting as per LA dwgs | Landscaping | Zone D | Subcontract | 4717 | 3985
|  | Landscaping | Zone D | Material | 2960 | 2501
|  | Landscaping | Zone D | Labour | 1437 | 1214
| 6.1.2 subtotal |  |  |  | 9114 | 7700
6.2.1 | Street furniture - seats, bins & bike hoops * | Landscaping | Zone C | Subcontract | 11630 | 9687
|  | Landscaping | Zone C | Material | 6226 | 5185
|  | Landscaping | Zone C | Labour | 3456 | 2878
| 6.2.1 subtotal |  |  |  | 21312 | 17750
6.2.2 | Imported topsoil 100thk spread to verges | Landscaping | Zone C | Subcontract | 35857 | 31110
|  | Landscaping | Zone C | Material | 17320 | 15028
|  | Landscaping | Zone C | Labour | 9674.6 | 8394
| 6.2.2 subtotal |  |  |  | 62851.6 | 54532